## Summary
Montana Resources, LLC
Operating Permit #00030
Final Comprehensive 5-Year Bond Review
2026-05-04
Reclamation Bond Summary
Item |  | Total Cost |  |  | Source, Assumptions, Adjustments, etc
DIRECT COSTS |  | FINAL BOND | PROPOSED BOND | PRELIM BOND
Task 1- Facilities, Structures, Waste, Infrastructure |  | 387331.9346 | 387331.9346 | 387331.9346
Task 2- Earthmoving (Backfilling, Grading, Ripping, Soil Placement) |  | 38722618.9469 | 38722618.9469 | 44482238.6884
Task 3- Revegetation |  | 2888366.6191 | 2888366.6191 | 3027534.0704
Task 4- Other Reclamation Activities (Years 1-5) |  | 13864279.4962 | 13864279.4962 | 14061156.8553
Task 5- Long-Term Reclamation Tasks (Years 6-33) |  | 1998566.9259 | 1998566.9259 | 3273908.5429
TOTAL DIRECT COSTS |  | 57861163.9228 | 57861163.9228 | 65232170.0915
INDIRECT COSTS |  | 2% | Discount Rate (Earned Interest)
Inflation (to next Comprehensive Review) | 2.75% | 8405684.7736 | 8405684.7736 | 5 | years
Mobilization | 4% | 2650673.9479 | 2650673.9479 |  | 1% - 10% of Inflated Direct Costs (line 18)
Contingencies | 10% | 6626684.8696 | 6626684.8696 |  | 2.5% - 10% of Inflated Direct Costs (line 18)
Engineering Redesign Fee | 5% | 3313342.4348 | 3313342.4348 |  | 2.5% - 6% of Inflated Direct Costs (line 18)
Contractor Profit/Overhead | 15% | 9940027.3044 | 9940027.3044 |  | 15% - 30% See Graph 1 (Graphs Tab)
Project Management | 2% | 1325336.9739 | 1325336.9739 |  | 2% - 7% See Graph 2 (Graphs Tab)
DEQ Indirect | 0% | 0 | 0
Other (BLM Project Management, Forest Service, etc) | 0% | 0 | 0
TOTAL INDIRECT COSTS |  | 32261750.3042 | 32261750.3042 | 39791371.214
Task 5- Long-Term Care & Maintenance (Years 6-33)* |  | 16714870.8206 | 16714870.8206 | 17308932.8443
Inflation (to next Comprehensive Review) |  | 2428225.1794 | 2428225.1794 |  | Calculated separately, not added to inflation row above
*Indirect Costs do not apply to Care & Maintenance contracts, but the applicable net discount rate (2.0%) has been corrected to assume 2.75% inflation
AREAS WITH PRE-1974 BONDING LEVEL ($500/acre) |  | 879724.313 | 878370.5301 | 878370.5301 | *Acreage corrected from 1756 (Prelim & Proposed) to 1759 (Final)
| Difference: | 1353.7829
GRAND TOTAL 5-YEAR BOND AMOUNT |  | 110145734.54 | 110144380.7571 | 123210844.6799
Existing Total Bond |  | 116905203 | 116905203 | 116905202.9493
Existing Obligated Bond Total |  | 116903653 | 116903653 | 116903651.9493 | Rounding error of $1 in Prelim Bond
Existing Unobligated Bond Total |  | 1550 | 1550 | 1551 | Rounding error of $1 in Prelim Bond
Additional Bond Needed |  | -6759468.46 | -6760822.2429 | 6305641.6799
| Reduction in Obligated | 6757918.46
| New Unobligated Total | 6759468.46

## Description
Montana Resources, LLC
Operating Permit #00030
Final Comprehensive 5-Year Bond Review
2026-05-04
Project Description
ACRONYM LIST | DEFINITION
BMFOU | Butte Mine Flooding Operable Unit
BSB | Butte Silver Bow
CZABA | Central Zone Alluvium Borrow Area
DEQ | Department of Environmental Quality
EIS | Environmental Impact Statement
EOR | Engineer of Record
EPA | Environmental Protection Agency
GMMIA | Granite Mountain Memorial Interpretive Area
IRP | Independent Review Panel
LCY | Loose Cubic Yard
LHD | Load, Haul, Dump
MCA | Montana Code Annotated
MEPA | Montana Environmental Policy Act
MMRA | Metal Mine Reclamation Act
MR | Montana Resources
OP | Operating Permit
RDS | Rock Disposal Site
Rec Plan | Reclamation Plan
ROD | Record of Decision
TSF | Tailings Storage Facility
VWP | Vibrating Wire Piezometer
WED | West Embankment Drain
YDTI | Yankee Doodle Tailings Impoundment
Task Summary - full details copied at bottom of tab
Task 1- Facilities, Structures, Waste, Infrastructure
Demolition and removal of non-BMFOU structures, excludes facilities exempt from MMRA
Removal and disposal of non-BMFOU equipment, materials, and/or hazardous wastes
Task 2- Earthmoving (Backfilling, Grading, Ripping, Soil Placement)
CZABA- Reclamation materials must be excavated for use across the entire site, tested for suitability, and separated for use. Footprint to be graded and ripped
TSF- Embankments- grading slopes, rip crests, build runoff collection ditches, haul and spread alluvium/soil, rip rap above HSB
TSF- Beach- Grading/backfilling settlement areas, haul and spread alluvium/soil. Some areas reclaimed immediately, others incrementally as pond recedes
RDS and Leach Pads- Many locations- grading slopes and crests, build runoff collection ditches, haul and spread alluvium/soil
Pits- Reslope accessible benches/roads, haul and spread alluvium/soil. Excludes Berkeley and elevations below the BMFOU PWL (5,410 ft) in Continental
Roads- general access and haul roads- grading, rip rap channel protection, build runoff collection ditches, haul and spread alluvium/soil
Stockpiles- rip surfaces in stockpile footprints after materials have been removed
Misc. Disturbance and Drill pads- grading, haul and spread alluvium/soil
Task 3- Revegetation
All reclaimed surfaces that are ripped, graded, and/or covered with alluvium or soil (cited above) to be revegetated:
Other areas to be revegetated without earthwork: McQueen Townsite, CZABA, partially reclaimed areas
Seeding/planting
Weed Control
Minor Maintenance
Tasks 4 and 5- Other Reclamation Activities and Long-Term Activities
Full details provided in the Reclamation Plan
Interim site management and maintenance while DEQ obtains bond (1 year)
Site management, maintenance, and oversight during initial reclamation ("Closure Period" years 2-5)
Site management, maintenance, and oversight during extended reclamation ("Post-Closure Period" years 6-33)
TSF- Beach- Monitoring tailings surface during drying, Dust control during closure periods (see Interim Maintenance and Post-Closure tasks)
Plug and abandon water wells and drill holes, not required for BMFOU or long-term monitoring
Monitoring-- water quality sitewide, embankment piezometer monitoring, systems maintenance, compilation of data and reporting
WED- Grout/plug lower segment of WED, repair/clean Extraction Pond, maintain electrical system, install/operate submersible pumps in Extract Basins
Repair/improve Clearwater Ditch with HDPE pipe, culverts, reinforcement mats, rip rap lined channels, maintenance
SEE ACREAGE TRACKING TAB
Facts
Comprehensive 5 year Review-- previous Final Determination issued 1/4/2026
General Assumptions:
If bond forfeiture occurs, DEQ would solicit bids for all phases of the mine reclamation project.
Based on DEQ experience at other mine sites, it is assumed the contractor would have the following earth moving equipment available.
D6 Dozer
D8T Dozer
D10T Dozer
Cat 320 Excavator
Cat 365 Excavator
Cat 720 Articulating Truck
Cat 740 Articulating Truck
Cat 950 Loader
Cat 980 Loader
6020B Shovel
14M Grader
740 Truck
777 Truck
Water Truck
Sources:
MR Permit Conditions (OP#00030) Operations and Reclamation Plans (2023)
Site Inspection Reports (2020-2025)
Annual Reports (2020-2025)
References:
Caterpillar Performance Handbook, Edition 49
Costmine Equipment Rates, 2025
Davis Bacon Heavy Highway Construction Wage Rates, January 2025
RS Means, Heavy Construction Cost Data, 2025 Q1
2023 RECLAMATION PLAN- CROSS REFERENCE TO 2025 BOND CALC
SECTION | TITLE | 2025 BOND CALC TAB
1 | INTRODUCTION | -
1.1 | PURPOSE | -
1.2 | LOCATION | AcreageTracking
1.3 | MODIFICATIONS | -
1.4 | OTHER AGENCIES INVOLVED IN RECLAMATION AT THE CONTINENTAL MINE | Description
1.4.1 | DEQ Water Quality Division, Water Protection Bureau | Description
1.4.2 | DEQ Air, Energy and Mining Division, Air Quality Bureau | Description
1.4.3 | US Army Corps of Engineers (USACE) | Description
1.4.4 | US Environmental Protection Agency (EPA) | Description
1.5 | PREPARERS | -
1.6 | REGULATORY COMPLIANCE | -
2 | LAND USE | -
2.1 | PRE-PERMIT LAND USE | -
2.2 | ADJACENT LAND USE | -
2.3 | PERMITTED LAND USE | Description
2.3.1 | Watershed Protection | -
2.3.2 | Wildlife Habitat | -
2.3.2.1 | Yankee Doodle Tailings Impoundment | -
2.3.2.2 | Continental Pit and Central Zone Alluvium Borrow Area | -
2.3.2.3 | Berkeley Pit | -
2.3.2.4 | Other Disturbances | -
2.3.3 | Ancillary Land Uses | -
2.4 | CONSISTENCY WITH BSB COMPREHENSIVE PLAN AND ZONING | -
2.4.1 | Growth Policy | -
2.4.2 | Zoning | -
3 | POST-CLOSURE TOPOGRAPHY AND DRAINAGE | Description
3.1 | POST-CLOSURE FINAL GRADING AND TOPOGRAPHY | Description
3.2 | POST-CLOSURE DRAINAGE AND CONTROLS | Description
4 | MATERIAL CHARACTERIZATION | -
4.1 | MINE WASTE CHARACTERISTICS | -
4.1.1 | Non-Ore Rock | -
4.1.2 | Tailings | -
4.2 | COVERSOIL CHARACTERISTICS | -
4.2.1 | Alluvium | Earthmoving
4.2.2 | Leached Cap | -
4.2.3 | Topsoil | Earthmoving
4.2.3.1 | Existing Disturbances | -
4.2.3.2 | Proposed Disturbances | -
4.2.3.3 | Stockpile Storage and Protection | -
4.2.4 | Preliminary Reclamation Coversoil Monitoring Results | Earthmoving
4.3 | COVERSOIL BALANCE | Earthmoving
4.4 | COVERSOIL DEPTHS | Earthmoving
4.5 | DECOMPACTION | Earthmoving
5 | AMENDMENTS | Earthmoving
5.1 | LIME | Earthmoving
5.2 | ORGANIC MATTER | Earthmoving
5.3 | FERTILIZER | Earthmoving
6 | REVEGETATION | Revegetation
6.1 | SPECIES SELECTION AND SEED MIXTURES | Revegetation
6.2 | SEEDBED PREPARATION | Revegetation
6.3 | SEEDING SCHEDULE AND METHODS | Revegetation
6.4 | TREE PLANTING | Revegetation
6.5 | INTERIM REVEGETATION | -
7 | EROSION AND SEDIMENT CONTROL | Earthmoving
7.1 | SOIL STABILIZATION | Earthmoving
7.2 | MAINTENANCE AND REPAIRS | Earthmoving
8 | RECLAMATION BY MINE COMPONENT
8.1 | YANKEE DOODLE TAILINGS IMPOUNDMENT | Earthmoving, Revegetation
8.1.1 | Embankment Slopes and Crest | Earthmoving, Revegetation
8.1.2 | Beach | Earthmoving, Revegetation
8.1.3 | Post-Closure Pond and Transition Zone | Earthmoving, Revegetation, Other, Long-Term
8.1.4 | Closure Spillway | Other
8.1.5 | West Embankment Drain and Pond | Other
8.2 | ROCK DISPOSAL SITES | Earthmoving, Revegetation
8.2.1 | East RDS Complex | Earthmoving, Revegetation
8.2.1.1 | Hillcrest RDS | Earthmoving, Revegetation
8.2.1.2 | East RDS | Earthmoving, Revegetation
8.2.1.3 | North East RDS | Earthmoving, Revegetation
8.2.2 | North RDS | Earthmoving, Revegetation
8.2.3 | Great Northern RDS | Earthmoving, Revegetation
8.2.4 | Pittsmont RDS | Earthmoving, Revegetation
8.2.5 | Woodville RDS | Earthmoving, Revegetation
8.2.6 | Access RDS | Earthmoving, Revegetation
8.2.7 | Nalley Valley RDS | Earthmoving, Revegetation
8.2.8 | South Continental Pit RDS | Earthmoving, Revegetation
8.2.9 | Horseshoe Bend RDS | Earthmoving, Revegetation
8.3 | PITS | Earthmoving, Revegetation
8.3.1 | Berkeley Pit | Description
8.3.2 | Continental Pit | Earthmoving, Revegetation
8.3.3 | Central Zone Alluvium Borrow Area | Earthmoving, Revegetation
8.4 | LEACH PADS | Earthmoving, Revegetation
8.5 | SUPPORT FACILITIES | Facilities, Earthmoving, Revegetation
8.5.1 | MMRA Facilities | Facilities, Earthmoving, Revegetation
8.5.2 | Exempt Facilities | AcreageTracking, Facilities
8.6 | SOIL STOCKPILE AREA RECLAMATION | Earthmoving, Revegetation
8.7 | ALLUVIUM AND LEACHED CAP STOCKPILE AREA RECLAMATION | Earthmoving, Revegetation
8.8 | MINE AND ACCESS ROADS | Earthmoving, Revegetation
8.9 | LONG-TERM MONITORING SITES | Earthmoving, Other
8.9.1 | Monitoring Wells and Drillholes | Other
8.9.2 | Trenches and Test Pits | Other
8.9.3 | Monitoring Access Roads | Earthmoving, Revegetation
8.1 | BMFOU INFRASTRUCTURE | Description, Facilities
9 | RECLAMATION SCHEDULE | Description
10 | MANAGEMENT AND MONITORING | Other, Long-Term
10.1 | PERMANENT EROSION AND SEDIMENT CONTROL | Earthmoving
10.2 | YDTI FACILITIES | Other, Long-Term
10.2.1 | Quantitative Performance Parameters | Other, Long-Term
10.2.2 | Monitoring Frequency | Other, Long-Term
10.2.3 | Inspections and Reviews | Other, Long-Term
10.2.3.1 | Engineer of Record | Other, Long-Term
10.2.3.2 | Independent Review Panel | Other, Long-Term
10.2.4 | Post-Closure WED Management | Description
10.2.5 | Post-Closure Beach and Pond Management and Monitoring | Other, Long-Term
10.3 | COVERSOIL TESTING | Earthmoving
10.4 | REVEGETATION MONITORING AND MANAGEMENT | Other, Long-Term
10.4.1 | First Growing Season Monitoring | Other
10.4.1.1 | Perennial Grass Seedling Establishment | Other
10.4.1.2 | Erosion | Earthmoving
10.4.1.3 | Invasive Species | Other
10.4.2 | Subsequent Growing Season Monitoring | Other, Long-Term
10.4.2.1 | Canopy Cover and Species Composition | Other
10.4.3 | Revegetation Management | Other
10.5 | WATER RESOURCES MONITORING | Other, Long-Term
10.6 | DUST CONTROL | Other, Long-Term
10.7 | WEED MANAGEMENT | Revegetation, Other, Long-Term
Schedule:
Background - Land Use and Other Stakeholders
Background - Permit History and Bonding Levels
Task 1- Facilities (Structures, Waste, Infrastructure)
Task 2- Earthmoving (Backfilling, Grading, Ripping, Soil Placement)
Task 3- Revegetation
Tasks 4 and 5- Other Reclamation Activities and Long-Term Activities
3.1 POST-CLOSURE FINAL GRADING AND TOPOGRAPHY
"Post-closure final grading and topography would be of comparable utility and stability as that of adjacent areas, with the exception of open pits and rock faces (MCA 82-4-336(9)(a))." "Contour trenches, benches, and/or grass or rock-lined channelways would be installed as specific situations warrant and are discussed for each disturbance type."
"All final grading will be made with non-noxious, noncombustible solids unless approval has been granted by DEQ for a supervised sanitary landfill (MCA 82-4-336(6)).
"Upon partial or complete saturation with water, graded fill, tailings, or spoil piles will be stable. Stability of the tailings and tailings embankment is addressed in MR’s Design Document for the YDTI, reviewed by the Independent Review Panel (IRP 2017) and previously submitted to DEQ. The IRP accepted the adequacy of the proposed design."
3.2 POST-CLOSURE DRAINAGE AND CONTROLS
"Post-closure water from all nonexempt disturbed areas shall be diverted or treated in a manner designed to control siltation, erosion or other water pollution damage to streams and natural water courses (ARM 17.24.115(f). "
"Based on the post-closure reclamation details, including post-closure grading, coversoil placement and revegetation of all nonexempt disturbed areas, post-closure runoff water is expected to be of good quality. Therefore, post-closure runoff water would be handled as stormwater with the post-closure drainage system designed to convey stormwater runoff around any remaining disturbed areas. Stormwater runoff would be segregated from post-closure process waters so that stormwater runoff may be discharged directly off site, thus reducing post-closure water treatment requirements. The post-closure stormwater drainage system outlined below is intended to meet this goal while providing flexibility in runoff water handling and discharge depending on final runoff water quality." "As part of final reclamation, runoff swales and/or ditches will be constructed along reclaimed slopes as needed for runoff and erosion control (ARM 17.24.115(d)). Initial design concepts include grass-lined swales in the upper reaches of drainages, transitioning to riprap-lined ditches in the lower reaches where flow velocities warrant (Figure RP-7-1). All drainage structures, including drainage ditches A, B and C, and the upgraded Clearwater Ditch would be designed to safely convey runoff generated from the 100 year-24 hour storm event, including riprapping where flow velocities warrant. Stormwater settling basins would be placed along major drainageways to slow flow velocities and allow for settling of entrained sediment. All stormwater drainage structures and provisions would be detailed in a post-closure erosion control plan. As currently planned, all stormwater runoff would report to the south mine boundary and Clearwater Ditch for direct discharge to Silver Bow Creek, if water quality allows. The conceptual drainage system is shown on Exhibit RP-2."
2023 Reclamation Plan Citations:
2.3 PERMITTED LAND USE
"Permitted land uses were originally mining and industrial, reflecting that the majority of these areas were disturbed prior to permit issuance. Post-closure land uses of less disturbed areas were watershed protection and small mammal and bird habitat. The 1998 Reclamation Plan (MR 1998) proposed watershed protection, wildlife habitat, visual resource mitigation, historic preservation, and industrial land uses. The 6450 Amendment identified watershed protection and wildlife habitat for the YDTI and other areas covered by the Amendment."
1.4 OTHER AGENCIES INVOLVED IN RECLAMATION AT THE CONTINENTAL MINE
"The Mining Bureau of the Air, Energy and Mining Division of the DEQ has primacy in regulating reclamation at the Continental Mine pursuant to the Montana Metal Mine Reclamation Act (MMRA) and implementing regulations. Other agencies, discussed below, also have regulatory or advisory roles involving reclamation.
1.4.1 DEQ Water Quality Division, Water Protection Bureau
DEQ’s Water Protection Bureau regulates discharge from point and non-point sources pursuant to the Montana Water Quality Act (Title 75, Chapter 5, MCA). MR anticipates developing, implementing, and maintaining a Stormwater Pollution Prevention Plan (SWPPP) in early 2023 for stormwater coverage under the Multi-Sector General Permit (MSGP) for stormwater discharges associated with industrial activity such as mining.
1.4.2 DEQ Air, Energy and Mining Division, Air Quality Bureau
DEQ’s Air Quality Bureau regulates air quality pursuant to Montana’s Clean Air Act (75-2-101 et seq., MCA) and companion regulations. MR operates pursuant to Air Quality Permit #1749-14, including following procedures set forth in its “Dust Control Plan for Yankee Doodle Tailings Impoundment” (MR 2022). Dust control during operations is addressed in Section 12.0 and Appendix OP-B of MR’s Operations Plan. Post-closure dust control on the YDTI is addressed in Section 10.6 of this reclamation plan.
1.4.3 U.S. Army Corps of Engineers (USACE)
The USACE issued a jurisdictional determination on August 27, 2018 (Corps No. NWO-2011-02509-MTM) finding potential waters of the U.S. at the mine to be isolated, non-jurisdictional waters that do not require authorizations from USACE for discharges of dredge or fill material.
1.4.4 U.S. Environmental Protection Agency (EPA)
In 1983, the EPA listed Silver Bow Creek as a Superfund Site on the National Priorities List (NPL) pursuant to the Comprehensive Environmental Response, Compensation and Liability Act (CERCLA). In 1987, historic and active mine areas in the vicinity of Butte were added to the Superfund Site and the name changed to Silver Bow Creek/Butte Area. The Silver Bow Creek/Butte Area Superfund Site is separated into several operable units one of which is the BMFOU that includes MR’s overall mine permit area. As a result of the Superfund designation, mine site water is addressed under the jurisdiction of the EPA pursuant to the Consent Decree and related documents. In 2001, the EPA and DEQ Remediation Division issued a “Decision Document Regarding Deferral by EPA to State Authority for the Butte Active Mining Area Operable Unit, Silver Bow Creek/Butte Area (Butte Portion) NPL Site” (EPA 2001). As a result of the Decision Document, EPA deferred use of CERCLA authority of the Butte Active Mine Area Operable Unit (BAMAOU) conditional upon MR meeting state regulatory requirements and posting of an adequate reclamation bond. Even if these conditions were met, EPA reserved the right to exercise CERCLA authority should the reclamation plan contained in the permits not be implemented by MR and/or enforced by the State, or bonding be inadequate to cover the cost of reclamation required by the permits."
2023 Reclamation Plan
(Section 8.5.1) Non-exempt facilities not part of the BMFOU remedy would be reclaimed in accordance with the MMRA. These include, but are not limited to:
• Explosive Storage Areas;
• Powder Magazines;
• Fuel Bays;
• Relocated Precipitation Plant
• Pump stations and pipelines;
• Water Management Structures (ditches and ponds);
• Tailings Pump Houses and Booster Stations;
• Tailings Pumpback Barges (2);
• Tailings Lines;
• Return Water Lines;
• Power Lines and Substations; and
• Central Water Tower.
"All regulated support facilities that have economic value would be dismantled and sold at the end of operations. Non-economically recoverable facilities would be dismantled and inert components (concrete, steel, wood, etc.) would be buried in an on-site disposal pit. The disposal pit would be covered, capped as necessary and revegetated. Any designated waste management site in the mine permit area would operate in accordance with the substantive elements of relevant sections of ARM 17.50.509 Operation and Maintenance Plan Requirements for a solid waste management system as detailed in Section 11.0 of MR’s Operations Plan."
"Fuel, oils, chemicals and other similar material would be recycled or deposited in an approved disposal facility."
"Except for facilities also used for BMFOU, jurisdictional surface facilities and structures would be removed during final reclamation, unless DEQ approves a waiver allowing certain structures to remain if they provide a beneficial post-closure use. Service corridors (e.g., power, above ground water lines) that are necessary for BMFOU activities will remain in place. Service corridors that provide future benefits may remain in place if approved by DEQ. Otherwise, service corridors would be removed at mine closure, and disturbed areas would be reclaimed." "Facility sites would be graded to blend with adjacent areas, ripped to relieve compaction, covered with 28 inches of alluvium [if slope is <5%, 20 inches of alluvium if slope is > 5%], amended as necessary based on testing, and seeded as described in Section 6.0. "
DEQ assumes that no scrap or resale value can be discounted in the bond, so demolished facilities and associated inert components would be buried in an on-site disposal pit (exact location not identified) OR hauled to an offsite disposal facility.
DEQ Assumptions: The classification of some areas as being “grandfathered,” "pre-1971,"pre-law," or “pre-1974” acres may have been confused through historical DEQ and MR correspondence and bond calculations. The information contained in this bond has been compiled based on previous bond reviews and the best available acreage tracking and current Operations and Reclamation Plans (2023), which reflect a consolidated permit OP#00030 (combined with former 00030A, 00041, and 00108 in 2021). Areas of mining disturbance existed prior to the date the MMRA took effect (3/9/1971). Additional amendments affecting bonding practices took effect on 7/1/1974. An opinion from the Attorney General in 1977 established that “The concentrator and precipitation plant operated by the Anaconda Company in Butte, Montana, are exempted from regulation under the Hard Rock Act by section 50-1219, R.C.M. 1947, since these facilities were constructed prior to enactment.” These facilities have been referred to by many terms (see above), though it may be most helpful to refer to them as "exempt" areas. Site maps often show these as shaded areas within the Permit 00030 boundary, though they are exempt from the permit. Reclamation bond is not held for these areas ($0/acre).
The permit exemption has been applied only to specific processing facilities. Other areas of pre-1971 disturbance (e.g. tailings impoundment, leach pads, dumps, roads, Berkeley Pit) were incorporated into Permit 00030, included in the Operating and Reclamation Plans, and bonded. The bonding level for the Permit 00030 area has been limited to $500/acre, based on bonding levels applied between 1971 and 1974. Other permit areas (post-1974; former Permits 00030A, 00041, and 00108) are bonded at the estimated current cost of completing reclamation. The full costs for removal and reclamation of some facilities or structures may not be applied to the total obligated bond because they are located within former Permit #00030 (pre-1974 disturbance), thus the bond limit of $500/acre has already been applied for that location. This might give the wrong impression that the facilities themselves are exempt from bonding, but it should not be interpreted that the facilities are exempt from the permit ("pre-law" or pre-1971). The statutory limit for bonding has been applied to the all pre-1974 disturbance areas. Another distinction can be made for some features within former Permit 00030 (pre-1974 disturbance) that may not be bonded because the long-term operation, reclamation, and/or removal of facilities will be managed under Superfund activities (within Butte Mine Flooding Operable Unit). These would include the Berkeley Pit and other features associated with water management and water treatment. The facilities are exempt from bonding under MMRA, but it should not be interpreted that the facilities are exempt from the permit ("pre-law" or pre-1971).
2023 Reclamation Plan Citations:
6.0 REVEGETATION
Revegetation would be conducted to provide stabilization through erosion and sedimentation control and reestablishment of a maintenance-free vegetative cover that meets post-closure land use objectives (MCA 82-4-336(8) and (9)(a) and ARM 17.24.115(1)(c)). All areas would be revegetated to conform with county standards for noxious weed control. Revegetation methods may be modified per DEQ consultation and approval based on results of ongoing MR and other local evaluations, availability of materials, and changes in reclamation technology.
6.1 SPECIES SELECTION AND SEED MIXTURES
Plant species recommended for revegetation are based on establishment and self-perpetuation potential, rooting and other growth characteristics, soil stabilizing qualities, metal and acid tolerance, commercial availability, wildlife palatability, and aesthetics.
Species selection is based on documentation of species occurrence and community composition on: 1) adjacent, (relatively) undisturbed plant communities surveyed prior to disturbance; 2) historic disturbances in the Butte-Silver Bow area; and 3) reclaimed sites at the mine. MR proposes to revegetate disturbances using native (and a few selected naturalized) grasses that: establish readily on a wide variety of substrates; have occurred widely in the Butte reclamation landscape since the 1970’s; and are able to compete successfully with noxious weeds. Those species which are drought tolerant and locally adapted to a relatively wide range of cover material conditions (texture, pH, metal tolerance, etc.) have been emphasized.
Seeding rates have been calculated on a Pure Live Seed (PLS) basis. Broadcast seeding rates have been formulated to average approximately 120 PLS per square foot; drill seeding would be at one-half the broadcast rate. Germination success and the effects of competition between species would be evaluated to determine if rate adjustments are indicated for subsequent revegetation efforts. Quickguard sterile triticale will be seeded on steeper slopes and sites requiring rapid, non-persistent initial stabilization.
The permanent seed mixture may be modified based on limited species availability, poor initial performance, new plant material releases, or advances in reclamation technology. The seed mixture emphasizes quick-establishing species and seeding rates that are expected to provide noxious weed competition. Seed that is genotypically and phenotypically adapted to the project area and from within the Northern Rocky Mountains or Great Plains would be used when commercially available in sufficient quantity and acceptable quality.
Forbs and shrubs would also be used to selectively revegetate disturbances to provide benefits for wildlife as well as improve visual diversity and interest. Forbs and shrubs would be added to the permanent seed mixture when it has been determined that noxious weeds are under control. Forbs and shrubs would be seeded at locations and rates to be determined, based on wildlife use considerations, visual significance, slope, aspect, composition, topography, and seed availability. 6.3 SEEDBED PREPARATION
Seedbed preparation would be conducted as needed after coversoil distribution and amendment application. On slopes that are less than 33 percent, the seedbed would be prepared along the contour, utilizing a chisel-plow, disc, harrow, cultipacker, or other appropriate equipment to break up the surface and prepare a firm seedbed. On slopes that are steeper than 33 percent, too narrow to operate equipment, or on sites where, if used, organic debris has been respread, the surface would be left in a roughened condition. If needed, compacted surfaces including the RDSs and, following their removal, soil and alluvium stockpile sites, would be ripped.
6.3 SEEDING SCHEDULE AND METHODS
Seeding would normally be conducted the first season following coversoil application. If site conditions are suitable (good soil moisture, predicted rainfall, north or east-facing slope), seeding would be conducted as soon after seedbed preparation as possible. Seeding would normally be conducted in fall (after September 15), or spring (prior to mid-June) depending on soil moisture, climatic conditions, and access. Spring seedings would be conducted as early in the season as possible to maximize use of early moisture.
Two methods of seeding would be employed; broadcast and drill. Broadcast seeding would be the preferred method on rocky areas and slopes steeper than 3H:1V. Broadcast seeding would be conducted by utilizing broadcast drop seeders or comparable equipment, manually-operated cyclone-type bucket spreaders, or a mechanical seed blower. Seed would be mixed frequently in the seed boxes to discourage settling. Where possible and practical, broadcast-seeded areas would be chained or harrowed to cover the seed. Where slope conditions allow, broadcast-seeded areas may be dozer-tracked perpendicular to the slope. On small or inaccessible sites, hand raking may be used to cover seed.
When hydroseeding is used, seed, fertilizer, and mulch (about 250 pounds per acre) will be sprayed in one application. A second application will spray the remainder of the cellulose fiber mulch (to achieve a total of about one ton per acre) and a tackifier (at the manufacturer’s recommended application rates).
Drill seeding may be utilized on slopes less than 3H:1V. Drill seeding will be done along the contour wherever the surface is not level. Seeding depth will generally be ¼- to ½-inch. Drill row spacing will vary from 7 to 14 inches.
6.4 TREE PLANTING
Trees may be selectively planted to provide visual screening, increase biological diversity, and enhance wildlife habitat. Tree planting would be limited to localized groupings; “plantation-style” row plantings would be avoided. Planting rates would be based on a total of about 400 trees per acre. Tree species are listed in Table RP-6-3. Species, planting ratios, and densities would be based on slope, aspect, and moisture conditions.
MR will determine tree planting areas based on visual design elements (screening, continuity with existing stands, landscape position) and will capitalize on site conditions, such as topography and substrate, to sustain tree growth once established. Planting areas would be delineated and documented in MR’s annual reports.
8.2 ROCK DISPOSAL SITES
Non-ore rock is used to build the YDTI Embankment, pit ramps, and haul roads. Suitable non-ore rock is also used for reclamation capping and can be used, if necessary, for dust control on the YDTI beach. When not necessary for construction, non-ore rock is placed in RDSs, which are also referred to as “Waste Rock Dumps.” General reclamation methods for RDSs are specified in Appendix RP-C and include:
• reducing slopes to not steeper than 2.7H:1V (except for a short section of the East-West Embankment which will be 2H:1V);
• regrading to keep water from ponding;
• constructing benches or runoff collection ditches on regraded slopes;
• redistributing 20 inches of coversoil on slopes and 28 inches of coversoil on tops and benches;
• testing and amending alluvium, if necessary;
• if needed, applying and incorporating organic matter into some areas if topsoil is not spread over alluvium (Section 5.2); and
• establishing vegetation and controlling weeds.
8.3.2 Continental Pit Post-closure, slopes within the Continental Pit are to be reclaimed as talus slopes and highwall features. Level areas above the 5,410 elevation (approximately 5468 Anaconda Copper Mining Company (ACM) Datum) will be revegetated (see Exhibit RP-2). These areas will be regraded, ripped, covered with 28 inches of alluvium, and seeded. Areas below the 5,410 elevation would be managed under BMFOU. 8.3.3.Central Zone Alluvium Borrow Area
Although the Central Zone was previously approved as a source of capping materials, MR has conducted additional drilling and prepared a mine plan for the Central Zone (Czehura 2021) which is described in more detail in MR’s Operations Plan. Characteristics and quantities of the alluvium are presented in Section 4.2.1 of this Plan.
Reclamation of the CZABA would be similar to that of the Continental Pit described above, with regrading, ripping, and seeding of wider level areas including the pit floor, benches, and haul roads. Coversoils would likely not be necessary in the CZABA. If testing indicates a pH below 5.5, lime would be added and incorporated to raise the pH to about 6.0.
8.4 LEACH PADS
Leach pads were constructed by the ACM starting about 1963. Pads are constructed of low-grade ore and form a series of shallow depressions. Once the pads are decommissioned, they are frequently kept on site for non-ore rock disposal. The North RDS and Great Northern RDS, for example, will be placed on inactive leach pads.
If a leach pad does not become a RDS, it would be graded and/or capped with non-ore rock to eliminate depressions and the tops would be covered with 28 inches of alluvium. The slopes of the leach pads would be graded to a 2.7H:1V or flatter slope and covered with 20 inches of alluvium. Amendments may be applied based on testing results. The sites would be seeded as described in Section 6.0 and summarized in Appendix RP-C.
8.6 SOIL STOCKPILE AREA RECLAMATION
Once all soil has been removed, stockpile storage areas would be ripped to relieve compaction. Revegetation would be conducted as described in Section 6.0 and summarized in Appendix RP-C.
8.7 ALLUVIUM AND LEACHED CAP STOCKPILE AREA RECLAMATION
Alluvium stockpiles have been, and will be sited on previously disturbed ground. One stockpile area will be reclaimed as part of the North RDS; the other will be ripped if needed, capped, and seeded. When decommissioned, the Lunch Room stockpile site will be reclaimed by leaving a 28-inch layer of alluvium, amending if necessary, and seeding. There are currently no leached cap stockpile areas; however, if any are sited in the future, they would be reclaimed similarly to alluvium stockpile sites. 8.8 MINE AND ACCESS ROADS (2023 Plan + MR25-001)
"Roads not necessary for post-closure management and monitoring will be reclaimed. Reclamation will consist of grading to blend into adjacent areas, ripping compacted surfaces, covering with appropriate coversoil, and amending and revegetating as described in Section 6.0 and summarized in Appendix RP-C. Stable road cuts in rock will not be graded. Grading will be conducted to minimize surface flow over fill slopes, and with non-noxious, nonflammable, noncombustible solids. Post-closure road locations are shown on Exhibit RP-2 and include the YDTI Embankment crest, the ramps on the south and east sides of the North RDS, the road along the eastern side of the YDTI, a road that accesses the north portion of the tailings pond, the Bumtown Road, and roads to BMFOU facilities.
7.0 EROSION AND SEDIMENT CONTROL
"To the extent feasible, erosion control would be initiated promptly after completion or abandonment of the operation on those portions of the complex that would not be subject to further disturbance (MCA 82-4-336(2))."
"Final erosion control will be accomplished by establishing perennial, self-perpetuating vegetation, except in open water or on exposed alluvium and bedrock highwalls (MCA 82-4-336(8)). Potential erosion from steeper slopes such as rock disposal sites, leach pad faces, and the YDTI Embankment face would be mitigated by constructing backsloped benches across the slope to reduce slope distance. The distance between benches would vary based on site conditions. Offsite sedimentation would be controlled by a combination of on-site reclamation and erosion control, post-closure drainage system (see Section 3.2), and post-closure topography." The area peripheral to the YDTI (west, north, and east) rises upslope, thus there is a lower potential runoff and sediment yield. As described in Section 3.2, West Embankment runoff will report to multiple stormwater basins located along the embankment toe for retention and infiltration. Runoff from extreme storm events and the Probable Maximum Flood (PMF) during operations and post-closure would be contained in the YDTI. However, a contingency spillway will be constructed during reclamation of the YDTI as an emergency water management system designed to prevent overtopping of the embankment. Water (and sediment) from the YDTI would flow into the Continental Pit. The Continental Pit and CZABA, as well as the Berkeley Pit would be repositories for onsite runoff from the southern portion of the mine area. Stormwater runoff would be handled by ditches within the mine area (see Section 3.2 and Exhibit RP-2). The Clearwater Ditch captures sediment from the East RDS complex and directs flows to the Dredge Pond, where it is managed through operations and/or BMFOU."
7.1 SOIL STABILIZATION
Mulching may be conducted on areas where coversoil has been applied to provide erosion control, promote soil moisture retention, and provide supplemental organic material. Supplemental mulching may be necessary on a site-by-site basis if revegetation is not successful, or erosion is evident. Where used, mulch would be spread over seeded areas at rates dependent on seeding method and slope. Only noxious weed-free straw and cellulose fiber mulches will be used. Straw mulch will be applied at a rate of about one ton per acre on drill seeded surfaces and up to two tons per acre on steeper slopes where conventional broadcast methods are used. Straw mulch will be anchored into the seedbed using a mulch crimper, disc, or by dozer tracking. Cellulose fiber mulch will be applied at a rate of about one ton per acre on hydroseeded areas. 7.2 MAINTENANCE AND REPAIRS
Erosion and sedimentation will be monitored during reclamation evaluations (see Section 10.4). Standard maintenance practices for reclaimed sites include promoting desirable perennial species establishment through control of noxious weeds, repair of rills and gullies, and reseeding if necessary. Deposits of sediment that may undesirably impact surface flows are mitigated by removing sediment deposits and/or repairing the area to control future erosion. Where erosion or sedimentation is identified, MR will implement erosion and sediment control Best Management Practices (BMPs) to mitigate the site. Table RP-7-1 lists possible BMPS. Table RP-7-1 Erosion and Sediment Control BMPs
Erosion Control BMPs Sediment Control BMPs
Surface Roughening Silt Fence
Vegetation Establishment Straw/Coir Wattles
Check Dams Earthen Berms
Runoff Diversion Ditches Sediment Traps/Basins
Slope Drains Sediment Removal
Erosion Control Blankets
Mulching
Erosion or sediment control BMPs would be determined on a case-by-case basis and installed per manufacturer’s recommendations. MR would consult DEQ’s “Field Guide for Best Management Practices” (DEQ 2014) for installation procedures.
Reclaimed areas redisturbed by erosion or sediment control BMPs will be reseeded where established vegetation is removed. Any repair work will be documented in annual reports.
2023 Reclamation Plan: 8.1.1 TSF Reclamation The North-South and East-West Embankments are constructed with an overall downstream embankment slope of 2H:1V or flatter. The face of the North-South Embankment and a portion of the East-West Embankment will be covered by the North RDS. Final grading will result in an overall slope of 2.7H:1V or flatter. A portion of the East-West Embankment is constructed at, and will remain at, 2H:1V. The lower portion of the East-West Embankment will be covered by the HsB RDS and will be graded at an approximate slope of 3H:1V. The West Embankment is constructed at its final slope of 3H:1V, with the exception of a small segment near the West Embankment Drain (WED) extraction pond, where the final slope would be graded to 2.5H:1V. Post-closure reclamation of the WED will be managed through the BMFOU remedy. All grading will be conducted using non-noxious, nonflammable, noncombustible solids (MCA 82-4-336(6)).
Surface water swales and ditches will be constructed as needed at variable distances along the embankment downstream slopes. The concept includes grass-lined swales in the upper reaches, transitioning to riprap-lined ditches in the lower reaches, as shown on Figure RP-7-1.
The minimum embankment crest width will be 200 feet. The short upstream embankment face between the crest and the tailings surface will be graded to a 2.7H:1V or flatter slope. An access road will be retained along the top of the embankment crest for post-closure use.
Coversoil will be distributed at a depth of 20 inches of alluvium (or 14 inches of alluvium with 6 inches of topsoil over it to achieve 20 inches) on the 3H:1V portion of the West Embankment concurrently with lift completion. The topsoil volume needed for resoiling the slope to the 6450-foot elevation is approximately 19,000 cubic yards. The East-West Embankment face will be capped with 20 inches of alluvium (or if topsoil is used, a combination of alluvium and topsoil to achieve a total of 20 inches) on the 3H:1V and 2.7H:1V or steeper slopes. Alluvium would be lime amended as necessary based on testing (see Section 5.1).
The North-South Embankment face will be covered by, and reclaimed in conjunction with, the North RDS, discussed in Section 8.2. The embankment crest will be capped with 28 inches of suitable or amended alluvium unless mine rock scheduling allows the direct-haul of the final 28 inches of the crest to be constructed of suitable leached cap. 8.1.2 Beach
Post-closure beach and pond acreage will change following closure as the pond drains. Table RP-8-2 lists beach and pond acreages annually through 2082 (assuming closure in 2031) based on modeling during the 6450 design phase. Modeling will be updated periodically to reflect changes resulting from the BMFOU remedy, on-site water management, and tailings deposition strategy.
The tailings beach will slope gradually away from the embankment to the north at a typical slope of less than one percent. Some topographic diversity would be created by final placement of the spigots. While no final grading is anticipated in the beach or pond area since water would drain northwards to the post-closure pond, it may be necessary to conduct some surface shaping to compensate for settlement.
The beach would either be capped with 28 inches of alluvium with the top six inches amended where necessary; or, where possible, salvaged topsoil would be used to cover as much of the beach area as possible to a depth of 6 inches over 22 inches of respread alluvium to achieve a total coversoil depth of 28 inches. Where topsoil is available, placing it over alluvium will enhance revegetation and evapotranspiration, thereby reducing percolation through the tailings.
8.1.3 Post-Closure Pond and Transition Zone
The tailings pond will be positioned to the north side of the facility, and away from the YDTI Embankments. The post-closure pond will be passively controlled by the invert position of the closure spillway.
A remnant pond will be present post-closure as was previously permitted in MR’s wet closure plan. The surface elevation of the pond at closure will be controlled due to construction of a spillway.
The pond size will decrease over time once tailings and make-up water, WED discharge, and upgradient sources (if diversions are applicable) are no longer added and water drains through the tailings to the south. Figure RP-8-3 shows the volume of the post-closure pond over time, with an ultimate equilibrium volume of about 500 acre-feet, corresponding to an elevation of about 6363 feet. This is a conservative estimate and does not include water reduction through the Pilot Project. Note that post-closure treatment of WED water as part of the BMFOU remedy would slightly affect acreages in Table RP-8-2. MR will periodically update and report current conditions. The beach area slope will be flatter than 5 percent. Coversoil will be spread on the beach to a depth of 28 inches of alluvium or a combination of 22 inches of alluvium and 6 inches of topsoil (see Table RP-4-7). The transition zone is projected to be a 5 percent slope (see Exhibit RP-2) and would be covered with 20 inches of coversoil. Should portions of the transition zone be less than 5 percent slope, coversoil depth would be increased to 28 inches. As water level drops and the transition zone dries, coversoil would be placed in 5 year increments. A 6-inch cover of rock, leached cap, or similar material would be placed as necessary for dust control concurrently with beach exposure. Coversoil material may be stockpiled on the beach area in advance to minimize haul distance post-closure. Coversoil would not be applied to the remnant pond.
SOIL/ALLUVIUM PLACEMENT: 2023 Reclamation Plan Citations:
(Section 5.0) "Where indicated by testing (Section 10.3), MR would utilize lime, organic matter, and/or fertilizer to create a suitable plant growth material (82-4-303(28)(c), MCA)."
(Section 10.3) "The majority of coversoil to be used for reclamation will be mined in the CZABA. This material has recently been evaluated for suitability."
(Section 4.2) "A 2018-2021 evaluation of quantity and quality of alluvium was completed to assess this resource (Czehura 2021). The evaluation included drilling and sampling 30 holes in the Central Zone and incorporated results from previous investigations. Characteristics of the alluvium deposit were identified using laboratory data from 846 composite samples taken at 10-foot intervals. The average texture ranges from sandy clay loam to loamy sand, with a mean coarse fragment content of 25 percent. The mean paste pH is 6.52 standard units (s.u.). Total sulfur averages 0.29 percent with a median value of 0.23 percent." (Section 4.2) 4.2.1 Alluvium
Central Zone alluvium is the primary coversoil resource at the mine. A 2018-2021 evaluation of quantity and quality of alluvium was completed to assess this resource (Czehura 2021).
The evaluation included drilling and sampling 30 holes in the Central Zone and incorporated results from previous investigations. During salvage operations, MR systematically samples and analyzes alluvial materials; those materials determined to be suitable for reclamation are stockpiled or used during concurrent reclamation. Alluvium not suitable for reclamation is discarded in the South Continental Pit RDS. If suitable alluvium for reclamation is in short supply, less favorable alluvium is stockpiled separately and amended with lime during redistribution. When possible, salvaged alluvium is direct-hauled from the CZABA and used as subsoil/soil for reclamation. Quantities of alluvium stored in the Lunch Room and Four Corners alluvium stockpiles are documented in MR’s Annual Reports (2014-2021). 4.2.3 Topsoil
Topsoil and subsoil salvage has been limited within the mine boundary because most of the active mine area was developed prior to soil salvage guidelines and regulations. Therefore, recent and future soil salvage will generally be limited to areas surrounding the YDTI. 4.3 Coversoil Balance
The CZABA pit design would produce about 23 million loose cubic yards of suitable alluvium (Table RP-4-6). This conservative design exceeds the estimated volume of about 11 million loose cubic yards needed for reclamation (Table RP-4-7) by a factor of 2, demonstrating that a more than adequate volume of suitable alluvium is available to reclaim the mine. Final volumes of alluvium needed for reclamation and a corresponding mine plan for the borrow area would be developed at closure.
4.4 COVERSOIL DEPTHS
The previous slope category of > 37 percent with 36 inches of coversoil on slopes has been combined with the ≥ 5 percent category. The installation of benches at intervals along steeper slopes would reduce erosion potential and negate the need for the deeper application of coversoil on slopes steeper than 37 percent. The depth of alluvium or leached cap would vary based on topsoil redistribution depth to achieve a total of 28” for slopes < 5 percent and 20” for slopes ≥ 5 percent.
Slope < 5% : 28 inches of alluvium or 22 inches alluvium + 6 inches of topsoil
Slope ≥ 5%: 20 inches of alluvium or 14 inches alluvium + 6 inches of topsoil
4.5 DECOMPACTION
During soil handling operations, efforts would be made to minimize compaction. Following grading and prior to capping material application, ripping would be performed as needed to relieve compaction utilizing ripper shanks behind a dozer or motor grader. On slopes that are steeper than 33 percent, the surface would be left in a roughened condition. If needed, compacted surfaces including rock disposal sites and, following their removal, soil and alluvium stockpile sites, would be ripped.
5.1 LIME
Alluvium to be used for coversoil would be suitable as a plant growth material without the addition of lime. Modeling of the CZABA shows an average pH of 6.6 for material to be used for reclamation (see Section 4.2.1). Material with a pH below 5.5 is considered waste. Alluvium sampling would identify unsuitable material.
If monitoring identifies any areas where pH is below 5.5 in respread coversoil, lime will be applied at appropriate rates to raise the pH to about 6.0. Lime would be incorporated to a depth of about 18 inches.
Reclaimed areas of the East RDS Complex monitored in 2021 had an average pH of 6.8 in the upper 9 inches of coversoil and an average pH of 7.0 throughout all soil horizons sampled, with perennial grass cover ranging from 30 to 46 percent (WESTECH 2022). A few small “hot spots” on the older reclaimed Hillcrest RDS had lower pH and low vegetation cover. Monitoring sites where both soils and vegetation were sampled in 2022 included older reclamation (1991-2014) associated with mine facilities, including the Berkeley Pit perimeter, Concentrator, Primary Crusher, Powerline Road, Woodville area, and other miscellaneous sites. Coversoil in the upper 8 inches in these areas had an average pH of 7.2. Throughout all soil horizons sampled (upper 17 inches), coversoil had an average pH of 7.1. Perennial grass cover varied from 40 to 62 percent (WESTECH 2023).
5.2 ORGANIC MATTER
Previous reclamation specifications for the mine had assumed that, where topsoil is not spread, organic matter would be applied and incorporated into alluvium or leached cap coversoil. The assumption was based on a Minor Revision (MR 02-001) for 2002 reclamation of the Woodville RDS. MR does not propose to implement the Woodville RDS specification mine wide.
Research into the need for, and use of, organic amendments for reclamation indicates that specific organic content may not be necessary for successful reclamation. Organic content is one component of growth material suitability but may not be necessary for reclamation success (Prodgers 2013). Other studies have identified the sensitivity of some soils to organic soil amendments by which the addition of certain types of amendments can result in decreased permanent vegetation due to unsustainable nutrient cycles (Larney & Angers 2011).
The potential use of organic amendments is determined by factors such as texture, nutrient content, and desired vegetation. MR has recently conducted on-site reclamation monitoring to evaluate characteristics of coversoil materials and vegetation response at previously reclaimed mine areas. Results indicate that there is no statistically significant difference in the cover of perennial grasses at sites with 1.5% organic matter compared to sites with 0.5% or less organic matter (WESTECH 2022 and 2023). The comparable vegetation response between various soil organic matter content groupings indicates that thresholds for soil organic content are not reliable predictors of revegetation.
Although certain levels of organic matter content may not be necessary for reclamation success, organic materials can be advantageous for initial establishment of vegetation at certain sites. Sites that may present challenging conditions for vegetation establishment include south-facing and/or steep slopes, or areas where soil crusting is present. Conditions at such sites could be mitigated through the application of organic matter. At sites with lower reclamation potential, organic matter applications at a rate up to 0.5% by volume could be incorporated into the upper 6 inches of coversoil.
Organic matter amendments could include straw or alfalfa mulch, which may also be applied for erosion control or to mitigate soil crusting on some sites (see Section 7.0). If soil crusting adversely affects vegetation establishment, MR could implement mechanical measures including rotary hoeing, harrowing, or discing. When possible, seeding will be conducted promptly after coversoil spreading to reduce the potential for precipitation to cause soil crusting. Organic compost is currently being stockpiled in the McQueen area and on the West Embankment (Figure RP-4-4) and could be utilized if amendment is necessary during reclamation. Other commercially available sources for compost will be identified for future potential use.
5.3 FERTILIZER
The use of organic or inorganic fertilizer may be indicated based on testing. When it has been used, MR has typically applied a compound inorganic fertilizer (N-P-K (16-16-16)).
Revision 25-001, 3/20 Reply:
Long Term Monitoring Sites:
Post-Closure Topography and Grading: Grade drill pads to blend with adjacent topography. Coversoil: Sites in previously undisturbed ground: none if topsoil still intact; 6 inches of topsoil if topsoil previously removed. Sites in mine: none if topsoil still intact; otherwise depth of coversoil to be consistent with adjacent area.
Decompaction: Rip or harrow (depending on degree of compaction) pads and road surfaces.
Seedbed Preparation: Seedbed to be firm but not compacted.
Seeding Method and Schedule: Broadcast smaller sites. Seed after 9/15 and before 6/15 unless erosion considerations necessitate off-season seeding.
Additional: Install Kelly humps, rock barriers, woody debris or locked gates if necessary to control access. Plug holes with 5-10 feet of cement per ARM 17.24.106. Cut casing below ground level per ARM 17.24.107(2).
Support Facilities:
Coversoil: Sites in previously undisturbed ground: none if topsoil still intact; 6 inches of topsoil if topsoil previously removed.
Sites in mine: none if topsoil still intact; otherwise depth of coversoil to be consistent with adjacent area (20 inches of alluvium if slope is ≥ 5 percent, or 28 inches of alluvium if slope is <5 percent). If topsoil still intact, no coversoil required.
Assumptions: The schedule in the Reclamation Plan reflects the required timelines for the permittee and their available equipment fleet and staffing.
Following a hypothetical bankruptcy or permit revocation and bond forfeiture, DEQ assumes that at least 1 year will be needed to resolve bankruptcy conditions and/or obtain the bond. Reclamation will occur annually across the mine site during the initial years post-closure (assumed within 5 years from closure), followed by less frequent reclamation of the TSF transition zone as the pond recedes to an equilibrium volume/elevation. BMFOU water management and treatment would be ongoing throughout this time period, under the applicable requirements for the Remedy. 2019 EIS: For the TSF- "Reclamation would be accomplished incrementally over an estimated 40-year period following mine closure as the tailings water recedes, exposing more Transition Zone for reclamation until the pond volume reaches approximately 1,000 acre-feet at equilibrium." - Year 1 interim management and monitoring (legal process/obtain bond); - Years 2-5 implement major reclamation actions, site management and monitoring; - Years 6-33 incremental reclamation of TSF transition zone, post-closure site management and monitoring Revegetation monitoring would occur annually for five years following initial seeding campaigns, then frequency would decrease to five year intervals until determining stable vegetation sucess to allow bond release/permit closure.
2023 Reclamation Plan: 10.2.5 Post-Closure Beach and Pond Management and Monitoring Post-closure pond management and monitoring will include:
• a closure spillway to be constructed to limit the elevation and volume of the post-closure pond;
• incremental reclamation of the transition zone as pond level recedes (see Section 8.1.3);
• survey of beach for slope and settlement and repair as necessary (see Section 8.1.2, Section 10.2.2, and Section 10.3). Monitoring of reclaimed tailings will be conducted annually to verify elevations and cap thickness using civil survey and/or aerial mapping surveys with ground control (drones, LIDAR). If settling occurs it will be backfilled with coversoil and revegetated.
• monitoring of pond level, pond volume, and pond water quality (see Section 8.1.3, Section 10.2.4, and Section 10.5); and
• for the Probable Case model of post-closure pond water quality, water treatment is not anticipated since the pool would remain alkaline and metals would remain low (see Appendix C “Phase Two Mass Load Model of the Yankee Doodle Tailings Pond” in Amendment 10 (MR 2018)). "For the Worst Case, the pool would gradually become slightly acidic after closure (net alkalinity of -200 mg/L and pH of 5.5 to 7.0), with iron of up to 36 mg/L and aluminum up to 16 mg/L. Sulfate would be around 1100 mg/L (TDS of 1800 mg/L) at closure and would gradually decline to less than 500 mg/L (TDS 1000 mg/L) around 30 years post-closure.
If acidic conditions were to develop after closure, lime would be added to maintain alkaline conditions and low metals. 5000 tons of lime would be needed over the 30-year post-closure period, or about 150 tons per year. "
2023 Rec Plan: 8.1.4 Closure Spillway
A conceptual closure spillway has been designed to prevent water from pooling against the embankment (Figure RP-8-4). A conceptual design for the closure spillway is presented in Appendix B to Knight Piésold’s Reclamation Overview report of the Design Document (KP 2018b).
The spillway walls and bottom in the segment would be excavated in bedrock. The spillway segment traversing previously disturbed areas would be regraded, covered with 20 inches of alluvium, and broadcast seeded with the mixture shown in Table RP-6-1.
8.1.5 West Embankment Drain and Pond
Post-closure, water collected by the WED would be managed as part of the BMFOU remedy per resolution of a stipulation to Permit Amendment 10. No bond is required for plugging and closing this feature, as was assumed in previous bonds. When the Extraction Pond is no longer deemed necessary, its reclamation would also be managed as part of the transition of WED flow to BMFOU remedy.
Assumptions: A conceptual post-closure spillway design was approved through Amend 010. A detailed design will be undertaken once the facility closure is imminent and closure conditions are available. The design is located in KP's Reclamation Overview Design Document, Appendix B. The spillway was modeled as a trapezoid channel cut into bedrock on the left abutment of the YDTI embankment. The excavated channel will extend 5,000 feet southward to a point where local topography creates a flow path to the Continental Pit. The conceptual spillway intake and channel designs and costs were provided by Knight Piesold (2020).
Bond Release (2008) Discussion:
In 2008, bond release was requested for resloping, soil placement, and vegetation establishment on multiple areas. Based on field inspection, the slope angles are satisfactory, approximately 2.5 to 3H:1V slope. The existing vegetation is a mixture of desirable grasses, forbs, and noxious weeds.
East and North East Dumps:
To achieve full bond release in the future, DEQ recommended the following for the East and North East Dumps:
Fix erosion gullies by fixing source problems, installing temporary BMP's, replace lost soil, seed, and weed spray (2-3x per year)
For the East and North East Dumps (Partially Reclaimed/Released) in the 2025 map, only the costs of revegetation, erosion repair, and weed control will apply
Hillcrest Dump:
No surface water collection ditches or slope break features were built on the Hillcrest slope (400-500 ft long) In addition, there exists three "hot spots" without vegetation, indicating poor soil quality.
To achieve full bond release in the future, DEQ recommended the following for the Hillcrest Dump:
Construct main surface water collection ditches to help prevent erosion, Fix all hot spots by selectively digging out the existing soil, re-apply lime and good quality soil, seed, and weed spray, Fix all erosion gullies by correcting the source problem, installing temporary BMPs, replace lost soil, seed, and weed spray (2-3x a time)
For the Hillcrest Dump (Partially Reclaimed/Released) in the 2025 map, the costs of constructing storm water channels, repairing hot spots, revegetation, erosion repair, and weed control will apply

## AcreageTracking-MAP
Montana Resources, LLC
Operating Permit #00030
Final Comprehensive 5-Year Bond Review
2026-05-04
FROM MR 1/23/2026 SUBMITTAL
Disturbance Acreage Summary by Feature and Bond Area
Feature | Post-July, 1 1974 | Pre-July, 1 1974 | BMFOU/Exempt/GMMIA | Grand Total | SLOPE CORRECTION* | FINAL BOND- USE THIS COLUMN FOR CALCS | DEQ NOTES
Alluvium Stockpile | 18.9866 |  |  | 18.9866 |  | 18.9866
Berkeley Pit (BMFOU) |  |  | 683.8706 | 683.8706 |  | NA | Not bonded- feature managed under BMFOU plans and authority
[6 empty] | NA | Water not separated, like it was in 2020 map/bond
Concentrator Area (EXEMPT) |  |  | 79.2377 | 79.2377 |  | NA | Not bonded- feature is pre-1971 processing facility and exempt from bonding
Concentrator Area Reclaimed (EXEMPT) |  |  | 15.8672 | 15.8672 |  | NA | Not bonded- feature is pre-1971 processing facility and exempt from bonding
Continental Pit - Highwall | 413.198 | 27.9877 |  | 441.1857 |  | NA | Unreclaimable/vertical surfaces
Continental Pit - Reclaimable Area | 210.485 | 24.5658 |  | 235.0507 |  | 210.485
Continental Pit 5410' NGVD29 / 5466' (BMFOU) |  |  | 249.2013 | 249.2013 |  | NA | Not bonded- feature managed under BMFOU plans and authority
CZ Pit Bench/Ramp | 58.6466 | 57.1464 |  | 115.7931 |  | 58.6466 | Assumptions based on Rec Plan, would remove acres from McQueen, Misc., and Pittsmont RDS. Shown in updated 5-year projection map
CZ Pit Highwall | 26.4752 | 16.8324 |  | 43.3076 |  | NA | Unreclaimable/vertical surfaces
Exploration Permit Partially Reclaimed/Released | 0.46488 |  |  | 0.46488 |  | NA | Address under Explo License bond
HsB Water Treatment Plant (BMFOU) |  |  | 8.9103 | 8.9103 |  | NA | Not bonded- feature managed under BMFOU plans and authority
Historic Preservation (GMMIA) |  |  | 16.9391 | 16.9391 |  | NA | Not bonded- feature to remain in current status for historic preservation under GMMIA plans
Leach Pad | 7.5139 | 119.0482 |  | 126.5621 |  | 7.5139
McQueen Townsite | 2.7219 | 0.70079 |  | 3.4227 |  | 2.7219
Misc | 159.1261 | 169.9447 |  | 329.0709 | 1.067 | 175.0165 | Includes Misc. Partially Reclaimed -- which has not been released
Misc Partially Reclaimed | 4.9006 | 9.5699 |  | 14.4705 |  | added above | Added to Misc. No partial release yet, bonded for sloping, soil placement, seeding and weed control
Misc Partially Reclaimed/Released | 2.9742 | 22.1945 |  | 25.1688 | 1.067 | 3.1735 | Reflects partial release of sloping and soil placement, not seeding and weed control
Office |  | 1.8159 |  | 1.8159 |  | all pre-1974 | Not an exempt processing facility, but contained pre-1974 area limited to $500/acre
Precipitation Plant Area | 0.78436 | 1.6235 |  | 2.4079 |  | 0.78436 | New polygon in new map- added to Earthmoving and Reveg
Misc Precipitation Plant RR | 0.33219 | 0.043185 |  | 0.37538 |  | 0.33219 | New polygon in new map- added to Earthmoving and Reveg
Garage Area |  | 32.1477 |  | 32.1477 |  | all pre-1974 | Not an exempt processing facility, but contained pre-1974 area limited to $500/acre
Primary Crusher (EXEMPT) |  |  | 30.8336 | 30.8336 |  | NA | Not bonded- feature is pre-1971 processing facility and exempt from bonding
Primary Crusher Reclaimed (EXEMPT) |  |  | 13.3056 | 13.3056 |  | NA | Not bonded- feature is pre-1971 processing facility and exempt from bonding
RDS Access | 14.1881 | 16.2001 |  | 30.3881 | 1.067 | 7.6697 | Calculated difference from total area (reported) and crest measurement
RDS Access Crest | 7 |  |  |  |  | 7 | Not separated on MR maps, crest measured from aerial imagery to assist with calculations
RDS East Crest | 29.3583 |  |  | 29.3583 |  | 29.3583
RDS East | 2.7526 |  |  | 2.7526 | 1.067 | 14.6371 | Includes RDS East Partially Reclaimed -- which has not been released
RDS East Partially Reclaimed | 10.9654 |  |  | 10.9654 |  |  | Added to RDS East. No partial release yet, bonded for sloping, soil placement, seeding and weed control
RDS East Partially Reclaimed/Released | 86.0559 |  |  | 86.0559 | 1.067 | 91.8216 | Reflects partial release of sloping and soil placement, not seeding and weed control
RDS Great Northern |  | 68.2258 |  | 68.2258 |  | all pre-1974
RDS Hillcrest Partially Reclaimed/Released | 47.5179 |  |  | 47.5179 | 1.067 | 50.7016 | Reflects partial release of sloping and soil placement, not seeding and weed control
RDS HsB |  | 45.9725 |  | 45.9725 |  | all pre-1974
RDS HsB Crest |  | 33.4632 |  | 33.4632 |  | all pre-1974
RDS Nalley Valley | 32.2678 | 40.0278 |  | 72.2956 | 1.067 | 34.4297
RDS North | 11.1952 | 27.1863 |  | 38.3816 | 1.067 | 11.9453
RDS North Crest | 12.31 | 76.6874 |  | 88.9974 |  | 12.31 | Not included in Prelim, area was unclear. Now added for all bond tasks
RDS North East Partially Reclaimed/Released | 18.6798 |  |  | 18.6798 | 1.067 | 19.9313 | Reflects partial release of sloping and soil placement, not seeding and weed control
RDS North East- New D East Expansion Disturbance | [6 empty] | Not a separate feature on map and Proposed bond, combined into Continental Highwall, Misc. or RDS East as applicable
RDS North East- New E East Drilling Disturbance | [6 empty] | Not a separate feature on map and Proposed bond, combined into Continental Highwall, Misc. or RDS East as applicable
RDS Pittsmont | 59.7435 | 18.1016 |  | 77.8451 | 1.067 | 63.7463 | New map and Proposed bond account for overlapping CZABA
RDS Pittsmont Crest | 26.5904 | 5.0759 |  | 31.6663 |  | 26.5904 | New map and Proposed bond account for overlapping CZABA
RDS South Continental Pit | 40.5861 | 3.6699 |  | 44.256 | 1.067 | 43.3053
RDS South Continental Pit Crest | 18.1201 | 0.57921 |  | 18.6993 |  | 18.1201
RDS Woodville Partially Reclaimed/Released | 0.59689 |  |  | 0.59689 | 1.067 | 0.63689 | Reflects partial release of sloping and soil placement, not seeding and weed control
Soil Stockpile | 23.4826 | 0.84106 |  | 24.3237 |  | 23.4826
YDTI Crests: | [6 empty] | All combined in 2025, rather than 2020 mapping method. Does not exclude crest road areas. Updated 5-year projection map needed
YDTI North-South Crest | 42.6213 | 20.4251 |  | 63.0464 |  | 42.6213 | Previous map, with separate features for each limb
YDTI East-West Crest | 5.8198 | 55.8833 |  | 61.7031 |  | 5.8198 | Previous map, with separate features for each limb
YDTI West Crest | 67.3777 | 6.3315 |  | 73.7092 |  | 67.3777 | Previous map, with separate features for each limb
YDTI Embankments 2.7:1 | [6 empty] | All combined in 2025, rather than 2020 mapping method. Updated in new map
YDTI North-South Embankment 2.7:1 | 48.1329 | 61.1107 |  | 109.2436 | 1.067 | 51.3578 | Assumed to be 2.7H:1V
YDTI East-West Embankment 2.7:1 | 1.6351 | 93.0781 |  | 94.7132 | 1.067 | 1.7446 | Assumed to be 2.7H:1V
YDTI West Embankment 2.7:1 | 0.54113 | 0.32453 |  | 0.86566 | 1.067 | 0.57738 | Only material placement- no regrade on West Embank downstream (COMBINATION OF MULTIPLE ANGLES)
YDTI West Embankment Partially Reclaimed (3:1) | 24.2047 |  |  | 24.2047 | 1.067 | 2.6725 | Treated as Downstream 3H:1V area, no partial release approved - removed area approved for release
YDTI West Embankment Partially Reclaimed - Released | 21.7 | Not separated on map- calculated |  |  | 1.067 | 23.1539 | Reflects partial release of sloping and soil placement, not seeding and weed control
YDTI West Embankment Partially Reclaimed - Graded | 3.1157 |  |  | 3.1157 | 1.067 | 3.3245 | Treated as Downstream 3H:1V area, no partial release approved
TSF: West Embankment (3:1 Downstream)- Soil Area |  | Not separated on map- DEQ calculated |  |  | corrected above | 5.997 | Remaining areas after partial release of 21.7 acres
TSF: West Embankment- Alluvium Area |  | Not separated on map- DEQ calculated |  |  | corrected above | 90.7914 | 23.1 acres of this area receives 14 inches alluvium, remaining slopes get 20 inches
TSF: N-S Embankment Alluvium Area |  | Not separated on map- DEQ calculated |  |  | corrected above | 101.9046
TSF: E-W Embankment Alluvium Area |  | Not separated on map- DEQ calculated |  |  | corrected above | 8.3719
YDTI Embankment Upstream 2.7:1 | [6 empty] | All combined in 2025, rather than 2020 mapping method. Updated in new map
YDTI North-South Embankment Upstream 2.7:1 | 7.4277 | 3.2053 |  | 10.633 | 1.067 | 7.9254
YDTI East-West Embankment Upstream 2.7:1 | 0.7567 | 6.0175 |  | 6.7742 | 1.067 | 0.80739
YDTI West Embankment Upstream 2.7:1 | 10.0232 | 0.61111 |  | 10.6343 | 1.067 | 10.6948
YDTI Embankments 2:1 | [6 empty] | Area is removed through the construction of HSB RDS
YDTI North-South Embankment 2:1 |  | 24.838 |  | 24.838 |  | all pre-1974 | All combined in 2025, rather than 2020 mapping method. Updated in new map
YDTI East-West Embankment 2:1 |  | 40.3694 |  | 40.3694 |  | all pre-1974 | All combined in 2025, rather than 2020 mapping method. Updated in new map
YDTI West Embankment 2.5:1 | 5.6893 | 0.62261 |  | 6.3119 | 1.08 | 6.1445
Area is removed through the construction of HSB RDS
Area is removed through the construction of HSB RDS
Area is removed through the construction of HSB RDS
YDTI Equilibrium Pond - Approx. 2000ac/ft - Elev. 6375ft | 139.7886 |  |  | 139.7886 |  | 139.7886 | This is a long-term/post-closure footprint, disconnnected from the first 5 years of reclamation following closure at 15,000 ac-ft
YDTI Beach | 735.5502 | 498.364 |  | 1233.9142 |  | 735.5502 | Updated in new map
TSF: Beach at Closure- Alluvium Area @ 22 inches |  | Not separated on map- DEQ calculated |  |  |  | 365.5 | Assume half of the topsoil coverage area = 731 ac in 2023 Rec Plan (731 ac / 2 = 366 ac) is split between pre-1974 and post-1974 areas
TSF: Beach at Closure- Soil Area @ 6 inches |  | Not separated on map- DEQ calculated |  |  |  | 365.5 | Topsoil resource will cover 731 acres at 6 inches (2023 Rec Plan)
TSF: Beach at Closure- Alluvium Area @ 28 inches |  | Not separated on map- DEQ calculated |  |  |  | 370.0502 | Remainder of beach that will not receive 6-inch soil layer (only alluvium)
YDTI Tailings Transition Zone | 251.6126 | 50.8085 |  | 302.421 |  | 251.6126
YDTI North Transition Zone | 50.7923 |  |  | 50.7923 |  | 50.7923
YDTI Embankment WED (BMFOU) |  |  | 1.2049 | 1.2049 |  | NA
[6 empty] | NA | See spillway costs, no reclamation footprint cited
Powerline Road Partially Reclaimed/Released | 0.96866 |  |  | 0.96866 |  | 0.96866 | Reflects partial release of sloping and soil placement, not seeding and weed control
Roads | 48.0412 | 59.477 |  | 107.5182 |  | 48.0412
Combined in other Roads in new map
YDTI North-South Embankment Road |  | 10.0696 |  | 10.0696 |  | all pre-1974 | Some slope roads
YDTI North-South Crest Road | 5.5285 | 2.6785 |  | 8.2069 |  | 5.5285 | Flat roads
YDTI East-West Crest Road | 0.61558 | 4.9498 |  | 5.5654 |  | 0.61558 | Flat roads
YDTI West Crest Road | 7.1845 | 0.63297 |  | 7.8174 |  | 7.1845 | Flat roads
ALL ROADS in post-1974 area (AC) |  | Not separated on map- DEQ calculated |  |  |  | 61.3697
All Road areas to be reclaimed (AC) |  | Not separated on map- DEQ calculated |  |  |  | 30.6848 | Assume 50% area reduction
Road Reclaimed (0-20% slope) (factor of 1.0) |  | Not separated on map- DEQ calculated |  |  |  | 15.3424 | Flat roads (assume half of roads area)
Road Reclaimed (20-40% slope) (factor of 1.0525) |  | Not separated on map- DEQ calculated |  |  | 1.0525 | 16.1479 | Slope roads (assume half of roads area)- corrected
Corrected Reclaimable Road Area |  | Not separated on map- DEQ calculated |  |  |  | 31.4903
Undisturbed | 474.8565 |  |  | 474.8565 |  | NA | Undisturbed- no bond required
Undisturbed - 711 Road | 0.24212 |  |  | 0.24212 |  | NA | Undisturbed- no bond required
*Assume RDS are 2.7H:1V to 3H:1V (in 2023 Rec Plan), other features based on reported slope
[5 empty] | Roads: | 1371718.3523 | sq ft
[6 empty] | 22861.9725 | ft long (Avg width 60 ft)
Grand Total (Reported) | 3273.5462 | 1759.4486 | 1099.3704 | 6132.3652 |  | 4.3299 | miles
|  |  | All RDS/Misc Areas Receiving Alluvium |  |  | 638.989 | No TSF features, partial bond released features, stockpiles/borrow area, or pre-1974
|  |  | ALL AREAS RECEIVING ALLUVIUM |  |  | 1870.6551 | No partial bond released features, stockpiles/borrow area, or pre-1974
[6 empty] | 1870.6551 | Alluvium Areas- Formula check from Earthmoving tab
Edited by DEQ for summary
DUST CONTROL ACCOUNTING
At Closure | Total | Pre-1974 ($500/acre) | Post-1974 (full bond)
Beach (initially reclaimable) | 1233.9 | 498.4 | 735.6 |  | Post-1974 areas- bonded for dust control, capping material, seed+weed control
Transition Zone (primary) | 302.4 | 50.8 | 251.6 |  | Post-1974 areas- bonded for dust control, capping material, seed+weed control
Transition Zone (north) | 50.8 | 0 | 50.8 |  | Post-1974 areas- bonded for seed+weed control
At Equilibrium | Total | Pre-1974 ($500/acre) | Post-1974 (full bond)
Beach - Reclaimed | 1536.3 | 549.2 | 987.2
Transition Zone (primary) - Turned to Beach | 0 | 0 | 0
Transition Zone (north)- Reclaimed | 50.8 | 0 | 50.8
POST-1974
Dust Control Area
|  | Annual spray | Year 1 | 147.12 | (Total initial beach divided by 5, first 5 years)
|  | Annual spray | Year 2 | 147.12 | (Total initial beach divided by 5, first 5 years)
|  | Annual spray | Year 3 | 147.12 | (Total initial beach divided by 5, first 5 years)
|  | Annual spray | Year 4 | 147.12 | (Total initial beach divided by 5, first 5 years)
|  | Annual spray | Year 5 | 147.12 | (Total initial beach divided by 5, first 5 years)
|  |  | Year 6 | 8.9857 | (Transition zone exposure = initial area divided by 28 years of pond drawdown)
|  |  | Year 7 | 8.9857 | (Transition zone exposure = initial area divided by 28 years of pond drawdown)
|  |  | Year 8 | 8.9857 | (Transition zone exposure = initial area divided by 28 years of pond drawdown)
|  |  | Year 9 | 8.9857 | (Transition zone exposure = initial area divided by 28 years of pond drawdown)
|  | Spray every 5 | Year 10 | 44.9286 | (Transition zone exposure = sum of 5 years, work completed)
|  |  | Year 11 | 8.9857 | (Transition zone exposure = initial area divided by 28 years of pond drawdown)
|  |  | Year 12 | 8.9857 | (Transition zone exposure = initial area divided by 28 years of pond drawdown)
|  |  | Year 13 | 8.9857 | (Transition zone exposure = initial area divided by 28 years of pond drawdown)
|  |  | Year 14 | 8.9857 | (Transition zone exposure = initial area divided by 28 years of pond drawdown)
|  | Spray every 5 | Year 15 | 44.9286 | (Transition zone exposure = sum of 5 years, work completed)
|  |  | Year 16 | 8.9857 | (Transition zone exposure = initial area divided by 28 years of pond drawdown)
|  |  | Year 17 | 8.9857 | (Transition zone exposure = initial area divided by 28 years of pond drawdown)
|  |  | Year 18 | 8.9857 | (Transition zone exposure = initial area divided by 28 years of pond drawdown)
|  |  | Year 19 | 8.9857 | (Transition zone exposure = initial area divided by 28 years of pond drawdown)
|  | Spray every 5 | Year 20 | 44.9286 | (Transition zone exposure = sum of 5 years, work completed)
|  |  | Year 21 | 8.9857 | (Transition zone exposure = initial area divided by 28 years of pond drawdown)
|  |  | Year 22 | 8.9857 | (Transition zone exposure = initial area divided by 28 years of pond drawdown)
|  |  | Year 23 | 8.9857 | (Transition zone exposure = initial area divided by 28 years of pond drawdown)
|  |  | Year 24 | 8.9857 | (Transition zone exposure = initial area divided by 28 years of pond drawdown)
|  | Spray every 5 | Year 25 | 44.9286 | (Transition zone exposure = sum of 5 years, work completed)
|  |  | Year 26 | 8.9857 | (Transition zone exposure = initial area divided by 28 years of pond drawdown)
|  |  | Year 27 | 8.9857 | (Transition zone exposure = initial area divided by 28 years of pond drawdown)
|  |  | Year 28 | 8.9857 | (Transition zone exposure = initial area divided by 28 years of pond drawdown)
|  |  | Year 29 | 8.9857 | (Transition zone exposure = initial area divided by 28 years of pond drawdown)
|  | Spray every 5 | Year 30 | 44.9286 | (Transition zone exposure = sum of 5 years, work completed)
|  | Spray at end | Year 31 | 8.9857 | (Transition zone exposure = initial area divided by 28 years of pond drawdown)
|  | Spray at end | Year 32 | 8.9857 | (Transition zone exposure = initial area divided by 28 years of pond drawdown)
|  | Spray at end | Year 33 | 8.9857 | (Transition zone exposure = initial area divided by 28 years of pond drawdown)
| Sprayed area between Years 6-33 |  |  | 251.6
| Initial Transition Zone Area |  |  | 251.6 | Formula check
Assumptions/Observations: Roads- Road width may vary from 20-100 feet (average 60 ft). Without further details about road segments (length and area) that would be retained versus the road areas that would be reclaimed-- it is assumed that the road acreage (post-1974 area) will be reduced by 50% through reclamation. This can also be visualized as reducing the existing road widths by half (by ~10-50 ft). Like other misc. disturbance acres, it is assumed that half of the reclaimed road acreage will need to be corrected for slope area.

## 1-Facilities
Montana Resources, LLC
Operating Permit #00030
Final Comprehensive 5-Year Bond Review
2026-05-04
Task 1- Facilities, Structures, Waste, Infrastructure
|  | Size / Quantity |  | Demolition Unit Cost |  | Total Demolition Cost | Source, Assumptions, Adjustments, etc
PRE-1971 PROCESSING FACILITIES (EXEMPT)
Primary Crusher Area | Exempt Pre-1971 processing facility | 44.1392 | AC |  |  | 0 | No bond held- ($0/acre)
Concentrator Area | Exempt Pre-1971 processing facility | 95.105 | AC |  |  | 0 | No bond held- ($0/acre)
PRE-1974 DISTURBANCE AREAS
Former Permit #00030 Footprint |  | 1759.4486 | AC | 500 | /AC | 879724.313 | Land footprint bonded at $500/acre- rectified with reported/updated acres
PRE-1974 AREAS TOTAL | [5 empty] | 879724.313
FACILITIES
BUILDING DEMOLITION - ASSUME ONSITE DISPOSAL
Explosive Storage Areas | Within Pre-1974 area ($500/acre) |  |  |  |  | 0 | Accounted in other acreage tracking
Powder Magazines | Within Pre-1974 area ($500/acre) |  |  |  |  | 0 | Accounted in other acreage tracking
Fuel Bays | Within Pre-1974 area ($500/acre) |  |  |  |  | 0 | Accounted in other acreage tracking
HSB Water Treatment Plant | Used, Maintained, Reclaimed under BMFOU |  |  |  |  | 0
Return Water Barges (2) | Used, Maintained, Reclaimed under BMFOU |  |  |  |  | 0
Water Management Structures | Used, Maintained, Reclaimed under BMFOU |  |  |  |  | 0
Power Lines and Substations | Above ground power lines and substations owned by Northwestern Energy |  |  |  |  | 0
Central Water Tower | Not needed for BMFOU; however, in Concentrator exclusion area |  |  |  |  | 0
Relocated Precip Plant (Pre-1974) | Portion within Pre-1974 area ($500/acre) |  |  |  |  | 0 | Accounted in other acreage tracking
Relocated Precip Plant (Post-1974) | Portion at full reclamation cost |  |  |  |  | 60598.8 | 18" reinforced concrete | Hours Req'd for On-Site Disposal Equip. |  | *Assumes RSMeans production rates
Foundation Slab | 18" reinforced concrete | 11840 | sf | 3.57 | /sf | 42268.8 | 6 inch cost multiplied by 3 | 78.9333 | hrs
Bins/Walls | 18" reinforced concrete (treat as thick footing) | 750 | lf | 24.44 | /lf | 18330 | Assume that 750 ft (of total 1,250 ft) of walls are in post-1974 area | 34.2857 | hrs
Relocated Precip Plant- Shaker Building | At full cost, Approx. dimensions: 30'L x 30'W x 10'H |  |  |  |  | 6451.5833
Foundation Slab | 18" reinforced concrete? | 905 | sf | 3.57 | /sf | 3230.85 | 905 sf reported by MR in Rev22-001 | 6.0333 | hrs
Footing |  | 120 | lf | 14.27 | /cf | 1712.4 |  | 3.2 | hrs
Steel frame building |  | 3016.6667 | cf | 0.5 | /cf | 1508.3333 | Volume estimated in Rev22-001 | 1.1225 | hrs
Precip Plant Area | Footprint reclamation addressed on the Earthmoving and Reveg tabs | [5 empty] | See Earthmoving and Reveg tabs
Misc Precipitation Plant RR | Footprint reclamation addressed on the Earthmoving and Reveg tabs | [5 empty] | See Earthmoving and Reveg tabs
RR Demolition | 8,500 ft on 2020 bond map; reported in 2025 as 0.3 acre | 1200 | lf | 19.86 | /lf | 23832 | DEQ measurement on 2025 imagery- Only 1,200 ft is exposed, the rest is buried by RDS, access roads, or otherwise obliterated
On-site Disposal
Load/Haul/Dump of Plant & Equipment | Excavator & Dump Truck w/ operators | 123.5749 | hrs | 228.94 | /hr | 28291.2288 | Assumes RSMeans Production Rate for Demolition Tasks
PIPELINE & CONDUIT REMOVAL
Tailings Pump Stations (No. 3 and McQueen) | Within Pre-1974 area ($500/acre) |  |  |  |  | 0 | Accounted in other acreage tracking
Tailings Lines (pre-1974) | Within Pre-1974 area ($500/acre) |  |  |  |  | 0 | Accounted in other acreage tracking
TSF Return Water Lines (pre-1974) | Within Pre-1974 area ($500/acre) |  |  |  |  | 0 | Accounted in other acreage tracking | Hours Req'd for On-Site Disposal Equip. |  | *Assumes RSMeans production rates
Tailings Lines (post-1974) |  | 16665 | lf | 9.64 | /lf | 160650.6 | 20-36" HDPE | 666.6 | hrs
TSF Return Water Lines (post-1974) | Used, Maintained, Reclaimed under BMFOU | 22420 | lf | 9.64 | /lf | 0 | 20-36" HDPE (would be $216,129) | 896.8 | hrs
E East Water Management (MR25-001)
Distance from E East to WQ-2 or WQ-5 | Plastic Pipe Removal (3/4" - 4") | 5280 | lf | 2.76 | /lf | 14572.8 | 3/4 - 4" HDPE | 60.3429 | hrs
Pipe Removal and Disposal | [7 empty] | Use labor hours for equipment and operator with on site disposal. Use material weight for off site disposal
On-site Disposal
Load/Haul/Dump of Removed Pipe | Excavator & Dump Truck w/ operators | 405.9357 | hrs | 228.94 | /hr | 92934.9224 | Assumes 25% of pipe removal time required for hauling pipe for disposal
CHEMICAL/HAZ WASTE REMOVAL
Fuel | All stored in pre-1974 areas or exempt facility areas |  |  |  |  | 0 | Accounted in other acreage tracking
Oils/Lubricants | All stored in pre-1974 areas or exempt facility areas |  |  |  |  | 0 | Accounted in other acreage tracking
Chemicals/Reagents | All stored in pre-1974 areas or exempt facility areas |  |  |  |  | 0 | Accounted in other acreage tracking
Disposal
Landfill Fee |  | 0 | ton | 3.21 | /ton | 0
Dropoff & Haul Fee |  | 0 | ea | 1582 | /ea | 0 | *haul time to C&D landfill
FACILITIES TOTAL | [5 empty] | 387331.9346
Reclamation Rates | [6 empty] | 2025 Q1 RS Means Rates - Billings - Standard Union
DEMOLITION
Small Wood Building | No salvage value, volume of standing bldg | 0.45 | /cf | 14800 | cf/day |  | *2025 RS Means 02 41 16 13 0700
Steel Building | No foundation or dump fees, volume of standing bldg | 0.5 | /cf | 21500 | cf/day |  | *2025 RS Means 02 41 16 13 0020
Foundation | 6" Thick Foundation with Reinforcing Bar | 1.19 | /sf | 3600 | sf/day |  | *2025 RS Means 02 41 16 17 0440
Footing - Standard | 1' Thick x 2' Wide Footing | 14.27 | /lf | 300 | lf/day |  | *2025 RS Means 02 41 16 17 1000
Footing - Heavy | 2' Thick x 3' Wide Footing | 24.44 | /lf | 175 | lf/day |  | *2025 RS Means 02 41 16.17 1140
Bridge Demolition - Steel, 50-100ft long, 8-10ft wide |  | 14.49 | /sf |  |  |  | *2025 RS Means 02 41 16 33 0200
Guard Rail Demolition - Corrugated Steel |  | 3.21 | /lf |  |  |  | *2025 RS Means 02 41 13 20 0100
Bridge Footing Demolition |  | 38.2 | /cf |  |  |  | *2025 RS Means 02 41 19 16 0050
Fencing | Chain link, posts and wire, 8-10' high, removal + disposal | 4.34 | /lf |  |  |  | *2025 RS Means 02 41 13 60 1700
Surface Pipeline | Production Rate: Plastic Pipe Removal (3/4" - 4") | 700 | lf/day | 2.76 | /lf |  | *2025 RS Means 02 41 13 38 1600
Surface Pipeline | Production Rate: Plastic Pipe Removal (6" - 8") | 500 | lf/day | 3.85 | /lf |  | *2025 RS Means 02 41 13 38 1700
Surface Pipeline | Production Rate: Plastic Pipe Removal (10" - 18") | 300 | lf/day | 6.45 | /lf |  | *2025 RS Means 02 41 13 38 1800
Surface Pipeline | Production Rate: Plastic Pipe Removal (20"-36") | 200 | lf/day | 9.64 | /lf |  | *2025 RS Means 02 41 13 38 1900
Steel Bridge Deck Demolition | Production Rate | 500 | sf/day | 14.49 | /lf |  | *2025 RS Means 02 41 16 33 0200
Guard Rail Demolition | Production Rate | 600 | lf/day | 3.21 | /lf |  | *2025 RS Means 02 41 13 20 0100
Steel Tank Demolition | Above Ground: 550 - 2,000 gal | 1582 | /ea |  |  |  | *2025 RS Means 13 05 05 75 0520
Steel Tank Demolition | Above Ground: 5,000 - 10,000 gal | 2777 | /ea |  |  |  | *2025 RS Means 13 05 05 75 0530
Steel Tank Demolition | Above Ground: 15,000 - 30,000 gal | 4346 | /ea |  |  |  | *2025 RS Means 13 05 05 75 0540
Petroleum Tank Cleaning - 500 gal |  | 90.28 | /ea |  |  |  | *2025 RS Means 02 65 10 30 0813
Petroleum Tank Cleaning - 3,000 gal |  | 108.33 | /ea |  |  |  | *2025 RS Means 02 65 10 30 0823
Petroleum Tank Cleaning - 5,000 gal |  | 117.75 | /ea |  |  |  | *2025 RS Means 02 65 10 30 0833
Petroleum Tank Cleaning - 8,000 gal |  | 135.81 | /ea |  |  |  | *2025 RS Means 02 65 10 30 0843
Petroleum Tank Cleaning - 10,000 gal |  | 158.57 | /ea |  |  |  | *2025 RS Means 02 65 10 30 0853
Petroleum Tank Cleaning - 12,000+ gal |  | 171.92 | /ea |  |  |  | *2025 RS Means 02 65 10 30 0863
Underground Storage Tank Cleaning and Removal |  | 505.76 | /ea |  |  |  | *2025 RS Means 02 65 10 30 0320
Concrete Pressure Grouting, 1:1 Sand (for closing buried pipelines) |  | 61.58 | /cf |  |  |  | *2025 RS Means 31 43 13 13 0200
Gas Piping Removal | 3"-4" PE Pipe | 2.71 | /lf |  |  |  | *2025 RS Means 02 41 13 50 0200
Septic Pipeline and Infrastructure Excavation |  | 6.93 | /lf |  |  |  | *2025 RS Means 31 23 16 13 0110
Concrete Installation |  | 125.33 | /cy |  |  |  | *2025 RS Means 03 05 05 10 0280
Railroad Ties & Track Removal |  | 19.86 | /lf |  |  |  | *2025 RS Means 02 41 13 33 3500
DISPOSAL COSTS | [6 empty] | *Assumes double 30 CY/ 10 ton Roll-Off Box
Landfill Fee |  | 39 | /ton |  |  |  | Billings Regional Landfill (2021)
|  | 390 | /roll-off |  |  |  | Billings Regional Landfill (2021)
Dropoff & Haul Fee |  | 1200 | /ea |  |  |  | Mackenzie Disposal (2025)
Rental Rate |  | 4 | /day |  |  |  | Mackenzie Disposal (2025)
Rolloff Capacity |  | 10 | ton |  |  |  | Mackenzie Disposal (2025)
|  | 30 | CY |  |  |  | Mackenzie Disposal (2025)
|  | 810 | CF |  |  |  | Mackenzie Disposal (2025)
Hazardous Waste Disposal (Liquid) |  | 155 | /hr |  |  |  | *2025 RS Means 02 81 20 10 3110
Hazardous Waste Disposal (Sludge) |  | 155 | /hr |  |  |  | *2025 RS Means 02 81 20 10 5000
Hazardous Waste Disposal (Solid) |  | 655 | /ton |  |  |  | *2025 RS Means 02 81 20 10 1130
Hazardous Waste Transportation |  | 8 | /mi |  |  |  | *2025 RS Means 02 81 20 10 1270
Hazardous Waste Disposal |  | 455 | /ton |  |  |  | *2025 RS Means 02 81 20 10 6020
Transport Petroleum Tank to Salvage Dump (@100 mi RT) - 5,000 gal | Doubled RS Means for 200mi RT | 830 | /ea |  |  |  | *2025 RS Means 02 65 10 30 1023
Transport Petroleum Tank to Salvage Dump (@100 mi RT) - 8,000 gal | Doubled RS Means for 200mi RT | 960 | /ea |  |  |  | *2025 RS Means 02 65 10 30 1026
Transport Petroleum Tank to Salvage Dump (@100 mi RT) - 12,000 gal | Doubled RS Means for 200mi RT | 1150 | /ea |  |  |  | *2025 RS Means 02 65 10 30 1029
Petroleum Sludge Disposal |  | 7 | /gal |  |  |  | *2025 RS Means 02 65 10 30 0390
NOTES AND DETAILED CALCULATIONS:
Precipitation Plant Demolition and Removal
Floor Slab (Post-1974 area) | Surface Area (ft2) | Surface Area (acres)
| 11840 | 0.27181
Reported by MR
Bins/Walls (Post-1974 area) | Bin Area (ft2) (Est.) | Material Volume (ft3)
| 750 | 1125
| Estimated | 18" (1.5 ft) thick
Shaker Building Demolition and Removal
Shaker Building (Post-1974 area) | Surface Area (ft2) | 905 | Reported by MR
| Debris Volume (ft3) | 3016.6667 | Estimated 10' tall, assume steel frame, exterior, roof
| Debris Volume (yd3) | 111.7284 | https://vinedisposal.com/how-to-calculate-demolition-debris-waste.html
Shaker Foundation (Post-1974 area) | Slab Area (ft2) | 905
Pipeline- Removal and Disposal
Water Pipelines (36 inch HDPE) | Post-1974 Area Pipelines in Pink |  | TOTAL
N-S Embank |  |  | 22420
Main Lengths - 2 lines | 11040 | ft
| 8980 | ft
Lower/Lunchroom | 800 | ft
3 lines visible | 800 | ft
| 800 | ft
Tailings Pipelines (24-26 inch HDPE) |  |  | TOTAL
West +E-W Embank |  |  | 16665
Main Lengths | 5650 | ft
| 300 | ft
Spigot Lines | 460 | ft
| 460 | ft
| 110 | ft
| 120 | ft
| 260 | ft
| 260 | ft
| 330 | ft
| 290 | ft
| 420 | ft
| 640 | ft
| 600 | ft
| 200 | ft
| 120 | ft
N-S Embank
Main Length | 2820 | ft
Spigot Lines | 50 | ft
| 80 | ft
| 110 | ft
| 75 | ft
| 50 | ft
| 60 | ft
Lower/Lunchroom | 800 | ft
4 lines visible | 800 | ft
| 800 | ft
| 800 | ft
Precip Plant Railroad
Based on 2020 and 2025 Bond Maps:
The exposed/accessible length of railroad within post-1974 bonding areas is approx. 1,200 ft
Copper Precipitation Plant- MR22-001 Demolish and Remove Precipitation Plant (concrete slab and bins/walls) and Shaker Building (steel frame building) No post-mine use has been verified for BMFOU water treatment, assume the facilities will be demolished and removed Facilities will be dismantled and removed completely, the underlying ground will be reclaimed as described above Inert material will be disposed in the on-site disposal area MR22-001, Deficiency Response (8/1/2022): "Demolition and reclamation of the relocated Precipitation Plant will be consistent with the Continental Mine Reclamation Plan (December 2021). The subsequent update of the Consolidated Operations and Reclamation Plans will include the new Precipitation Plant location."
"When deemed appropriate, demolition and reclamation of the relocated Precipitation Plant will be consistent with the prior Precipitation Plant in the Continental Mine Reclamation Plan (December 2021)." MR22-001, Deficiency Response (9/12/2022):
"The relocated facility is being reverse engineered from the old facility. There are no IFC drawings or other drawings not already provided to DEQ. Construction materials and methods are standard materials and methods for industrial construction (e.g. 18" reinforced concrete and steel buildings)."
"All other operations (e.g. shaker building) are identical to the old facility."
2023 Reclamation Plan Citations; (Does not include the most recent number of tailings spigots)
5.3.3.1 Tailings Distribution System
Tailings are pumped from the Concentrator to the YDTI as a by-product of processing. The tailings distribution system is shown in Figure OP-5-4. The tailings distribution system utilizes tailings pumps, booster pump houses, and pipelines to convey tailings from the Concentrator to the YDTI. Four tailings pump house stations (the Main Tailings Pump House, McQueen Booster Pump House, No. 2 Booster Pump House, and No. 3 Booster Pump House) provide the required pressure to pump the tailings up to the YDTI – a total elevation increase of approximately 875 feet.
Three tailings distribution pipelines (two operational and one standby) transport tailings to the YDTI. Approximately 17,000 feet (3.25 miles) of existing tailings distribution pipeline has been installed at the project site, including sections of 22-inch steel pipe and 24- to 26-inch HDPE pipe. The single-walled tailings pipeline is installed on the ground surface and locally anchored with mounds of overburden or pipe support trestles. The tailings slurry flow rate is approximately 18,000 gpm with a solids concentration (by weight) between 33 and 37 percent.
5.3.4 Water Reclaim System
Supernatant water is reclaimed for reuse in the mill process from the northeast end of the YDTI using floating barges. MR maintains two reclaim water pump barge units in the supernatant pond (for redundancy). Each of the barges is equipped with four vertical turbine pump units. The barge pumps deliver a total of approximately 12,000 gpm of reclaim water into a junction box located on the side slope of Rampart Mountain, approximately 1,500 feet away (50 feet elevation increase). From the junction box, reclaim water gravity discharges to the mill at an elevation decrease of approximately 875 feet, and at a distance of 5.1 miles away. The reclaim water is initially conveyed back to the Concentrator via two 36-inch diameter HDPE pipelines (0.7 miles long). As the pipeline grade steepens down to the mill, the reclaim water is conveyed by a single 42-inch-diameter HDPE pipeline. Approximately the last mile of reclaim pipeline is further downsized to a 36-inch-steel pipeline for conveyance into the Butte Concentrator facilities.
The reclaim pipeline alignment follows the access road along the eastern edge of the YDTI. Immediately south of the Tailings No. 2 Booster Pump House, the reclaim pipeline enters the site pipeline corridor, which extends from the Butte Concentrator to the YDTI. As part of BMFOU water management (Pilot Project), a take-off valve has been installed in the reclaim pipeline near the McQueen Booster Pump House and a pipeline installed to the polishing facility.
The reclaim water is delivered to two locations at the Butte Concentrator: to the Concentrator building for direct use in processing and to the process water reservoir located west of the Butte Concentrator and Lime Slaker Silos. During the Pilot Project and potentially beyond mine operation, water will also be delivered to the polishing facility.

## 2-Earthmoving
Montana Resources, LLC
Operating Permit #00030
Final Comprehensive 5-Year Bond Review
2026-05-04
Task 2- Earthmoving (Backfilling, Grading, Ripping, Soil Placement)
CORRECTED ACREAGES ARE BELOW ON THIS TAB
Efficiency
Task | Equipment | Equipment | Grade | Other | Total Factor | Production |  | Net Production |  | Quantity |  | Total Required |  | Equipment Cost |  | Labor Cost |  | TOTAL COST |  | Source, Assumptions, Adjustments, etc
EARTHMOVING | [18 empty] | 2025 Prelim
Ripping | [19 empty] | SEE MORE NOTES BELOW
Roads + TSF Crest Roads (post-1974 area) | Dozer with Ripper (Cat D10T) | 0.83 | 0.9 | 0.95 | 0.70965 | 0.58081 | AC/hr | 0.41217 | AC/hr | 31.4903 | AC | 76.4012 | hr | 312.43 | /hr | 48.03 | /hr | 27539.5791 | 31800.6012 | Reduce current road footprints (width or acreage) by 50%, leave remaining roads for access
TSF: N-S Embankment Crest | Dozer with Ripper (Cat D10T) | 0.83 | 0.9 | 0.95 | 0.70965 | 0.58081 | AC/hr | 0.41217 | AC/hr | 42.6213 | AC | 103.4071 | hr | 312.43 | /hr | 48.03 | /hr | 37274.1213 | 23285.5819
TSF: E-W Embankment Crest | Dozer with Ripper (Cat D10T) | 0.83 | 0.9 | 0.95 | 0.70965 | 0.58081 | AC/hr | 0.41217 | AC/hr | 5.8198 | AC | 14.1199 | hr | 312.43 | /hr | 48.03 | /hr | 5089.6711 | 4983.3999
TSF: West Embankment Crest | Dozer with Ripper (Cat D10T) | 0.83 | 0.9 | 0.95 | 0.70965 | 0.58081 | AC/hr | 0.41217 | AC/hr | 67.3777 | AC | 163.4705 | hr | 312.43 | /hr | 48.03 | /hr | 58924.5944 | 60318.7835
Continental Pit- Accessible Benches | (2) Dozer with Ripper (Cat D10T) | 0.83 | 0.9 | 0.95 | 0.70965 | 1.1616 | AC/hr | 1.6487 | AC/hr | 210.485 | AC | 127.6687 | hr | 624.86 | /hr | 96.06 | /hr | 92038.8858 | 317883.9399 | *Production rate doubled to assume 2 Dozers (MR Operator Preliminary Bond comment 1/23/26)
Stockpile Footprints | Dozer with Ripper (Cat D10T) | 0.83 | 0.9 | 0.95 | 0.70965 | 0.58081 | AC/hr | 0.41217 | AC/hr | 42.4692 | AC | 103.038 | hr | 312.43 | /hr | 48.03 | /hr | 37141.0659 | 37141.0677
CZABA Bench/Ramp | Dozer with Ripper (Cat D10T) | 0.83 | 0.9 | 0.95 | 0.70965 | 0.58081 | AC/hr | 0.41217 | AC/hr | 58.6466 | AC | 142.2874 | hr | 312.43 | /hr | 48.03 | /hr | 51288.9048 | 51597.9245
Precip Plant Area (Facility Footprint) | Dozer (Cat D10T) | 0.83 | 0.9 | 0.75 | 0.56025 | 0.46488 | AC/hr | 0.26045 | AC/hr | 0.78436 | AC | 3.0116 | hr | 312.43 | /hr | 48.03 | /hr | 1085.5572 | 1085.5572
Misc Precipitation Plant RR | Dozer (Cat D10T) | 0.83 | 0.9 | 0.75 | 0.56025 | 0.46488 | AC/hr | 0.26045 | AC/hr | 0.33219 | AC | 1.2755 | hr | 312.43 | /hr | 48.03 | /hr | 459.7544 | 459.7554
Recontouring - Regrading | [19 empty] | SEE MORE NOTES BELOW
TSF: N-S Embankment Upstream | Dozer (Cat D10T) | 0.83 | 0.9 | 0.75 | 0.56025 | 1500 | LCY/hr | 840.375 | LCY/hr | 144500 | LCY | 171.947 | hr | 312.43 | /hr | 48.03 | /hr | 61980.0327 | 61980.0327
TSF: N-S Embankment Downstream | Dozer (Cat D10T) | 0.83 | 0.9 | 0.75 | 0.56025 | 1500 | LCY/hr | 840.375 | LCY/hr | 2110684.7407 | LCY | 2511.5987 | hr | 312.43 | /hr | 48.03 | /hr | 905330.8602 | 905330.8602
TSF: E-W Embankment Upstream | Dozer (Cat D10T) | 0.83 | 0.9 | 0.75 | 0.56025 | 1500 | LCY/hr | 840.375 | LCY/hr | 36125 | LCY | 42.9868 | hr | 312.43 | /hr | 48.03 | /hr | 15495.0082 | 15495.0082
TSF: E-W Embankment Downstream | Dozer (Cat D10T) | 0.83 | 0.9 | 0.75 | 0.56025 | 1500 | LCY/hr | 840.375 | LCY/hr | 4515.625 | LCY | 5.3733 | hr | 312.43 | /hr | 48.03 | /hr | 1936.876 | 1936.876
TSF: West Embankment Upstream | Dozer (Cat D10T) | 0.83 | 0.9 | 0.75 | 0.56025 | 1500 | LCY/hr | 840.375 | LCY/hr | 231200 | LCY | 275.1153 | hr | 312.43 | /hr | 48.03 | /hr | 99168.0524 | 99168.0524
TSF: West Embankment Downstream | NA- At final slope, further grading not needed | [8 empty] | 0.80739 | AC
TSF: Beach Settlement (10% of area) | Dozer (Cat D6) | 0.83 | 0.9 | 0.95 | 0.70965 | 0.13946 | AC/hr | 0.09897 | AC/hr | 98.7163 | AC | 997.4385 | hr | 92.68 | /hr | 48.03 | /hr | 140349.5727 | 126211.3554 | 10% area of the estimated beach area. Previous bond had lump sum $500k.
RDS Access | Dozer (Cat D10T) | 0.83 | 0.9 | 0.75 | 0.56025 | 1500 | LCY/hr | 840.375 | LCY/hr | 184960 | LCY | 220.0922 | hr | 312.43 | /hr | 48.03 | /hr | 79334.4419 | 79334.4419 | *Not split up on map, like others: 7.0 acres measured on dump top, remaining slope (corrected) is 12.5 ac
RDS Access Crest | Dozer (Cat D10T) | 0.83 | 0.9 | 0.95 | 0.70965 | 0.46488 | AC/hr | 0.3299 | AC/hr | 7.6697 | AC | 23.2485 | hr | 312.43 | /hr | 48.03 | /hr | 8380.1683 | 7853.9535 | *Not split up on map, like others: 7.0 acres measured on dump top, remaining slope (corrected) is 12.5 ac
RDS East | Dozer (Cat D10T) | 0.83 | 0.9 | 0.75 | 0.56025 | 1500 | LCY/hr | 840.375 | LCY/hr | 818807 | LCY | 974.3353 | hr | 312.43 | /hr | 48.03 | /hr | 351208.8903 | 351208.8903
RDS East Crest | Dozer (Cat D10T) | 0.83 | 0.9 | 0.95 | 0.70965 | 0.46488 | AC/hr | 0.3299 | AC/hr | 29.3583 | AC | 88.9916 | hr | 166.29 | /hr | 48.03 | /hr | 19072.6753 | 19072.6751
RDS Great Northern | Within Pre-1974 area ($500/acre) |  |  |  | Accounted in other acreage tracking | [12 empty] | 0 | 0
RDS Hillcrest - RELEASED | NA- previously released, further grading not needed | [16 empty] | 0 | 0
RDS HSB | Within Pre-1974 area ($500/acre) |  |  |  | Accounted in other acreage tracking | [12 empty] | 0 | 0
RDS Nalley Valley | Dozer (Cat D10T) | 0.83 | 0.9 | 0.75 | 0.56025 | 1500 | LCY/hr | 840.375 | LCY/hr | 885062.5 | LCY | 1053.1757 | hr | 312.43 | /hr | 48.03 | /hr | 379627.7004 | 379627.7004
RDS North | Dozer (Cat D10T) | 0.83 | 0.9 | 0.75 | 0.56025 | 0.46488 | AC/hr | 0.26045 | AC/hr | 11.9453 | AC | 45.8646 | hr | 312.43 | /hr | 48.03 | /hr | 16532.3684 | 11022.0869
RDS North Crest | Dozer (Cat D10T) | 0.83 | 0.9 | 0.95 | 0.70965 | 0.46488 | AC/hr | 0.3299 | AC/hr | 12.31 | AC | 37.3145 | hr | 166.29 | /hr | 48.03 | /hr | 7997.2338 |  | Not depicted in prior map
RDS North East - RELEASED | NA- previously released, further grading not needed | [16 empty] | 0 | 0
RDS North East- 2022 D East Expansion | Combined into other features in new map | [16 empty] | 0 | 2768.0125
RDS North East- 2025 E East Drilling | Combined into other features in new map | [16 empty] | 0 | 13840.0627
RDS Pittsmont | Dozer (Cat D10T) | 0.83 | 0.9 | 0.75 | 0.56025 | 1500 | LCY/hr | 840.375 | LCY/hr | 1228250 | LCY | 1461.5499 | hr | 312.43 | /hr | 48.03 | /hr | 526830.2781 | 526830.2781 | Includes RDS face that will be exposed from relocating rock to S Cont Pit RDS
RDS Pittsmont Crest | Dozer (Cat D10T) | 0.83 | 0.9 | 0.75 | 0.56025 | 0.46488 | AC/hr | 0.26045 | AC/hr | 26.5904 | AC | 102.0953 | hr | 312.43 | /hr | 48.03 | /hr | 36801.2781 | 38047.2787
RDS South Continental Pit | Dozer (Cat D10T) | 0.83 | 0.9 | 0.75 | 0.56025 | 1500 | LCY/hr | 840.375 | LCY/hr | 293515.625 | LCY | 349.2674 | hr | 312.43 | /hr | 48.03 | /hr | 125896.9415 | 125896.9415
RDS South Continental Pit Crest | Dozer (Cat D10T) | 0.83 | 0.9 | 0.75 | 0.56025 | 0.46488 | AC/hr | 0.26045 | AC/hr | 18.1201 | AC | 69.5733 | hr | 312.43 | /hr | 48.03 | /hr | 25078.3839 | 12852.4171
RDS Woodville - RELEASED | NA- previously released, further grading not needed | [16 empty] | 0 | 0
Leach Pads- Crest | Dozer (Cat D10T) | 0.83 | 0.9 | 0.75 | 0.56025 | 0.46488 | AC/hr | 0.26045 | AC/hr | 7.5139 | AC | 28.8501 | hr | 312.43 | /hr | 48.03 | /hr | 10399.2997 | 10399.3011
Pit Benches | Dozer (Cat D10T) | 0.83 | 0.9 | 0.75 | 0.56025 | 0.46488 | AC/hr | 0.26045 | AC/hr | 210.485 | AC | 808.1688 | hr | 312.43 | /hr | 48.03 | /hr | 291312.5426 | 251533.8434
Roads | Dozer (Cat D10T) | 0.83 | 0.9 | 0.75 | 0.56025 | 0.46488 | AC/hr | 0.26045 | AC/hr | 31.4903 | AC | 120.9088 | hr | 312.43 | /hr | 48.03 | /hr | 43582.8006 | 50326.0872
Misc. Disturbance | Dozer (Cat D10T) | 0.83 | 0.9 | 0.75 | 0.56025 | 0.46488 | AC/hr | 0.26045 | AC/hr | 175.0165 | AC | 671.9857 | hr | 312.43 | /hr | 48.03 | /hr | 242223.9735 | 334038.2165
CZABA Bench/Ramp | Dozer (Cat D10T) | 0.83 | 0.9 | 0.75 | 0.56025 | 0.46488 | AC/hr | 0.26045 | AC/hr | 58.6466 | AC | 225.1771 | hr | 312.43 | /hr | 48.03 | /hr | 81167.3302 | 81656.3698
Rock Removal and Relocation
RDS Pittsmont- Portion Removed for CZABA | 988 Loader, 740 Truck, D8T Dozer | 0.75 | 0.95 | 0.9 | 0.64125 | 806.9238 | LCY/hr | 517.4399 | LCY/hr | 265200 | LCY | 512.5233 | hr | 604.13 | /hr |  |  | 309630.722 | 309630.722 | SEE MORE NOTES BELOW
Alluvium/Soil Placement | [7 empty] | TOTAL VOLUME NEEDED |  | 6250166.7229 | LCY | [8 empty] | SEE MORE NOTES BELOW | *Dozer costs removed from LHD task for most features, addressed in following dozer line item with D10T (MR Operator Preliminary Bond comment 1/23/26)
Areas receiving Alluvium +/- Soil: | [7 empty] | TOTAL AREA COVERED |  | 1870.6551 | AC | [9 empty] | *Production rates doubled to assume 2 Dozers, where applicable (MR Operator Preliminary Bond comment 1/23/26)
TSF: N-S Embankment (Load/Haul/Dump) | 6020B Shovel, 777 Truck | 0.75 | 0.95 | 0.9 | 0.64125 | 1344.6985 | LCY/hr | 862.2879 | LCY/hr | 319851.6591 | LCY | 370.9337 | hr | 2475.59 | /hr |  |  | 918279.7652 | 1165831.28 | *Labor included in Equipment total
Spread Alluvium | (2) D10T | 0.83 | 0.95 | 0.75 | 0.59137 | 1200 | LCY/hr | 709.65 | LCY/hr | 319851.6591 | LCY | 450.7175 | hr | 624.86 | /hr | 96.06 | /hr | 324931.2451 | 703282.5988
TSF: E-W Embankment (Load/Haul/Dump) | 6020B Shovel, 777 Truck | 0.75 | 0.95 | 0.9 | 0.64125 | 1261.2657 | LCY/hr | 808.7867 | LCY/hr | 28770.545 | LCY | 35.5725 | hr | 2475.59 | /hr |  |  | 88062.8696 | 121867.5512 | *Labor included in Equipment total
Spread Alluvium | (2) D10T | 0.83 | 0.95 | 0.75 | 0.59137 | 1200 | LCY/hr | 709.65 | LCY/hr | 28770.545 | LCY | 40.5419 | hr | 624.86 | /hr | 96.06 | /hr | 29227.4519 | 68954.7066
TSF: West Embankment (Load/Haul/Dump) - Alluvium Area (Includes 20" and 28") | 6020B Shovel, 777 Truck | 0.75 | 0.95 | 0.9 | 0.64125 | 1373.0187 | LCY/hr | 880.4483 | LCY/hr | 311758.7724 | LCY | 354.091 | hr | 3226.34 | /hr |  |  | 1142417.8358 | 2387667.2406 | *Labor included in Equipment total | *Removed 21.7 acres of earthwork, for partial release on West Embankment
Spread Alluvium | (2) D10T | 0.83 | 0.9 | 0.75 | 0.56025 | 1200 | LCY/hr | 672.3 | LCY/hr | 311758.7724 | LCY | 463.7197 | hr | 624.86 | /hr | 96.06 | /hr | 334304.8256 | 1233521.1345 |  | *Removed 21.7 acres of earthwork, for partial release on West Embankment
TSF: West Embankment- Soil Area (6" added on 14" alluvium) | 980 Loader, (3) 740 Truck | 0.75 | 0.95 | 0.9 | 0.64125 | 427.5862 | LCY/hr | 274.1897 | LCY/hr | 4837.5742 | LCY | 17.6432 | hr | 604.13 | /hr |  |  | 10658.7673 | 48560.5502 | *Labor included in Equipment total | *Removed 21.7 acres of earthwork, for partial release on West Embankment
Spread Soil | (2) D8T | 0.83 | 0.9 | 0.75 | 0.56025 | 500 | LCY/hr | 280.125 | LCY/hr | 4837.5742 | LCY | 17.2693 | hr | 332.58 | /hr | 96.06 | /hr | 7402.3305 | 33724.4665 |  | *Removed 21.7 acres of earthwork, for partial release on West Embankment
TSF: Beach at Closure- Alluvium Area (Includes 22" and 28") | 6020B Shovel/980 Loader, 777/740 Truck, D8T Dozer | 0.75 | 0.95 | 0.9 | 0.64125 | 1344.6985 | LCY/hr | 862.2879 | LCY/hr | 2474101.055 | LCY | 2869.2284 | hr | 3455.24 | /hr |  |  | 9913872.7508 | 9207932.0194 | *Labor included in Equipment total
Spread Alluvium | (1) D10T | 0.83 | 0.9 | 0.75 | 0.56025 | 600 | LCY/hr | 336.15 | LCY/hr | 2474101.055 | LCY | 7360.1102 | hr | 312.43 | /hr | 48.03 | /hr | 2653025.3348 | 2464110.3979
TSF: Beach at Closure- Soil Area (6" added on 22" alluvium) | 980 Loader, 740 Truck, D8T Dozer | 0.75 | 0.95 | 0.9 | 0.64125 | 347.6636 | LCY/hr | 222.9393 | LCY/hr | 294836.6667 | LCY | 1322.4978 | hr | 604.13 | /hr |  |  | 798960.5849 | 798960.5849 | *Labor included in Equipment total
Spread Soil | (2) D8T | 0.83 | 0.9 | 0.75 | 0.56025 | 500 | LCY/hr | 280.125 | LCY/hr | 294836.6667 | LCY | 1052.5182 | hr | 332.58 | /hr | 96.06 | /hr | 451151.4103 | 451151.4103
RDS Access (includes slope and crest) | 6020B Shovel, 777 Truck | 0.75 | 0.95 | 0.9 | 0.64125 | 1338.0531 | LCY/hr | 858.0265 | LCY/hr | 46974.0182 | LCY | 54.7466 | hr | 2225.34 | /hr |  |  | 121829.7519 | 141290.8221 | *Labor included in Equipment total
Spread Alluvium | (2) D10T | 0.83 | 0.9 | 0.75 | 0.56025 | 1200 | LCY/hr | 672.3 | LCY/hr | 46974.0182 | LCY | 69.8706 | hr | 624.86 | /hr | 96.06 | /hr | 50371.1277 | 97965.0107
RDS East (includes slope and crest) | 980 Loader, 740 Truck | 0.75 | 0.95 | 0.9 | 0.64125 | 1344.6985 | LCY/hr | 862.2879 | LCY/hr | 149875.1163 | LCY | 173.811 | hr | 2475.59 | /hr |  |  | 430284.7357 | 397157.4336 | *Labor included in Equipment total
Spread Alluvium | (2) D10T | 0.83 | 0.9 | 0.75 | 0.56025 | 1200 | LCY/hr | 672.3 | LCY/hr | 149875.1163 | LCY | 222.9289 | hr | 624.86 | /hr | 96.06 | /hr | 160713.9206 | 252893.6705
RDS Great Northern | Within Pre-1974 area ($500/acre) | [16 empty] | 0 | 0 | Accounted in other acreage tracking
RDS Hillcrest - RELEASED | Previous Partial Release | [16 empty] | 0 | 0
RDS HSB | Within Pre-1974 area ($500/acre) | [16 empty] | 0 | 0 | Accounted in other acreage tracking
RDS Nalley Valley | 6020B Shovel, 777 Truck | 0.75 | 0.95 | 0.9 | 0.64125 | 1481.8727 | LCY/hr | 950.2509 | LCY/hr | 92577.7495 | LCY | 97.4245 | hr | 1474.59 | /hr |  |  | 143661.2486 | 173778.15 | *Labor included in Equipment total
Spread Alluvium | (2) D10T | 0.83 | 0.9 | 0.75 | 0.56025 | 1200 | LCY/hr | 672.3 | LCY/hr | 92577.7495 | LCY | 137.703 | hr | 624.86 | /hr | 96.06 | /hr | 99272.871 | 186078.4673
RDS North (Includes Crest) | 6020B Shovel, 777 Truck | 0.75 | 0.95 | 0.9 | 0.64125 | 1684.2421 | LCY/hr | 1080.0202 | LCY/hr | 91307.7677 | LCY | 84.5426 | hr | 1474.59 | /hr |  |  | 124665.7389 | 52830.6611 | *Labor included in Equipment total
Spread Alluvium | (2) D10T | 0.83 | 0.9 | 0.75 | 0.56025 | 1200 | LCY/hr | 672.3 | LCY/hr | 91307.7677 | LCY | 135.814 | hr | 624.86 | /hr | 96.06 | /hr | 97911.0455 | 64295.5068 | Feature did not exist prior to 2020 bond review
RDS North East - RELEASED | Previous Partial Release | [16 empty] | 0 | 0
RDS North East- 2022 D East Expansion | Combined into other features in new map | [16 empty] | 0 | 14871.3701
RDS North East- 2025 E East Drilling | Combined into other features in new map | [16 empty] | 0 | 18799.3115 | *Labor included in Equipment total
RDS Pittsmont (includes slope and crest) | 6020B Shovel, 777 Truck | 0.75 | 0.95 | 0.9 | 0.64125 | 1305.0289 | LCY/hr | 836.8498 | LCY/hr | 271504.8015 | LCY | 324.4367 | hr | 1224.34 | /hr |  |  | 397220.8614 | 558100.8697 | *Labor included in Equipment total
Spread Alluvium | (2) D10T | 0.83 | 0.9 | 0.75 | 0.56025 | 1200 | LCY/hr | 672.3 | LCY/hr | 271504.8015 | LCY | 403.8447 | hr | 624.86 | /hr | 96.06 | /hr | 291139.7315 | 605963.6358
RDS South Continental Pit (includes slope and crest) | 6020B Shovel, 777 Truck | 0.75 | 0.95 | 0.9 | 0.64125 | 1481.8727 | LCY/hr | 950.2509 | LCY/hr | 184655.5074 | LCY | 194.3229 | hr | 1474.59 | /hr |  |  | 286546.615 | 178953.7243 | *Labor included in Equipment total
Spread Alluvium | (2) D10T | 0.83 | 0.9 | 0.75 | 0.56025 | 1200 | LCY/hr | 672.3 | LCY/hr | 184655.5074 | LCY | 274.6624 | hr | 624.86 | /hr | 96.06 | /hr | 198009.5915 | 191620.3777
RDS Woodville - RELEASED | Previous Partial Release | [16 empty] | 0 | 0
Leach Pads | 6020B Shovel, 777 Truck | 0.75 | 0.95 | 0.9 | 0.64125 | 1252.4439 | LCY/hr | 803.1297 | LCY/hr | 28285.6999 | LCY | 35.2193 | hr | 1975.09 | /hr |  |  | 69561.3735 | 84657.8044 | *Labor included in Equipment total
Spread Alluvium | (2) D10T | 0.83 | 0.9 | 0.75 | 0.56025 | 1200 | LCY/hr | 672.3 | LCY/hr | 28285.6999 | LCY | 42.073 | hr | 624.86 | /hr | 96.06 | /hr | 30331.2908 | 60662.5898
Pit Benches | 6020B Shovel, 777 Truck | 0.75 | 0.95 | 0.9 | 0.64125 | 1428.4643 | LCY/hr | 916.0028 | LCY/hr | 792359.044 | LCY | 865.0182 | hr | 1975.09 | /hr |  |  | 1708488.7575 | 1795346.0149 | *Labor included in Equipment total
Spread Alluvium | (2) D10T | 0.83 | 0.9 | 0.75 | 0.56025 | 1200 | LCY/hr | 672.3 | LCY/hr | 792359.044 | LCY | 1178.5796 | hr | 624.86 | /hr | 96.06 | /hr | 849661.5826 | 1467280.7534
Roads | 6020B Shovel, 777 Truck | 0.75 | 0.95 | 0.9 | 0.64125 | 1192.1804 | LCY/hr | 764.4857 | LCY/hr | 118543.5613 | LCY | 155.0632 | hr | 1474.59 | /hr |  |  | 228654.5822 | 340783.0069 | *Labor included in Equipment total
Spread Alluvium | (2) D10T | 0.83 | 0.9 | 0.75 | 0.56025 | 1200 | LCY/hr | 672.3 | LCY/hr | 118543.5613 | LCY | 176.3254 | hr | 624.86 | /hr | 96.06 | /hr | 127116.5019 | 293568.8422
Misc. Disturbance | 6020B Shovel, 777 Truck | 0.75 | 0.95 | 0.9 | 0.64125 | 1192.1804 | LCY/hr | 764.4857 | LCY/hr | 658840.0017 | LCY | 861.8082 | hr | 1474.59 | /hr |  |  | 1270813.7298 | 2261939.167 | *Labor included in Equipment total
Spread Alluvium | (2) D10T | 0.83 | 0.9 | 0.75 | 0.56025 | 1200 | LCY/hr | 672.3 | LCY/hr | 658840.0017 | LCY | 979.9792 | hr | 624.86 | /hr | 96.06 | /hr | 706486.5893 | 1948556.263
Precip Plant Area | 6020B Shovel, 777 Truck | 0.75 | 0.95 | 0.9 | 0.64125 | 1192.1804 | LCY/hr | 764.4857 | LCY/hr | 2952.6745 | LCY | 3.8623 | hr | 1474.59 | /hr |  |  | 5695.3118 | 7350.8482
Spread Alluvium | (2) D10T | 0.83 | 0.9 | 0.75 | 0.56025 | 1200 | LCY/hr | 672.3 | LCY/hr | 2952.6745 | LCY | 4.3919 | hr | 624.86 | /hr | 96.06 | /hr | 3166.2086 | 6332.4167
Misc Precipitation Plant RR | 6020B Shovel, 777 Truck | 0.75 | 0.95 | 0.9 | 0.64125 | 1192.1804 | LCY/hr | 764.4857 | LCY/hr | 1250.5144 | LCY | 1.6358 | hr | 1474.59 | /hr |  |  | 2412.0741 | 3113.2329
Spread Alluvium | (2) D10T | 0.83 | 0.9 | 0.75 | 0.56025 | 1200 | LCY/hr | 672.3 | LCY/hr | 1250.5144 | LCY | 1.8601 | hr | 624.86 | /hr | 96.06 | /hr | 1340.9503 | 2681.9065
TSF Transition Zone - Reclamation Begins in Year 5, After Exposure in Years 0-4 | [19 empty] | SEE MORE NOTES BELOW
Recontouring/Regrading
TSF: Transition Zone Settlement (10% of area) | Dozer (Cat D6) | 0.83 | 0.9 | 0.95 | 0.70965 | 0.13946 | AC/hr | 0.09897 | AC/hr | 4.4931 | AC | 45.3985 | hr | 92.68 | /hr | 48.03 | /hr | 6388.0256 | 5051.5062 | 10% area of the exposed south transition zone (in Year 5)- not North Transitio Zone
Assume placement in new stockpile near Transition Zone during the initial reclamation phase- then Long Term costs apply to moving material out of stockpile (not Central Zone haul)
Alluvium/Soil Placement | [9 empty] | 251.6126 | AC
TSF- Move Alluvium to create Transition Zone Stockpile for future (Load Haul Dump) | 6020B Shovel, 777 Truck | 0.75 | 0.95 | 0.9 | 0.64125 | 1063.3388 | LCY/hr | 681.866 | LCY/hr | 676558.2352 | LCY | 992.2158 | hr | 2475.59 |  |  |  | 2456319.5216 | 1942401.9399 | 2020 bond assumed a Central Zone haul (17,500 ft) and testing campaign every 5 years (in NPV)
TSF- North Transition Zone | Only seeded- no alluvium placement | [8 empty] | 50.7923 | AC | [6 empty] | 0 | 0
Applied to Long Term (future) and not Years 0-5 | *above row for full volume with Shovel/777 truck | [18 empty] | For LHD each time, every 5 years
TSF- Tailings Transition Zone (from stockpile) | 365 Excavator, 740 Truck | 0.75 | 0.95 | 0.9 | 0.64125 | 315.7407 | LCY/hr | 202.4688 | LCY/hr | 676558.2352 | LCY | 3341.544 | hr | 356.3 | /hr |  | 1993839.7384 |  | 3824105.9428 | For 30 years
Spread material relocated from stockpile to new beach | (2) D8T | 0.83 | 0.9 | 0.75 | 0.56025 | 500 | LCY/hr | 280.125 | LCY/hr | 676558.2352 | LCY | 2415.2012 | hr | 332.58 | /hr | 96.06 | /hr |  |  | Added to row above, to be split out over 5 years
Alluvium Testing and Separation | [19 empty] | SEE MORE NOTES BELOW
Alluvium Volume for Testing (not all suitable) | Many parameters and variable sampling frequencies, based on volume- see calculations below | [8 empty] | 7812708.4036 | LCY | [6 empty] | 538212.6222 | 529304.7387 | Suitable material placement is addressed in costs above
Separate Nonsuitable Material:
Non-Suitable Material (Load Haul Dump at RDS) | 6020B Shovel, 777 Truck | 0.75 | 0.95 | 0.9 | 0.64125 | 1063.3388 | LCY/hr | 681.866 | LCY/hr | 1562541.6807 | LCY | 2291.567 | hr | 1224.34 | /hr |  |  | 2805657.1848 | 2791273.3982 | Unsuitable material (assumed to be extra 25% of material excavated)- hauled to RDS S. Cont. Pit
Respread Soil Monitoring | [19 empty] | SEE MORE NOTES BELOW
All features receiving alluvium and soil placement | Many parameters and variable sampling frequencies, based on acreage- see calculations below | [16 empty] | 601457.6492 | 599202.5152
Hot Spot Repair- Hillcrest | [19 empty] | SEE MORE NOTES BELOW
RDS Hillcrest Hot Spots (estimated area) | Dozer (Cat D8T) | [6 empty] | 4 | hr/hot spot | 10 | hot spots | 40 | hr | 166.29 | /hr | 48.03 | /hr | 16636.6766 | 16636.6766 | Includes dozer for ripping/incorporating to 18 inches, plus the cost for lime
Construct Surface Water Collection Ditches
TSF: N-S Embankment | Dozer (Cat D8T) | [6 empty] | 100 | lf/hr | 19500 | lf | 195 | hr | 166.29 | /hr | 48.03 | /hr | 41792.4 | 41792.4 | Prior bond map measurements
TSF: E-W Embankment | Dozer (Cat D8T) | [6 empty] | 100 | lf/hr | 16500 | lf | 165 | hr | 166.29 | /hr | 48.03 | /hr | 35362.8 | 35362.8 | Prior bond map measurements
TSF: West Embankment | NA | [16 empty] | 0 | 0 | Not Applicable for short slopes, only basins
RDS Access | Dozer (Cat D8T) | [6 empty] | 100 | lf/hr | 1000 | lf | 10 | hr | 166.29 | /hr | 48.03 | /hr | 2143.2 | 2143.2 | Prior bond map measurements
RDS East | Dozer (Cat D8T) | [6 empty] | 100 | lf/hr | 15000 | lf | 150 | hr | 166.29 | /hr | 48.03 | /hr | 32148 | 32148 | Prior bond map measurements
RDS Great Northern | Within Pre-1974 area ($500/acre) | [16 empty] | 0 | 0 | Accounted in other acreage tracking
RDS Hillcrest | Dozer (Cat D8T) | [6 empty] | 100 | lf/hr | 11000 | lf | 110 | hr | 166.29 | /hr | 48.03 | /hr | 23575.2 | 23575.2 | Prior bond map measurements
RDS HSB | Within Pre-1974 area ($500/acre) | [16 empty] | 0 | 0 | Accounted in other acreage tracking
RDS Nalley Valley | Dozer (Cat D8T) | [6 empty] | 100 | lf/hr | 1000 | lf | 10 | hr | 166.29 | /hr | 48.03 | /hr | 2143.2 | 2143.2 | Prior bond map measurements
RDS North - Adjacent to TSF (Amend 010) | Dozer (Cat D8T) | [6 empty] | 100 | lf/hr | 7000 | lf | 70 | hr | 166.29 | /hr | 48.03 | /hr | 15002.4 | 15002.4 | Prior bond map measurements
RDS North East - RELEASED | NA | [16 empty] | 0 | 0 | Previous Partial Release
RDS Pittsmont | Dozer (Cat D8T) | [6 empty] | 100 | lf/hr | 7000 | lf | 70 | hr | 166.29 | /hr | 48.03 | /hr | 15002.4 | 15002.4 | Prior bond map measurements
RDS Woodville - RELEASED | NA | [16 empty] | 0 | 0 | Previous Partial Release
RDS South Continental Pit | Dozer (Cat D8T) | [6 empty] | 100 | lf/hr | 650 | lf | 6.5 | hr | 166.29 | /hr | 48.03 | /hr | 1393.08 | 1393.08 | Prior bond map measurements
Roads (post-1974 areas) | Dozer (Cat D8T) | [6 empty] | 100 | lf/hr | 34877.9121 | lf | 348.7791 | hr | 166.29 | /hr | 48.03 | /hr | 74750.3413 | 104324.5906 | Prior bond map measurements
Runoff Ditch A | Within Pre-1974 area ($500/acre) | [16 empty] | 0 | 0 | Accounted in other acreage tracking
Runoff Ditch B | Dozer (Cat D8T) | 0.83 | 0.9 | 0.95 | 0.70965 | 0.25 | AC/hr | 100 | lf/hr | 8850 | lf | 88.5 | hr | 166.29 | /hr | 48.03 | /hr | 18967.32 | 18967.32 | 2023 Rec Plan- Measure Map (GIS or Google)
Runoff Ditch C (post-1974 areas) | Dozer (Cat D8T) | 0.83 | 0.9 | 0.95 | 0.70965 | 0.25 | AC/hr | 100 | lf/hr | 4800 | lf | 48 | hr | 166.29 | /hr | 48.03 | /hr | 10287.36 | 10287.36 | 2023 Rec Plan- Measure Map (GIS or Google)
Runoff Ditch- Clearwater (not upper 840 ft) | Dozer (Cat D8T) | 0.83 | 0.9 | 0.95 | 0.70965 | 0.25 | AC/hr | 100 | lf/hr | 15000 | lf | 150 | hr | 166.29 | /hr | 48.03 | /hr | 32148 | 32148 | Upper 840 ft is bonded separately
Rip Rap Channel Protection
Rip Rap Ditches (Machine placed for Slope Protection) | [7 empty] | ASSUME 30% NEED RIP RAP |  | 32190 | lf | 63187.7778 | cy | 52.65 | /cy |  |  | 3326836.5 | 3326836.5 | 2025 RSMeans 31 37 13 10 0100
Rip Rap Roads (Machine placed for Slope Protection) | [7 empty] | ASSUME 50% NEED RIP RAP |  | 17438.9561 | lf | 8073.5908 | cy | 52.65 | /cy |  |  | 425074.5541 | 593251.1887 | 2025 RSMeans 31 37 13 10 0100
Rip Rap Slope above HSB
TSF: E-W Embankment | A portion removed by Minor Amend 011, which would be graded to 3:1, capped with soil, and revegetated. Other portions of 2:1 slope and riprap would remain until future permitting | [8 empty] | Within Pre-1974 area ($500/acre) | [7 empty] | 0 | 0 | Accounted in other acreage tracking
TSF: N-S Embankment | A portion removed by Minor Amend 011, which would be graded to 3:1, capped with soil, and revegetated. Other portions of 2:1 slope and riprap would remain until future permitting | [8 empty] | Within Pre-1974 area ($500/acre) | [7 empty] | 0 | 0 | Accounted in other acreage tracking
Runoff Settling Basins
Basins in pre-1974 areas (n = 5) | Within Pre-1974 area ($500/acre) | [16 empty] | 0 | 0 | Accounted in other acreage tracking
Basins in post-1974 areas (n = 5; 0.1 acre each) | Dozer (Cat D8T) | 0.83 | 0.9 | 0.95 | 0.70965 | 0.25 | AC/hr | 0.17741 | AC/hr | 0.5 | AC | 2.8183 | hr | 166.29 | /hr | 51.53 | /hr | 613.8801 | 613.8801
Upper Clearwater Ditch Improvements
Install HDPE pipe (24 inch) | Corrugated HDPE 24" Type S | [8 empty] | 840 | lf |  |  | 45.01 | /lf |  |  | 37808.4 | 37808.4 | 2025 RSMeans 33 42 11 50 1070
Install Concrete Manholes (n = 5) | Storm Drainage Manhole (6'ID x 4' deep) | [8 empty] | 5 | qty |  |  | 4597.97 | each |  |  | 22989.85 | 22989.85 | 2025 RSMeans 33 05 61 10 1190
Rip Rap- purchase and machine placed | Assumes 100lf | Assume approx. 27 ft^3 riprap per foot length of armored swale (KP, 2020; half of the volumetric conversion of the TSF Spillway) | [7 empty] | 100 | LCY |  |  | 52.65 | /LCY |  |  | 5265 | 5265 | 2025 RSMeans 31 37 13 10 0100
Install slope reinforcement mat | [9 empty] | 100 | sqyd |  |  | 6.02 | sqyd |  |  | 602 | 602 | 2025 RSMeans 31 25 14 16 0062
Excavation and Backfill
Pipe Excavation & Backfill | 3' wide x 6' deep trench | [8 empty] | 840 | lf | 560 | cy | 10.14 | /cy |  |  | 5678.4 | 5678.4 | 2025 RSMeans 31 23 16 13 0110 & 31 23 16 13 3020
Manhole Excavation & Backfill | 12' x 12' x 8' deep | [8 empty] | 5 | qty | 42.6667 | cy | 12.47 | /cy |  |  | 532.0533 | 532.0533 | 2025 RSMeans 31 23 16 13 0500 & 31 23 16 13 3020
EARTHMOVING TOTAL | [17 empty] | 38722618.9469 | 44482238.6884
General Earthmoving Assumptions
Equipment Efficiency:
Crawler Equipment (tracks) | Rubber-tired Equipment | Condition
0.92 | 0.83 | Excellent
0.83 | 0.75 | Average
0.75 | 0.67 | Poor/Night
Dozer Groundwork Production: | 0.25 | AC/hr |  | Includes assumed equipment and operator efficiency rates
D6T Contouring/Dozer Equipment Production Calculations |  |  |  | Dozer D8T
Dozer Material Moving
Dozer Pushing Production @ 100ft Push Distance | 450 | LCY/hr |  | *Cat Production Handbook 49 (19-61)
Volume to Push (2ft depth) | 3226.6667 | LCY/AC
Dozer Production Rate | 0.13946 | AC/hr
Dozer Grading
Dozer Grading Speed | 2.1 | mph
Blade Width (Semi U) | 10.6667 | ft |  | *Cat Production Handbook 49 (19-47)
Grading Pass Overlap | 2 | ft
Dozer Production Rate | 2.2061 | AC/hr
Dozer Ripping
Dozer Ripping Speed | 1 | mph
Rip Width | 7.25 | ft |  | *Cat Production Handbook 49 (19-75)
Rip Length (per Acre) | 6008.2759 | ft
Rip Time (per Acre) | 1.1379 | hr
Shank Depth | 3 | ft
Volume Ripped | 4840 | cy/AC
Dozer Ripping Production Rate | 0.87879 | AC/hr
D8T Contouring/Dozer Equipment Production Calculations |  |  |  | Dozer D8T
Dozer Material Moving
Dozer Pushing Production @ 100ft Push Distance | 800 | LCY/hr |  | *Cat Production Handbook 49 (19-60)
Volume to Push (2ft depth) | 3226.6667 | LCY/AC
Dozer Production Rate | 0.24793 | AC/hr
Dozer Pushing Production @ 300ft Push Distance | 250 | LCY/hr |  | *Cat Production Handbook 49 (19-60)
Dozer Grading
Dozer Grading Speed | 2.1 | mph
Blade Width (Semi U) | 12.9167 | ft |  | *Cat Production Handbook 49
Grading Pass Overlap | 2 | ft
Dozer Production Rate | 2.7788 | AC/hr
Dozer Ripping
Dozer Ripping Speed | 0.75 | mph
Rip Width | 8.0833 | ft |  | *Cat Production Handbook 49 (19-79)
Rip Length (per Acre) | 5388.866 | ft
Rip Time (per Acre) | 1.3608 | hr
Shank Depth | 3 | ft
Volume Ripped | 4840 | cy/AC
Dozer Ripping Production Rate | 0.73485 | AC/hr
D10T Contouring/Dozer Equipment Production Calculations |  |  |  | Dozer D10T
Dozer Material Moving
Dozer Pushing Production @ 100ft Push Distance | 1500 | LCY/hr |  | *Cat Production Handbook 49 (19-60)
Volume to Push (2ft depth) | 3226.6667 | LCY/AC
Dozer Production Rate | 0.46488 | AC/hr
Dozer Pushing Production @ 300ft Push Distance | 600 | LCY/hr |  | *Cat Production Handbook 49 (19-60)
Dozer Grading
Dozer Grading Speed | 2.5 | mph
Blade Width (Semi U) | 16.25 | ft |  | *Cat Production Handbook 49
Grading Pass Overlap | 2 | ft
Dozer Production Rate | 4.3182 | AC/hr
Dozer Ripping
Dozer Ripping Speed | 0.5 | mph
Rip Width | 9.5833 | ft |  | *Cat Production Handbook 49 (19-81)
Rip Length (per Acre) | 4545.3913 | ft
Rip Time (per Acre) | 1.7217 | hr
Shank Depth | 3 | ft
Volume Ripped | 4840 | cy/AC
Dozer Ripping Production Rate | 0.58081 | AC/hr
Alluvium Hauling Equipment Production Calculations
[15 empty] | Precip Plant Area + Precip RR |  | TSF Transition Zone | TSF Transition Zone | TSF Transition Zone | Non-suitable CZ Alluvium to S. Cont Pit RDS
|  | N-S Embankment | E-W Embankment | West Embankment | TSF - Alluvium | North Dump | East Dump | Access | Nalley Valley | S. Cont. Pit | Pittsmont | Leach Pads | Pit Benches | Roads | Misc. Disturbance | E East (MR25-001) | Excavator/740 Truck | Shovel/777 Truck | Excavator/740 Truck | to RDS
Haul Distance (Stockpile to Placement Area) | LF (to Central Zone) | 13200 | 14250 | 19535 | 13200 | 10000 | 13200 | 11000 | 3500 | 3500 | 2000 | 9500 | 8000 | 5000 | 5000 | 500 | 17400 | 17400 | 5000 | 5000
Hauler Cycle Time
Truck Loaded Speed | mph | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 20 | 20 | 12 | 20 | 12
Truck Unloaded Speed | mph | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20
Load Time (with Exchange) | min | 2.45 | 2.45 | 2.45 | 2.45 | 2.45 | 2.45 | 2.45 | 2.45 | 2.45 | 2.45 | 2.45 | 2.45 | 2.45 | 2.45 | 2.45 | 4.5 | 2.45 | 4.5 | 2.45
Haul Time (Loaded) | min | 12.5 | 13.4943 | 18.4991 | 12.5 | 9.4697 | 12.5 | 10.4167 | 3.3144 | 3.3144 | 1.8939 | 8.9962 | 7.5758 | 4.7348 | 4.7348 | 0.28409 | 9.8864 | 16.4773 | 2.8409 | 4.7348
Dump and Maneuver | min | 1.6 | 1.6 | 1.6 | 1.6 | 1.6 | 1.6 | 1.6 | 1.6 | 1.6 | 1.6 | 1.6 | 1.6 | 1.6 | 1.6 | 1.6 | 1.6 | 1.6 | 1.6 | 1.6
Return Time (Unloaded) | min | 7.5 | 8.0966 | 11.0994 | 7.5 | 5.6818 | 7.5 | 6.25 | 1.9886 | 1.9886 | 1.1364 | 5.3977 | 4.5455 | 2.8409 | 2.8409 | 0.28409 | 9.8864 | 9.8864 | 2.8409 | 2.8409
Total Cycle Time (Truck) | min | 24.05 | 25.6409 | 33.6485 | 24.05 | 19.2015 | 24.05 | 20.7167 | 9.353 | 9.353 | 7.0803 | 18.4439 | 16.1712 | 11.6258 | 11.6258 | 4.6182 | 25.8727 | 30.4136 | 11.7818 | 11.6258
Hauler Production
Hauler Capacity (Truck) | CY | 77 | 77 | 77 | 77 | 77 | 77 | 77 | 77 | 77 | 77 | 77 | 77 | 77 | 77 | 31 | 31 | 77 | 31 | 77
Total Hauler Production | CY/hr | 192.0998 | 180.1808 | 137.3019 | 192.0998 | 240.606 | 192.0998 | 223.0088 | 493.9576 | 493.9576 | 652.5144 | 250.4888 | 285.6929 | 397.3935 | 397.3935 | 402.7559 | 71.8904 | 151.9055 | 157.8704 | 397.3935
Loader Cycle Time
Loader Capacity | CY | 15.7 | 15.7 | 15.7 | 15.7 | 15.7 | 15.7 | 15.7 | 15.7 | 15.7 | 15.7 | 15.7 | 15.7 | 15.7 | 15.7 | 8 | 3.1 | 15.7 | 3.1 | 15.7
Loader Passes/Hauler |  | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 4 | 10 | 5 | 10 | 5
Loader Cycle Time | min | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7
Load Hauler Time | min | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 | 2.8 | 7 | 3.5 | 7 | 3.5
Number of Trucks Required (per Loader) | Trks | 7 | 8 | 10 | 7 | 6 | 7 | 6 | 3 | 3 | 3 | 6 | 5 | 4 | 4 | 2 | 4 | 9 | 2 | 4
Number of Trucks Assumed | Trks | 7 | 7 | 10 | 7 | 7 | 7 | 6 | 3 | 3 | 2 | 5 | 5 | 3 | 3 | 1 | 2 | 7 | 2 | 2
Total Production Rate
Hauling Production Rate | LCY/hr | 1344.6985 | 1261.2657 | 1373.0187 | 1344.6985 | 1684.2421 | 1344.6985 | 1338.0531 | 1481.8727 | 1481.8727 | 1305.0289 | 1252.4439 | 1428.4643 | 1192.1804 | 1192.1804 | 402.7559 | 143.7807 | 1063.3388 | 315.7407 | 794.7869
Hourly Fleet Rate (including operator) |  | 2475.59 | 2475.59 | 3226.34 | 3455.24 | 2904.23 | 2475.59 | 2225.34 | 1474.59 | 1474.59 | 1224.34 | 1975.09 | 1975.09 | 1474.59 | 1474.59 | 299.17 | 356.3 | 2475.59 | 356.3 | 1224.34
Loader/Shovel (6020B, 15.7CY capacity) | 723.84 | 723.84 | 723.84 | 723.84 | 723.84 | 723.84 | 723.84 | 723.84 | 723.84 | 723.84 | 723.84 | 723.84 | 723.84 | 723.84 | 723.84 |  |  | 723.84 |  | 723.84
Hauler (777D, 77CY capacity) | 250.25 | 1751.75 | 1751.75 | 2502.5 | 1751.75 | 1751.75 | 1751.75 | 1501.5 | 750.75 | 750.75 | 500.5 | 1251.25 | 1251.25 | 750.75 | 750.75 |  |  | 1751.75 |  | 500.5
Motor Grader (14H) - See Annual O&M Cost |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
Dozer (D8T) | 214.32 | 0 | 0 | 0 | 428.64 | 428.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
Water Truck - See Annual O&M Cost |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
Loader/Shovel (980) | 173.25 |  |  |  | 173.25 | [10 empty] | 173.25
Hauler (740) | 125.92 |  |  |  | 377.76 | [10 empty] | 125.92 | 125.92 |  | 125.92
Loader (365D) | 230.38 | [15 empty] | 230.38 |  | 230.38
[17 empty] | Removed D8 (added as separate step), added 740 haul |  | Removed D8 (added as separate step), added 740 haul
Soil Hauling Equipment Production Calculations
|  | West Embankment | TSF - Topsoil | RDS Pittsmont Rock Removal
Haul Distance (Stockpile to Placement Area) | LF | 7920 | 10560 | 1000
Hauler Cycle Time
Cat 740 Loaded Speed | mph | 20 | 20 | 20
Cat 740 Unloaded Speed | mph | 20 | 20 | 20
Load Time (with Exchange) | min | 2.45 | 2.45 | 2.45
Haul Time (Loaded) | min | 4.5 | 6 | 0.56818
Dump and Maneuver | min | 1.6 | 1.6 | 1.6
Return Time (Unloaded) | min | 4.5 | 6 | 0.56818
Total Cycle Time (Cat 740 Truck) | min | 13.05 | 16.05 | 5.1864
Hauler Production
Hauler Capacity (Cat 740 Truck) | CY | 31 | 31 | 23.25 | Assumes 75% by volume for rock instead of soil
Total Hauler Production | CY/hr | 142.5287 | 115.8879 | 268.9746
Loader Cycle Time
Loader Capacity (980) | CY | 8 | 8 | 8
Loader Passes/Hauler |  | 4 | 4 | 3
Loader Cycle Time | min | 0.6 | 0.6 | 0.6
Load Hauler Time | min | 2.4 | 2.4 | 1.8
Number of Trucks Required (per Loader) | Trks | 6 | 7 | 3
Number of Trucks Assumed | Trks | 3 | 3 | 3
Total Production Rate
Hauling Production Rate | LCY/hr | 427.5862 | 347.6636 | 806.9238
Hourly Fleet Rate (including operator) |  | 604.13 | 604.13 | 604.13
Loader/Shovel (980) | 173.25 | 173.25 | 173.25 | 173.25
Hauler (740) | 125.92 | 377.76 | 377.76 | 377.76
Motor Grader (14H) - See Annual O&M Cost |  | 0 | 0 | 0
Dozer (D8T) | 53.12 | 53.12 | 53.12 | 53.12
Water Truck - See Annual O&M Cost |  | 0 | 0 | 0
NOTES AND DETAILED CALCULATIONS:
Ripping- Select Disturbance Areas, Stockpile Footprints, Roads
Roads (post-1974) Length in miles | 6.6057 | Assume 20-100 ft width (avg 60)
Roads (post-1974) Length in feet | 34877.9121 | Rip rap channel needed
Embank Crest Roads (post-1974) Length in miles | 2.1992 | Assume 50 ft width
Embank Crest Roads (post-1974) Length in feet | 11611.7762 | Flat, rip rap channel not needed
RECONTOURING - REGRADING
Backfill and Shape TSF Beach Settlement:
RDS Regrading:
| Access | Nalley Valley | S. Cont. Pit | Pittsmont
Height of RDS (FT) | 80 | 175 | 125 | 100 | Estimated from topography in 2023 Rec Plan Map
Crest Length of RDS (FT) | 2000 | 2000 | 1300 | 8500 | Estimated from aerial imagery
Cut, fill, and rehandle volume per foot of crest (LCY/FT) | 92.48 | 442.5312 | 225.7812 | 144.5
Total cut, fill, and rehandle volume is (LCY) | 184960 | 885062.5 | 293515.625 | 1228250
Contour Interval | Bench Height | East Side Crest Length | West Side Crest Length | East Side Volume (cut & fill AOR to 3H:1V slope) | West Side Volume (cut & fill AOR to 2.7H:1V slope)
5780 | 20 | Regraded | 250 | 0 | 1445
5800 | 20 | Regraded | 400 | 0 | 2312
5820 | 20 | Regraded | 850 | 0 | 4913
5840 | 20 | 1200 | 1100 | 8064 | 6358
5860 | 20 | 1000 | 1400 | 6720 | 8092
5880 | 20 | 800 | 1600 | 5376 | 9248
5900 | 20 | 1800 | 1650 | 12096 | 9537
5920 | 20 | 1600 | 1300 | 10752 | 7514
5940 | 20 | 3000 | 1250 | 20160 | 7225
5960 | 20 | 3800 | 1200 | 25536 | 6936
5980 | 20 | 3800 | 4400 | 25536 | 25432
6000 | 20 | 3600 | 4400 | 24192 | 25432
6020 | 20 | 4800 | 4500 | 32256 | 26010
6040 | 20 | 5800 | 4600 | 38976 | 26588
6060 | 20 | 6000 | 4800 | 40320 | 27744
6080 | 20 | 5800 | 4600 | 38976 | 26588
6100 | 20 | 5600 | 4400 | 37632 | 25432
6120 | 20 | 2600 | 2000 | 17472 | 11560
6140 | 20 | 2600 | 2000 | 17472 | 11560
6160 | 20 | 2400 | 2000 | 16128 | 11560
6180 | 20 | 2200 | 1800 | 14784 | 10404
6200 | 20 | 2000 | 1800 | 13440 | 10404
6220 | 20 | 1900 | 1900 | 12768 | 10982
6240 | 20 | 1800 | 1800 | 12096 | 10404
6260 | 20 | 1700 | 1700 | 11424 | 9826
6280 | 20 | 1700 | 1700 | 11424 | 9826
6300 | 20 | 1750 | 1750 | 11760 | 10115
Total |  | 69250 | 61150 | 465360 | 353447
The total cut, fill, and rehandle volume (LCY) |  | 818807
TSF Embankments- Regrading
The grading calculations only apply to the slopes which occur within OP 00030A
See 2025 Site Plan Map for permit boundaries and the defined boundaries for each embankment limb
|  |  | Task 1 | Task 1 | Task 2 | Task 2 | Task 3 | Task 3
|  |  | N-S Embank D/S | N-S Embank U/S | E-W Embank D/S | E-W Embank U/S | West Embank D/S | West Embank U/S
Crest length (length of Slope Reduction) in Post-1974 Areas (FT) |  |  | 4800 | 4000 | 500 | 1000 | Resloping N/A | 6400
The cut, fill, and rehandle volume per foot of crest length from AOR(LCY/FT) |  |  | 439.726 | 36.125 | 9.0312 | 36.125 | - | 36.125 | (Ref Exhibit 3)
The total cut, fill, and rehandle volume is (LCY) |  |  | 2110684.7407 | 144500 | 4515.625 | 36125 | - | 231200
| Volume of Material (LCY) |  | 2110684.7407 | 144500 | 4515.625 | 36125 |  | 231200
Rock Removal and Relocation
"Pittsmont hauling adjusted to account for removing 204,000 bcyds of rock from the dump (to allow Central Zone removal and adjacent road)"
Costs to include- mine, load, haul, dump | 204000 | BCY
| 265200 | LCY | MR estimates 30% swell factor
Haul & Spread Alluvium
Slope | Alluvium without soil (inches) | Alluvium, with 6" topsoil (inches)
< 5% | 28 | 22
≥ 5 % | 20 | 14
ROADS AND MISC (POST-1974 AREAS)
| Roads | Misc | Cont Pit Benches | Precip Plant Area | Misc. Precip Plant RR | SUM ALL
Areas to receive alluvium cover (AC) | 31.4903 | 175.0165 | 210.485 | 0.78436 | 0.33219 | 418.1084
Thickness of alluvium cover (IN) | 28 | 28 | 28 | 28 | 28
Volume of alluvium (LCY) | 118543.5613 | 658840.0017 | 792359.044 | 2952.6745 | 1250.5144
Feature- total volume of alluvium (LCY) | 118543.5613 | 658840.0017 | 792359.044 | 2952.6745 | 1250.5144
Total Alluvium Volume (LCY) | 118543.5613 | 658840.0017 | 792359.044 | 2952.6745 | 1250.5144 | 1573945.7958
Density of alluvium (LBS/LCY) | 3300 | 3300 | 3300 | 3300 | 3300
Weight of alluvium (TONS) | 195596.8762 | 1087086.0027 | 1307392.4225 | 4871.9128 | 2063.3488 | 2590075.3014
Haul distance at 4% grade (FT) | 5000 | 5000 | 8000 | 1800 | 4000
2023 REC PLAN ACRES: | Under Misc? Unclear | 374 | 148 |  |  |  | Does not separate pre-1974 areas
2023 REC PLAN VOLUME: |  | 1004219 | 557138 |  |  |  | Does not separate pre-1974 areas
RDS (POST-1974 AREAS) | [5 empty] | slope corrected |  | slope corrected |  | slope corrected |  | slope corrected |  | slope corrected
| Leach Pad Slopes | Leach Pad Tops | RDS North East- 2022 D East Expansion | RDS North East- 2025 E East Drilling | Access Top* | Access Slope | Nalley Valley Top | Nalley Valley Slope | S Cont. Pit Top | S Cont. Pit Slope | Pittsmont Top | Pittsmont Slope | East Dump Tops | East Dump Slopes | RDS North | RDS North Crest | SUM ALL
Areas to receive alluvium cover (AC) | 0 | 7.5139 | Combined into other features in new map |  | 7 | 7.6697 | NA- Under Leach Pad | 34.4297 | 18.1201 | 43.3053 | 26.5904 | 63.7463 | 29.3583 | 14.6371 | 11.9453 | 12.31 | 264.3162
Thickness of alluvium cover (IN) | All pre-1974 area | 28 |  |  | 28 | 20 | 28 | 20 | 28 | 20 | 28 | 20 | 28 | 20 | 28 | 28
Volume of alluvium (LCY) |  | 28285.6999 |  |  | 26351.1111 | 20622.907 |  | 92577.7495 | 68212.2511 | 116443.2563 | 100098.0777 | 171406.7238 | 110517.5302 | 39357.586 | 44967.4137 | 46340.354
Feature- total volume of alluvium (LCY) |  | 28285.6999 |  |  | 46974.0182 | Added to left | 92577.7495 | Added to left | 184655.5074 | Added to left | 271504.8015 | Added to left | 149875.1163 | Added to left | 91307.7677 | Added to left
Total Alluvium Volume (LCY) |  | 28285.6999 |  |  | 46974.0182 |  | 92577.7495 |  | 184655.5074 |  | 271504.8015 |  | 149875.1163 |  | 91307.7677 |  | 865180.6605
Density of alluvium (LBS/LCY) |  | 3300 |  |  | 3300 |  | 3300 |  | 3300 |  | 3300 |  | 3300 |  | 3300
Weight of alluvium (TONS) |  | 46671.4049 |  |  | 77507.13 |  | 152753.2868 |  | 304681.5871 |  | 447982.9224 |  | 247293.9419 |  | 150657.8167 |  | 1427548.0897
Haul distance at 4% grade (FT) |  | 9500 |  |  | 11000 |  | 3500 |  | 3500 |  | 2000 |  | 13200 |  | 13200
2023 REC PLAN ACRES: |  |  |  |  | *Not split up on map, like others: 7.0 acres measured on dump top, remaining slope (corrected) is 12.5 ac | [8 empty] | ALL RDS+ LEACH |  |  | 869 | Does not separate pre-1974 acres/volumes
2023 REC PLAN VOLUME: | [16 empty] | 2641107 | Does not separate pre-1974 acres/volumes
TSF (POST-1974 AREAS) | [6 empty] | Only material placement- no regrade on West Embank downstream
| N-S Embank | N-S Embank | N-S Embank | E-W Embank | E-W Embank | E-W Embank | West Embank | West Embank | West Embank | West Embank | West Embank
Variable TSF Slopes: | Acreage | Alluv Thick (Inches) | Alluv Volume (LCY) | Acreage | Alluv Thick (Inches) | Alluv Volume (LCY) | Acreage | Soil Thick (Inches) | Soil Volume (LCY) | Alluv Thick (Inches) | Alluv Volume (LCY)
2H:1V Slope Area (Corrected for slope) | 0 | - | - | 0 | - | - | 0 | - | - | - | -
2.5H:1V Slope Area (Corrected for slope) | 0 | - | - | 0 | - | - | 6.1445 | - | - | 20 | 16521.7899
2.7H:1V Slope Downstream Area (Corrected for slope) | 51.3578 | 20 | 138095.4325 | 1.7446 | 20 | 4691.1652 | 0.57738 | - | - | 20 | 1552.5155
2.7H:1V Slope Upstream Area (Corrected for slope) | 7.9254 | 20 | 21310.5256 | 0.80739 | 20 | 2170.9934 | 10.6948 | - | - | 20 | 28757.0691
3H:1V Slope Area (Corrected for slope) | 0 | - | - | 0 | - | - | 5.997 | 6 | 4837.5742 | 14 | 11287.6732 | WAS 27.3 AC PRIOR TO RELEASE OF 21.7 AC
Crest Area (Not corrected for slope) | 42.6213 | 28 | 160445.701 | 5.8198 | 28 | 21908.3863 | 67.3777 | - | - | 28 | 253639.7247
TOTAL | 101.9046 |  | 319851.6591 | 8.3719 |  | 28770.545 | 90.7914 |  | 4837.5742 |  | 311758.7724
23.1 acres of this will get 6 inch soil
| TSF Beach at Closure | TSF Beach Transition Zone | N-S Embank | E-W Embank | West Embank | SUM ALL
Total Beach Area (post-1974) | 735.5502
Areas to receive alluvium cover (AC) - 28 Inches | 370.0502
Areas to receive alluvium cover (AC) - 22 Inches** | 365.5 | 5 year increments | 101.9046 | 8.3719 | 90.7914 | 936.6179
Areas to receive soil cover (AC) - 6 Inches** | 365.5 | see below |  |  | 5.997
Thickness of alluvium cover (IN) | 28
Thickness of alluvium cover (IN) | 22
Feature- total volume of alluvium (LCY) | 2474101.055 |  | 319851.6591 | 28770.545 | 311758.7724
Total Alluvium Volume (LCY) | 2474101.055 |  | 319851.6591 | 28770.545 | 311758.7724 | 3134482.0315
Density of alluvium (LBS/LCY) | 3300 |  | 3300 | 3300 | 3300
Weight of alluvium (TONS) | 4082266.7408 |  | 527755.2375 | 47471.3992 | 514401.9745 | 5171895.352
Haul distance at 4% grade (FT) | 17000 |  | 13200 | 14250 | 19535
Thickness of soil cover (IN) | 6 |  |  |  | 6
Feature- total volume of soil (LCY) | 294836.6667 |  |  |  | 4837.5742
Density of soil (LBS/LCY) | 2800 |  |  |  | 2800
Weight of soil (TONS) | 412771.3333 |  |  |  | 6772.6039
Haul distance at 4% grade (FT) for West Soil | 8500 |  |  |  | 7920
| **Assume half of the topsoil area (731 ac / 2 = 366 ac) is split in OP 00030 (pre-1974) & 30A (post-1974). |  |  |  | 7920 ft from soil stockpiles to West Embank
2023 REC PLAN ACRES: | 1217 | 398 |  |  |  | 505 |  | Does not separate pre-1974 acres/volumes
2023 REC PLAN VOLUME: | 3991656 | 1070178 |  |  |  | 727733 |  | Does not separate pre-1974 acres/volumes
Soil | 608662 |  |  |  |  | All YDTI (NON BEACH)
| BONDED | REPORTED
TOTAL ALLUVIUM NEEDED (LCY) | 6250166.7229 | 10883030 | 2023 REC PLAN, INCLUDES PRE-1974 AREAS
TOTAL SOIL NEEDED (LCY) | 299674.2409 | 608662 | 2023 REC PLAN, INCLUDES PRE-1974 AREAS
TOTAL AREA COVERED (AC) | 1870.6551 | 3511 | 2023 REC PLAN, INCLUDES PRE-1974 AREAS
Haul & Spread Alluvium Per 5 Year Period- TRANSITION ZONE
Area to be incrementally reclaimed (Post-1974) |  | Areas will be reclaimed over 28 years (33 total minus Years 1-5) |  |  | Divide by 28 Years
YDTI North Transition Zone (AC) | 50.7923 | Reseeding only |  |  | 1.814 | AC
YDTI Tailings Transition Zone (AC) | 251.6126 | Potential grading on small areas (10%)- soil and reseeding |  |  | 8.9862 | AC
Timeframe | Years | Total Reclaimed Beach Area | Reclaimable Tailings Transition Zone | Reclaimable North Trans Zone
Closure | 0-5 | 735.5502 | 0 | 0
| 5-10 | 780.481 | 44.9308 | 9.07
| 10-15 | 825.4118 | 44.9308 | 9.07
| 15-20 | 870.3426 | 44.9308 | 9.07
| 20-25 | 915.2734 | 44.9308 | 9.07
| 25-30 | 960.2042 | 44.9308 | 9.07
Equilibrium | 30-33 | 987.1627 | 26.9585 | 5.442
|  | Total | 251.6126 | 50.7923
Post Closure Acreage
Area of Transition zone to get alluvium during POST CLOSURE(AC) |  | 251.6126 | Every 5 years for 33 years
Thickness of alluvium cover (IN) |  | 20
Volume of alluvium (LCY) |  | 676558.2352
Total Alluvium Volume (LCY) |  | 676558.2352
Density of alluvium (LBS/LCY) |  | 3300
Weight of alluvium (TONS) |  | 1116321.088
Haul distance at 4% grade (FT) |  | 17400 | (Central Zone Alluvium)
COSTS FOR PLACING MATERIAL ON TRANSITION FOR NEXT 30 YEARS- SEE LONG-TERM TAB
Alluvium Testing and Separation
Total Alluvium Volume Needed (LCY) | 6250166.7229
Total Alluvium Volume in CZABA (LCY) | 23053000
Unknown- assume that 25% additional material is excavated and tested, but found to be unsuitable
Total Alluvium Volume to be Tested (LCY) | 7812708.4036
Total Alluvium Unsuitable- Haul to RDS (LCY) | 1562541.6807
Updated from Energy Labs- 9/3/2025
Analyses |  | Sample Frequency (per LCY) | Total Number of Samples | Cost per Parameter | Cost for Samples
Paste pH |  | 2500 | 3125.0834 | 22 | 68751.834
Coarse Fragments |  | 10000 | 781.2708 | 36 | 28125.7503
Copper |  | 10000 | 781.2708 | 180 | 140628.7513
Total Metals ICP Scan |  | 30000 | 260.4236 | 180 | 46876.2504
Acid Base Accounting (AGP + ANP for lime supplement) |  | 2500 | 3125.0834 | 38 | 118753.1677
Shipping ($10/each) |  |  |  |  | 80731.3202
Sample disposal fee ($3/each) |  |  |  |  | 24219.3961
TOTALS |  |  | 8073.132 |  | 508086.4699
Estimate for Full Time Soil Scientist
Soil Scientist Hourly Rate ($/HR) w/ truck |  | 121.45
Number of Hours (HR) |  | 248.054 | ASSUMED TO BE 25% OF JOB HOURS
Total Cost of Soils Scientist |  | 30126.1523
Total Alluvium Testing Costs |  |  |  | 538212.6222
Respread Soil Monitoring
Field Work for Soil Monitoring | Rate | Quantity | Cost
Project Manager | 230.55 | 40 | 9222
Staff Scientist/Sr. Field Tech | 186.79 | 40 | 7471.6
Field Technician | 95.79 | 480 | 45979.2 | Assume 3 months (12 weeks) total for sampling
Admin Support | 82.66 | 40 | 3306.4
Supplies | 1000 | 1 | 1000
Subtotal Per Event |  |  | 66979.2
Total Field Work Costs ($/YEAR) |  |  | 66979.2
Data Compilation- Report Preparation | Rate | Quantity | Cost
Project Manager | 230.55 | 8 | 1844.4
Staff Scientist/Sr. Field Tech | 186.79 | 40 | 7471.6
Field Technician | 95.79 | 40 | 3831.6
Admin Support | 82.66 | 16 | 1322.56
Map/GIS/Drafting | 0 | 16 | 0
Total Reporting Costs ($/YEAR) |  |  | 14470.16
FROM TABLE RP-10-3
ACRES PER SAMPLE
| Alluvium |  |  |  | Topsoil
| Central Zone |  | Stockpile | Continental Pit | Stockpile | Direct Haul
Parameter | Known Good Quality | Lesser Quality or Unknown
pH | 2 | 1 | 1 | 1
Organic Matter | 2 | 1 | 1 | 1 | 1 | 2
Cu, Zn | 6 | 3 | 3 | 3
Total metals | 20 | 10 | 10 | 10
ABA | 20 | 10 | 10 | 10
N, P, K | 2 | 1 | 1 | 1 | 1 | 2
Coarse Frag Content | 2 | 1 | 1 | 1 | 1 | 2
Texture | 2 | 1 | 1 | 1 | 1 | 2
Total sulfur | 2 | 1 | 1 | 1
Areas With Upper Topsoil Layer (AC) | 371.497
Areas With Upper Alluvium Layer (AC) | 1499.1581 | Total alluvium area minus the area where soil will be on top (tested above)
Assume 50% of respread material is known good quality, 50% is unknown quality or source
NUMBER OF SAMPLES
| Alluvium |  |  |  | Topsoil
| Central Zone |  | Stockpile | Continental Pit | Stockpile | Direct Haul |  | Updated from Energy Labs- 9/3/2025
Parameter | Known Good Quality | Lesser Quality or Unknown |  |  |  |  | Total Number of Samples | Cost per Parameter | Cost for Samples
pH | 374.7895 | 749.579 | Included in total Alluvium Area |  |  |  | 1124.3686 | 22 | 24736.1083
Organic Matter | 374.7895 | 749.579 |  |  | 185.7485 | 92.8742 | 1402.9913 | 25 | 35074.7826
Cu, Zn | 124.9298 | 249.8597 |  |  |  |  | 374.7895 | 180 | 67462.1135
Total metals | 37.479 | 74.9579 |  |  |  |  | 112.4369 | 180 | 20238.6341
ABA | 37.479 | 74.9579 |  |  |  |  | 112.4369 | 38 | 4272.6005
N, P, K | 374.7895 | 749.579 |  |  | 185.7485 | 92.8742 | 1402.9913 | 63 | 88388.4521
Coarse Frag Content | 374.7895 | 749.579 |  |  | 185.7485 | 92.8742 | 1402.9913 | 36 | 50507.6869
Texture | 374.7895 | 749.579 |  |  | 185.7485 | 92.8742 | 1402.9913 | 49 | 68746.5738
Total sulfur | 374.7895 | 749.579 |  |  |  |  | 1124.3686 | 45 | 50596.5851
Shipping ($10/each) | [8 empty] | 84603.6556
Sample disposal fee ($3/each) | [8 empty] | 25381.0967
[6 empty] | TOTALS | 8460.3656 |  | 520008.2892
RESPREAD SOIL MONITORING- TOTAL COSTS |  |  | 601457.6492
Hillcrest Soil Hot Spots
Area of lower Hillcrest Dump (ft2) | 784068 | Measured from map:
Area of lower Hillcrest Dump (AC) | 17.9997
Area of Hillcrest Hot Spots (AC) | 3.5999 | Assume 20%- Visual estimate from map, sampled hot spots are circled in red
Average lime application rate (ton/AC) | 16
Lime applied (ton) | 57.5991
Unit cost for hydrated lime ($/ton)- delivered | 140 | Updated cost from MR on 11/30/2025
Cost for hydrated lime for hot spots | 8063.8766
Construct Surface Water Collection Ditches + Rip Rap Protection
Improve Upper Clearwater Ditch
Assumptions: The tailings beach will gradually slope away from the embankment to the north at a typical slope of one percent. Some topographic diversity will be created by final spigot placement. While no final grading is anticipated, it will be necessary to backfill and shape settlement areas before soil is placed. DEQ estimates 10% of the tailings beach will required extra shaping or backfill - this will also continue for segments of the Transition Zone into the future. To reshape the settlement area a low ground pressure Cat D6T dozer would be used. The Cat D6T would chisel off the sides, push tailings or fill into the settlement void.
See Description Tab for additional details. Assumptions/Observations:
Roads- Road width may vary from 20-100 feet. Without further details about road segments (length and area) that would be retained versus the road areas that would be reclaimed-- it is assumed that the road acreage (post-1974 area) will be reduced by 50% through reclamation. This can also be visualized as reducing the existing road widths by half (by ~10-50 ft). Like other misc. disturbance acres, it is assumed that half of the reclaimed road acreage will need to be corrected for slope area. TSF Embankment Crests-- All crest elevations = 6,450 ft
- N-S Embankment: 6,500 feet long
- E-W Embankment: 5,500 feet long
- West Embankment: 6,800 feet long
The crest on each embankment limb would be ripped prior to soil placement. An access road (assume 50 ft wide) along the top of each crest will remain for pos-closure access and monitoring.
2023 Reclamation Plan Citations: 3.1 POST-CLOSURE FINAL GRADING AND TOPOGRAPHY
As part of final reclamation, runoff swales and/or ditches will be constructed along reclaimed slopes as needed for runoff and erosion control (ARM 17.24.115(d)). Initial design concepts include grass-lined swales in the upper reaches of drainages, transitioning to riprap-lined ditches in the lower reaches where flow velocities warrant (Figure RP-7-1; Exhibit RP-2). All drainage structures, including drainage ditches A, B and C, and the upgraded Clearwater Ditch would be designed to safely convey runoff generated from the 100 year-24 hour storm event, including riprapping where flow velocities warrant. Stormwater settling basins would be placed along major drainageways to slow flow velocities and allow for settling of entrained sediment. All stormwater drainage structures and provisions would be detailed in a post-closure erosion control plan. As currently planned, all stormwater runoff would report to the south mine boundary and Clearwater Ditch for direct discharge to Silver Bow Creek, if water quality allows.
Assumptions/Observations: After the slopes are recontoured to the final configuration, a survey party will locate the surface water ditches. A survey party fee of 15% is also included. To break up the long reclaimed slopes, benches or drainage swales will be cut every 100 feet (vertical). A D8T dozer can cut, shape, and finish blading 100 linear feet of ditch per hour. To construct the ditches along the slope, a dozer would walk back out to the slopes, and using the blade to push the muck downslope creating a berm with a "U" bottom. - For the N-S Embankment, approximately 19,500 feet (6,500 X 3) of ditches would need to be constructed (assuming ~350 ft high slope). - For the E-W Embankment, approximately 16,500 feet (5,500 X 3)of ditches would need to be constructed (assuming ~360 ft high slope). - The downstream West Embankment toes into native ground, therefore no surface water ditches will be necessary. - Other channel lengths have been measured in previous bond reviews. The 2023 Reclamation Plan includes additional primary ditches (Ditch A, B, C, and Clearwater), some portions are contained in pre-1974 acres (already bonded at $500/acre).
Initial designs indicate the typical ditches will be trapezoid shape, approximately 20 feet wide, so a 20 ton articulating truck and hydraulic excavator can place rip rap. Along roads, rip rap placement would occur in collector ditches adjacent to to the road, with the ditches being trapezoid shape and average 10 feet wide at the top. Additional settling basins would be designed in the final plan, but assume 0.1 acre for each feature.
The rip rap will be brought in from offsite, assuming that all material at the mine is potentially acid generating. A portable screening and crushing plant may be necessary to manufacture bedding material. Large size rip rap can be taken from onsite stockpiles. In the absence of more detailed designs, assume that rip rap placement is needed along 30% of total ditches and 50% of remaining roads. The estimated cost for completing a rip rap lined ditch is $60 per foot. Engineering and survey fee of 15% is also included.
Assumptions/Observations: The Upper Clearwater Ditch is an eroding, unlined channel along the toe of the East Dump and the embankment of Interstate 15. The length of the eroding channel is 840 feet at which point the water enters an existing 24 inch culvert. In October 2010, Water & Environmental Techologies, PC (WET) completed a proposed underground drainage infrastructure design for the Upper Clearwater Ditch. The proposed design includes capturing all existing surface flows and directing them into a buried 24 inch HDPE culvert for the entire length of the eroding channel. The design includes the addition of five manholes and five sections of 24 inch HDPE Pipe (840 feet of pipe total) The design also includes, slope reinforement mats, and rip rap lined channels, and a trash grate to minimize clogging, and maintenance.
Side slopes of dumps require resloping and regrading. The existing dump slope angle are approximately 40 degrees. The reclamation of dumps will include resloping the waste rock to a 2.7H:1V slope, covering with growth media, and establishing vegetation.
Assumptions/Observations: The downstream face of N-S Embankment will not be covered by the North RDS in 2025, so the surface must be resloped prior to capping and revegetation. The downstream face of E-W Embankment must be resloped prior to capping and revegetation. The downstream West Embankment slopes were constructed to either 3H:1V or 2.5H:1V, therefore no resloping is required. The tailings beach would not reach its full extent (under Amendment 010) in year 2025. The upstream face (between beach surface and dam crest) will need to be considered for each embankment, an elevation difference of 50 feet is assumed. The access road (50 ft wide) along the top of each crest will remain for post closure monitoring. The N-S Embankment is approximately 6,500 feet long, in 2025 it will be constructed to the 6,450 ft elevation. The embankment is constructed using downstream construction method with heavy rock fill. The N-S Embankment is constructed in 50 to 100-ft lifts of waste rock at the angle of repose. As the embankment height increases to the 6450 foot crest elevation, a new ramp will be constructed, aiding in North RDS construction. The E-W Embankment is approximately 5,500 feet long, in 2025 it will be constructed to the 6,450 ft elevation. The West Embankment is approximately 6,800 feet long, in 2025 it will be constructed to the 6,450 ft elevation. The reclamation plan calls for downstream embankment slope to be reduced to either a 2H:1V or 2.7H:1V slope and capping with 20 inches of amended alluvium. The section of the embankment adjacent to the Precipitation Plant will be resloped to 2H:1V and capped with 20 inches of alluvium. The section very close to the Precipitation Plant will be covered with course rockfill (riprap) that is nonacid generating sourced from off-site. There are no slopes within OP 00030A that need to be reduced to 2H:1V .
Assumptions: To fix the hot spots, the 2023 Rec Plan states "Lime will be applied at appropriate rates to raise the pH to about 6.0. Lime would be incorporated to a depth of about 18 inches."
The reclaimed hot spot is then seeded and weed sprayed for 5-years afterwards.
10.3 COVERSOIL TESTING
The majority of coversoil to be used for reclamation will be mined in the CZABA. This material has recently been evaluated for suitability (see Section 4.2.1). This information on quality and location within the Central Zone will reduce the need for testing after alluvium is spread. Additionally, field pH testing will be conducted prior to spreading. In-place characterization and field pH analyses will reduce the probability that unsuitable material or material needing lime application will be spread.
Given the variability of alluvium within the Central Zone, however, some testing of respread alluvium may be conducted to determine if amendments might be necessary. Table RP-10-3 presents guidelines for sampling respread alluvium. MR may increase or decrease sampling intensity depending on uniformity or diversity of parameters in respread alluvium.
Respread topsoil sampling (Table RP-10-3) would focus on whether fertilizer may be necessary. TESTING ASSUMPTIONS:
Even with information from the Rec Plan, during bankruptcy DEQ would need to characterize the CZABA materials upon excavation to determine suitability for reclamation cover and segregate the materials accordingly.
Costs are needed to excavate, test, haul good material for placement and poor material to disposal (S. Cont. Pit RDS), then place good material for reclamation cover. Testing would also indicate whether soil amendments would be needed. The 2023 Reclamation Plan clarifies the soil suitability criteria for initial testing, but a frequency is not specified. The following assumptions for testing frequency is based on the reclamation program established for the Woodville Dump (2002). . DEQ assumes the following sampling and analysis schedule would be applicable to initial soil testing. DEQ assumes a qualified soils scientist (with pickup truck) would be involved with the alluvium salvage operation full time for sample collection and preparation, QA/QC, and reporting/record keeping. DEQ assumes that a third party laboratory would process and analyze soil samples.
8.2.4 Pittsmont RDS
The Pittsmont RDS is just east of the Berkeley Pit and overlies the western portion of the Central Zone. It consists of a northern disposal area and a southern disposal area bisected by a haul road to the primary crusher.
Since 2018, the Montana Natural Resource Damage Program (NRDP) has delivered Parrot Tailings mine waste and associated water from dewatering activities removed from the historic Parrot Smelter to MR. The tailings have been hauled to a location on the east side of the Pittsmont RDS. A portion of the east side of the Pittsmont RDS would be removed and regraded in conjunction with development of the CZABA. 2.3.2.2 Continental Pit and Central Zone Alluvium Borrow Area
The Continental Pit and Central Zone Alluvium Borrow Area (CZABA) highwalls could create potential nesting sites for birds that typically nest in cliff habitat, including species that could construct stick nests on the rock face or use ledges, fractures/fissures and cavities in the rock. Bats may also roost in fractures/fissures in the highwall face. The Continental Pit highwall may be near the upper elevational nesting/roosting limits of some bird and bat species, and its elevation and proximity to Butte, I-15/I-90 and other comparatively constant, intense human activity may limit its attractiveness to some species or individuals.
The highwall created in the CZABA associated with removal of a small portion of the Pittsmont RDS would be graded during reclamation to 2.7H:1V or less, and wildlife habitat can be expected to be similar to other RDSs.
Assumptions:
DEQ cannot directly use the coversoil balance data provided in the 2023 Rec Plan, as Table RP-4-7 provides the acreages, alluvium volumes, and soil volumes that would be involved for the entire facility. There is no distinction made for pre-1974 disturbance acres versus post-1974 disturbance, so the costs cannot be derived directly from the material volume totals. There is no distinction provided for individual polygons within larger features (e.g. the TSF features are grouped by slope and not embankment limb; all RDS are combined; features contained within Misc. footprint are not clear), to correlate with prior acreage tracking (2023 Op Plan; Table OP-2-1) or bonding assumptions. Acreage and volume tracking methods from the 2020 bond are carried forward here.
8.1.3 Post-Closure Pond and Transition Zone The beach area slope will be flatter than 5 percent. Coversoil will be spread on the beach to a depth of 28 inches of alluvium or a combination of 22 inches of alluvium and 6 inches of topsoil (see Table RP-4-7). The transition zone is projected to be a 5 percent slope (see Exhibit RP-2) and would be covered with 20 inches of coversoil. Should portions of the transition zone be less than 5 percent slope, coversoil depth would be increased to 28 inches. As water level drops and the transition zone dries, coversoil would be placed in 5 year increments. A 6-inch cover of rock, leached cap, or similar material would be placed as necessary for dust control concurrently with beach exposure. Coversoil material may be stockpiled on the beach area in advance to minimize haul distance post-closure. Coversoil would not be applied to the remnant pond. Assumptions: Post closure period assumes that the initial beach has been capped within the first five years. As the pond recedes over the next 30 years, the remaining tailings beach surface (transition zone) and the exposed north short transition zone can be reclaimed. The strips of transition zone (approx. 800 ft wide) would then incrementally become future "Reclaimed Beach." Reclamation of the incremental exposed beach is similar to the initial beach acres but with contractor using smaller equipment Assuming a local contractor wins the bid, and has available a Cat 345 Hydraulic Excavator and 2-Cat 740 articulating trucks to mine, load, and haul the alluvium The capping material would be mined in the Central Zone all at once in the first 5 years of closure, then hauled into a stockpile on the TSF, near the transition zone. This material would be tested all at once as well, rather then testing and hauling material from the Central Zone every 5 years. Spreading the alluvium is accomplished with a Cat 8T - assume the operating hours equal to the truck hours hauling the alluvium. Initial haul must be considered, even if stockpiles are created nearby for future use. The exposed north transition zone would not receive alluvium (excluded in this task), but the area will be seeded.
East Dump Reclamation would include:
Resloping the east side (along the Clearwater Ditch) and south side (near Hillcrest Dump) to a 3H:1V slope.
Reslope the west side (along the Continental Pit) to a 2.7H:1V slope.
Blend the north end to the North East Dump reclamation and southwest end to the Hillcrest Dump reclamation.
Reslope the top of the dump to keep the water from ponding by providing drainage swales.
The existing dump slope angle are at angle of repose, approximately 40 degrees.
The East Dump northern segment final top elevation is 6,300 feet.
The East Dump southern segment final top elevation is 6100 feet. With respect to the dump-slope bulldozer work:
2023 Reclamation Plan:
4.2.1 ALLUVIUM
Characteristics of the alluvium deposit were identified using laboratory data from 846 composite samples taken at 10-foot intervals. The average texture ranges from sandy clay loam to loamy sand, with a mean coarse fragment content of 25 percent. The mean paste pH is 6.52 standard units (s.u.). Total sulfur averages 0.29 percent with a median value of 0.23 percent.
Preliminary calculations for Uncorrected Lime Rate (ULR)were modeled using conservative parameters and expressed as tons of CaCO3 per 1000 tons of soil (t/kt). Projected ULR rates use the Acid Base Account (ABA), balancing Acid Neutralization Potential (ANP) with Acid Generation Potential (AGP) in addition to the active acidity defined by the Shoemaker-McLean-Pratt (SMP) buffer. The projected ULR for the entirety of the alluvium resource averages about 7.5 t/kt ranging from 0 (no lime necessary) to 114.5 t/kg. The ULR for 18 inches of alluvium depth ranges from 0 tons/acre (t/ac) to 240 t/ac, averaging about 16 t/ac.
5.1 LIME
"If monitoring identifies any areas where pH is below 5.5 in respread coversoil, lime will be applied at appropriate rates to raise the pH to about 6.0. Lime would be incorporated to a depth of about 18 inches."
Assumptions:
Without specific information about the total area of Hillcrest hot spots that need lime amendment/repair, a portion of the Hillcrest surface area will be assumed for treatment.
Without specific information about the ULR for the Hillcrest hot spots, the average lime rate of 16t/ac will be assumed for amendment.
Sampling Guidelines for Respread Coversoil- from Table RP-10-3 in 2023 Reclamation Plan DEQ does not have an in-house laboratory and assumes that a 3rd party contractor and laboratory would be needed for sampling and analysis
The Reclamation Plan also includes monitoring for vegetation and potential repairs (soil placement or amendment) or reseeding. The uncertainty with this scenario is assumed to be included in the contingency alluvium volume costs and other total bond contingency.

## 3-Revegetation
Montana Resources, LLC
Operating Permit #00030
Final Comprehensive 5-Year Bond Review
2026-05-04
Task 3- Revegetation
CORRECTED ACREAGES ARE BELOW ON THIS TAB
Type and Location | Quantity |  | Revegetation Cost |  | Other Cost |  | Total Cost |  | Source, Assumptions, Adjustments, etc
REVEGETATION - YEARS 1 - 5
SEEDING & WEED CONTROL
TSF: N-S Embankment- Alluvium Area | 101.9046 | AC | 1500 | /AC | 0 | /AC | 152856.835 |  | Excludes crest road, embankment road, former riprap area
TSF: E-W Embankment- Alluvium Area | 8.3719 | AC | 1500 | /AC | 0 | /AC | 12557.7926 |  | Excludes crest road, embankment road, former riprap area
TSF: West Embankment- Alluvium/soil Area | 90.7914 | AC | 1500 | /AC | 0 | /AC | 136187.0259
TSF: West Embankment- RELEASED | 23.1539 | AC | 1500 | /AC | 0 | /AC | 34730.85 |  | Other tasks/costs released, but no release for revegetation
TSF: Beach at Closure- Total Area | 735.5502 | AC | 1500 | /AC | 0 | /AC | 1103325.2433
TSF- Tailings Transition Zone (per future 5-year increment) | 44.9308 | AC/5-yr | 1500 | /AC | 0 | /AC |  | 67396.2233 | Cost for later phases (Years 6-33). Total area to be split into equal 5-year increments (acreage to left here), see Long Term tab
TSF- North Transition Zone (per future 5-year increment) | 9.07 | AC/5-yr | 1500 | /AC | 0 | /AC |  | 13605.0734 | Cost for later phases (Years 6-33). Total area to be split into equal 5-year increments (acreage to left here), see Long Term tab
RDS Access | 7.6697 | AC | 1500 | /AC | 0 | /AC | 11504.5143
RDS Access Crest | 7 | AC | 1500 | /AC | 0 | /AC | 10500
RDS East | 14.6371 | AC | 1500 | /AC | 0 | /AC | 21955.6782
RDS East Crest | 29.3583 | AC | 1500 | /AC | 0 | /AC | 44037.3866
RDS East - RELEASED | 91.8216 | AC | 1500 | /AC | 0 | /AC | 137732.4216
RDS Great Northern | Within Pre-1974 area ($500/acre) | [5 empty] | 0 |  | Accounted in other acreage tracking
RDS Hillcrest - RELEASED | 50.7016 | AC | 1500 | /AC | 0 | /AC | 76052.4376 |  | Other tasks/costs previously released, not for revegetation
RDS HSB | Within Pre-1974 area ($500/acre) | [5 empty] | 0 |  | Accounted in other acreage tracking
RDS Nalley Valley | 34.4297 | AC | 1500 | /AC | 0 | /AC | 51644.6124
RDS North | 11.9453 | AC | 1500 | /AC | 0 | /AC | 17917.9482
RDS North Crest | 12.31 | AC | 1500 | /AC | 0 | /AC | 18465.0171 |  | Not depicted in prior map
RDS North East - RELEASED | 19.9313 | AC | 1500 | /AC | 0 | /AC | 29897.0154 |  | Other tasks/costs previously released, not for revegetation
RDS North East- 2022 D East Expansion |  | AC | 1500 | /AC | 0 | /AC | 0 |  | Combined into other features in new map
RDS North East- 2025 E East Drilling |  | AC | 1500 | /AC | 0 | /AC | 0 |  | Combined into other features in new map
RDS Pittsmont | 63.7463 | AC | 1500 | /AC | 0 | /AC | 95619.4534 |  | Includes footprint of RDS removal for CZABA?
RDS Pittsmont Crest | 26.5904 | AC | 1500 | /AC | 0 | /AC | 39885.5977
RDS South Continental Pit | 43.3053 | AC | 1500 | /AC | 0 | /AC | 64958.0149
RDS South Continental Pit Crest | 18.1201 | AC | 1500 | /AC | 0 | /AC | 27180.2063
RDS Woodville - RELEASED | 0.63689 | AC | 1500 | /AC | 0 | /AC | 955.3288 |  | Other tasks/costs previously released, not for revegetation
Leach Pads- Crest | 7.5139 | AC | 1500 | /AC | 0 | /AC | 11270.8663
Continental Pit- Accessible Benches | 210.485 | AC | 1500 | /AC | 0 | /AC | 315727.4821
Stockpile Footprints | 42.4692 | AC | 1500 | /AC | 0 | /AC | 63703.8091
Precip Plant Area | 0.78436 | AC | 1500 | /AC | 0 | /AC | 1176.5379
Misc Precipitation Plant RR | 0.33219 | AC | 1500 | /AC | 0 | /AC | 498.2864
Misc. Disturbance | 175.0165 | AC | 1500 | /AC | 0 | /AC | 262524.794
Misc. Disturbance - RELEASED | 3.1735 | AC | 1500 | /AC | 0 | /AC | 4760.2186 |  | Other tasks/costs previously released, not for revegetation
CZABA Bench/Ramp | 58.6466 | AC | 1500 | /AC | 0 | /AC | 87969.974 |  | Details TBD in pending MR map
Roads- Areas to be Reclaimed | 31.4903 | AC | 1500 | /AC | 0 | /AC | 47235.4805 |  | Assumes 50% of road areas reclaimed (width cut in half); 50% of that area needs slope correction (1.052)
Powerline Road - RELEASED | 0.96866 | AC | 1500 | /AC | 0 | /AC | 1452.9895 |  | Other tasks/costs previously released, not for revegetation
McQueen Townsite | 2.7219 | AC | 1500 | /AC | 0 | /AC | 4082.8016 |  | Check against areas removed for CZABA and pre-1974 areas?
TOTALS | 1979.5786 | AC |  |  |  |  | 2888366.6191
Post-mining features would be managed by BMFOU parties, additional weed control not applied to those areas
Revegetation & Weed Control
Standard Revegetation Costs
Native Seed Mix w/ Moderate Site Prep | 1000 | /ac | *Based on 2025 NRCS Average Seeding Costs
Itemized Revegetation Costs
Condition Seedbed Surface (till, disk, scarify, etc) | 166.37 | /ac | *Based on 2024 MDT Average Contract Price
Seed (typical $250/ac, update per reclamation plan) | 250 | /ac | *2025 Great Basin Seed Company Prices
Seed Application
Drill Seeding (3:1 slope, or less) | 490 | /ac | *2024 MDT Average Contract Price
Drill Seeding (steeper than 3:1) | 1400 | /ac | *2024 MDT Average Contract Price
Broadcast Seeding Application (hand or tractor) | 515 | /ac | *2024 MDT Average Contract Price
Fertilizing Area | 180 | /ac | *2024 MDT Average Contract Price
Reapplication/Fill in Seeding | 191.25 | /ac | *Assumes 25% reseeding/fill in broadcast seeding
BMPs
Erosion Control Blanket | 4.33 | /sy | *2024 MDT Average Contract Price
Straw Wattle | 2.87 | /ft | *RS Means 312514160600 (biodegradeable log)
Silt Fence | 3.51 | /ft | *RS Means 312514161000
Weed Control
Standard Weed Control (5 year revegetation period) | 500 | /ac | *Based on 2025 MT Noxious Weed Control Costs
Total | 1500 | /ac
Assumptions: The estimated revegetation and weed spraying cost for a 5-year period is $1,500 per acre, which includes minor erosion repair and seeding, applying fertilizer, BMPs, etc.
The seeding is accomplished using a small dozer with a seeder attached to the front and a harrow pulled behind.

## 4-Other
Montana Resources, LLC
Operating Permit #00030
Final Comprehensive 5-Year Bond Review
2026-05-04
Task 4- Other Reclamation Activities
Description | Quantity |  | Unit Cost |  | Total Cost |  | Source, Assumptions, Adjustments, etc
OTHER RECLAMATION COST
DRILL HOLE AND WELL ABANDONMENT
West Ridge Monitoring Wells | Total Estimated Well Footage |  |  |  |  | 2025 Prelim | Taken from Explo License details and Amend 010
Plug and abandon drill holes (Explo, now under OP) | 5693 | ft | 13.43 | /ft | 76456.99 | 76456.99
MR25-001 E East- Dewatering Wells | Total Estimated Well Footage
Water Supply Well - Plug/Grout | 10000 | ft | 20.08 | /ft | 200800 | 200800 | Estimated- updated depths from 2025 activities not yet available, consider potential for next 5 years
Pump Removal & Disposal | 4 |  | 460.65 | /well | 1842.6 | 1842.6 | 1/2 - 5 HP Pump, 2023 RS Means 02 41 13 76 0300 | Estimated- updated depths from 2025 activities not yet available, consider potential for next 5 years
Riser pipe removal |  |  |  |  | 0 | 127600 | *Per Operator Preliminary Comments received 1/23/26. No riser pipe removal required in addition to downhole pump removal.
Total Estimated Well Footage
Sitewide Drilling (Pending Annual Reporting) | 5000 | ft | 20.08 | /ft | 100400 | 100400 | Estimated- updated depths from 2025 activities not yet available, consider potential for next 5 years
TSF SPILLWAY CONSTRUCTION
TSF Spillway at Closure | See calculations and notes below |  |  |  | 3448167.3518 |  | Based on KP, 2020 estimates
Detail design TBD-- would extend from TSF embankment to flowpath toward Continental Pit
YEAR 1 - INTERIM SITE MANAGEMENT
Site Care & Maintenance/Reclamation Management (3rd part representative for Agency) |  |  |  |  | 1075328.8 | 1075328.8 | Maintain essential operations while DEQ gets the bond. Anticipated tasks to include dust control (other tasks/tabs), erosion control, weed control, site security, etc.
Site Administration & Equipment |  |  |  |  | 209092 | 209092 | *Includes part time lease of Water Truck and Grader as site reclamation fleet support
Dust Control
Purchase TerraMac |  |  |  |  | 334866 | 334866 | Assume purchase, rather than long-term periodic leasing. Updated quote would be helpful
Magnesium Chloride Application (Assumes 1 spraying on initial beach area, split evenly over 5 years) |  |  |  |  | 348046.5109 | 325901.9827
TSF + Water Monitoring, Management, Treatment and Maintenance
Maintain/replace piezometers + related networks |  |  |  |  | 25000 | 25000
TSF monitoring and inspections (beach, embankments, pond, transition zone, etc.) |  |  |  |  | 92686.32 | 92686.32
In Situ lime treatment for TSF Pond, based on modeling for Amend 010 |  |  |  |  | 0 | 56000 | No longer required in Proposed Bond. As modeled in the "Probable Case" in Amend 010 and further supported by no longer diverting post-closure WED seepage to the pond (now part of BMFOU management)
Sitewide water quality monitoring, compilation of data and reporting |  |  |  |  | 120818.88 | 120818.88
Revegetation Monitoring, compilation of data and reporting |  |  |  |  | 41966.88 | 41966.88
Engineer of Record Inspection + Review |  |  |  |  | 18444 | 18444 | Annual inspection by EOR
YEAR 2 - INITIAL RECLAMATION / CLOSURE SITE MANAGEMENT
Site Care & Maintenance/Reclamation Management (3rd part representative for Agency) |  |  |  |  | 1075328.8 |  | Staff for monitoring/oversight for construction activities and implementing Reclamation Plan (YEARS 2 - 5)
Site Administration & Equipment |  |  |  |  | 209092 |  | *Includes part time lease of Water Truck and Grader as site reclamation fleet support
Dust Control (Assumes first 5 year is split evenly over 5 years)
Magnesium Chloride Application |  |  |  |  | 348046.5109
TSF + Water Monitoring, Management, Treatment and Maintenance
Maintain/replace piezometers + related networks |  |  |  |  | 25000
TSF monitoring and inspections (beach, embankments, pond, transition zone, etc.) |  |  |  |  | 92686.32
In Situ lime treatment for TSF Pond, based on modeling for Amend 010 |  |  |  |  | 0 |  | No longer required in Proposed Bond. As modeled in the "Probable Case" in Amend 010 and further supported by no longer diverting post-closure WED seepage to the pond (now part of BMFOU management)
Sitewide water quality monitoring, compilation of data and reporting |  |  |  |  | 120818.88
Revegetation Monitoring, compilation of data and reporting |  |  |  |  | 41966.88
Engineer of Record Inspection + Review |  |  |  |  | 18444 |  | Annual inspection by EOR
YEAR 3 - INITIAL RECLAMATION / CLOSURE SITE MANAGEMENT
Site Care & Maintenance/Reclamation Management (3rd part representative for Agency) |  |  |  |  | 1075328.8 |  | Staff for monitoring/oversight for construction activities and implementing Reclamation Plan (YEARS 2 - 5)
Site Administration & Equipment |  |  |  |  | 209092 |  | *Includes part time lease of Water Truck and Grader as site reclamation fleet support
Dust Control (Assumes first 5 year is split evenly over 5 years)
Magnesium Chloride Application |  |  |  |  | 348046.5109
TSF + Water Monitoring, Management, Treatment and Maintenance
Maintain/replace piezometers + related networks |  |  |  |  | 25000
TSF monitoring and inspections (beach, embankments, pond, transition zone, etc.) |  |  |  |  | 92686.32
In Situ lime treatment for TSF Pond, based on modeling for Amend 010 |  |  |  |  | 0 |  | No longer required in Proposed Bond. As modeled in the "Probable Case" in Amend 010 and further supported by no longer diverting post-closure WED seepage to the pond (now part of BMFOU management)
Sitewide water quality monitoring, compilation of data and reporting |  |  |  |  | 120818.88
Revegetation Monitoring, compilation of data and reporting |  |  |  |  | 41966.88
Engineer of Record Inspection + Review |  |  |  |  | 18444 |  | Annual inspection by EOR
YEAR 4 - INITIAL RECLAMATION / CLOSURE SITE MANAGEMENT
Site Care & Maintenance/Reclamation Management (3rd part representative for Agency) |  |  |  |  | 1075328.8 |  | Staff for monitoring/oversight for construction activities and implementing Reclamation Plan (YEARS 2 - 5)
Site Administration & Equipment |  |  |  |  | 209092 |  | *Includes part time lease of Water Truck and Grader as site reclamation fleet support
Dust Control (Assumes first 5 year is split evenly over 5 years)
Magnesium Chloride Application |  |  |  |  | 348046.5109
TSF + Water Monitoring, Management, Treatment and Maintenance
Maintain/replace piezometers + related networks |  |  |  |  | 25000
TSF monitoring and inspections (beach, embankments, pond, transition zone, etc.) |  |  |  |  | 92686.32
In Situ lime treatment for TSF Pond, based on modeling for Amend 010 |  |  |  |  | 0 |  | No longer required in Proposed Bond. As modeled in the "Probable Case" in Amend 010 and further supported by no longer diverting post-closure WED seepage to the pond (now part of BMFOU management)
Sitewide water quality monitoring, compilation of data and reporting |  |  |  |  | 120818.88
Revegetation Monitoring, compilation of data and reporting |  |  |  |  | 41966.88
Engineer of Record Inspection + Review |  |  |  |  | 18444 |  | Annual inspection by EOR
YEAR 5 - INITIAL RECLAMATION / CLOSURE SITE MANAGEMENT
Site Care & Maintenance/Reclamation Management (3rd part representative for Agency) |  |  |  |  | 1075328.8 |  | Staff for monitoring/oversight for construction activities and implementing Reclamation Plan (YEARS 2 - 5)
Site Administration & Equipment |  |  |  |  | 209092 |  | *Includes part time lease of Water Truck and Grader as site reclamation fleet support
Dust Control (Assumes first 5 year is split evenly over 5 years)
Magnesium Chloride Application |  |  |  |  | 348046.5109
TSF + Water Monitoring, Management, Treatment and Maintenance
Maintain/replace piezometers + related networks |  |  |  |  | 25000
TSF monitoring and inspections (beach, embankments, pond, transition zone, etc.) |  |  |  |  | 92686.32
In Situ lime treatment for TSF Pond, based on modeling for Amend 010 |  |  |  |  | 0 |  | No longer required in Proposed Bond. As modeled in the "Probable Case" in Amend 010 and further supported by no longer diverting post-closure WED seepage to the pond (now part of BMFOU management)
Sitewide water quality monitoring, compilation of data and reporting |  |  |  |  | 120818.88
Revegetation Monitoring, compilation of data and reporting |  |  |  |  | 41966.88
Engineer of Record and Independent Review Panel Inspections + Review |  |  |  |  | 63273.6 |  | Annual inspection by EOR
OTHER RECLAMATION COSTS |  |  |  |  | 13864279.4962
Well Decommissioning
Well Abandonment Cost (shallow geotech wells) | 13.43 | /ft |  | 2025 RS Means 02 41 13 76 0600
Well Abandonment Cost (up to 8"dia) | 13.43 | /ft |  | 2025 RS Means 02 41 13 76 1000
Well Abandonment Cost (above 10" dia) | 20.08 | /ft |  | 2025 RS Means 02 41 13 76 0700
Water Well Pump Removal (up to 5hp) | 460.65 | /ea |  | 2025 RS Means 02 41 13 76 0300
NOTES AND DETAILED CALCULATIONS:
Drill Hole and Well Abandonment Details
West Ridge Monitoring Wells (taken from Exploration License #00711 bond calculation) |  |  | Well Name | Depth (ft)
|  |  | MW 12-11 | 200
|  |  | MW 12-12 | 200
|  |  | MW 12-13 | 200
|  |  | MW 12-14 | 150
|  |  | MW 12-15 | 200
|  |  | MW 12-16 | 191
|  |  | MW 12-17 | 195
|  |  | MW 12-18 | 115
|  |  | MW 15-01 | 230
|  |  | MW 15-02 | 197
|  |  | MW 15-03 | 386
|  |  | MW 15-04 | 220
|  |  | MW 15-05 | 240
|  |  | MW 15-06 | 400
|  |  | MW 15-07 | 203
|  |  | MW 15-08 | 102
|  |  | MW 15-09 | 142
|  |  | MW 15-10 | 100
|  |  | MW 15-11 | 201
|  |  | MW 15-12 | 99
|  |  | MW 15-13 | 101
|  |  | MW 16-01 | 517
|  |  | MW 16-02D | 552
|  |  | MW 16-02S | 552
|  |  | TOTAL | 5693
E East Drilling and Dewatering Program-- Sitewide Drilling Program (all in Revision 25-001)
Construct TSF Spillway at Closure
Invert Elevation (ft) |  | 6387.5 |  | From conceptual design
Max Discharge (CFS) |  | 330 |  | From conceptual design
Base Width (ft) |  | 10 |  | From conceptual design
Flow Depth (ft) |  | 4.5 |  | From conceptual design
Minimum Grad (%) |  | 1 |  | From conceptual design
Cut Slope into Rampart Mountain |  | 1H:0.58V |  | From conceptual design
Cut Slope into Fill |  | 1H:1.35V |  | From conceptual design
Spillway Channel Length (ft) |  | 2539 |  | From conceptual design
Total Spillway Cut Volume (BCY) |  | 150000 |  | From conceptual design
Total Spillway Cut Volume (LCY) |  | 187500
Armored Swale Length (ft) |  | 730 |  | From conceptual design
Unarmored Swale Length (ft) |  | 7450 |  | From conceptual design
Total Rip Rap Volume (LCY) |  | 1487.037 |  | Approx. 55 ft^3 riprap per foot length of armored swale
Haul Distance to N-S Embankment (miles) |  | 2 |  | From conceptual design
Rock Swell Factor |  | 1.25
Rip Rap Cost
Rip Rap Unit Rate ($/LCY) |  | 52.65 |  | 2025 RSMeans 31 37 13 10 0100
Total Rip Rap Cost |  | 78292.5
Drill and Blast
Drill and Blast Unit Rate ($/BCY) |  | 16.53 |  | 2025 RSMeans 31 23 16 30 0250
Total Drill and Blast Cost |  | 2479500
Swale Grading Cost
Total Swale Length (ft) |  | 8180
Production Rate (l.c.y/hr) |  | 450 |  | Production Rate (max) |  | 375 | lcy/hr
Derating Factors (rock type, operator, grade) |  | 0.747 |  | Correction Factors |  | 0.747
Availability |  | 0.9 |  | Average Operator, Loose stockpile, 50 mins/hr efficiency
Corrected Production Factor |  | 302.535
Volume of Swale (ft3) |  | 743737.87 |  |  | Equipment
Volume of Swale (l.c.y.) |  | 34432.3088 |  | D6 Dozer | 92.68 | /hr
Hours of Work (h) |  | 113.8126 |  |  | Labor
D6 Dozer Unit Cost ($/hr) |  | 140.71 |  |  | 48.03 | /hr |  | Assumptions:
Total |  | 16014.5774 |  |  | 140.71 | /hr |  | Soil Density of 2300 lb per l.c.y
Power-shift machines with 0.05-min fixed time
Using D6M-6SU Dozer (Line G)
Hauler Cycle Time (Min.) | [7 empty] | References: http://nheri.ucsd.edu/facilities/docs/Performance_Handbook_416C.pdf
Haul 10,560 feet One Way, Total Resistance 10%
Cat Edition 45 p.1-21 Cat 753C Haul Truck Rimpull-Speed-Gradeability Curve Loaded Speed (MPH) |  |  |  | 10
Cat Edition 45 p.1-21 Cat 735C Haul Truck Rimpull-Speed-Gradeability Curve Empty Speed (MPH) |  |  |  | 20
Load with Exchange |  | 1.5 | Estimated time for loading alluvium was 2.45. This is a much smaller excavator but calc needs to be completed.
Haul |  | 12
Dump and Maneuver |  | 1.6
Return |  | 6
Potential Cycle Time |  | 21.1
Wait on Slow Hauler |  | 0
Wait to Load, Bunching AVG |  | 0 | Bunching Calc | # of Trucks (Hauler Capabilities)
Total Cycle Time |  | 21.1 | 19.6 | 13.0667
Cycles per Hour |  | 2.8436
CAT 735C Heaped Capacity (LCY) |  | 25
Hauler Potential Production (LCY/HR) |  | 71.09
385C Passes per Hauler |  | 5 | 5 | 390F capacity
Loader Cycle Time (Min.) |  | 0.7
Load Time Truck (Min.) |  | 3.5
Number of Trucks Required |  | 6.0286
Production Rate (LCY/Min.) |  | 7.1429
Hourly Production (LCY/Hr) |  | 428.5714
Efficiency Factor |  | 0.83
Availability |  | 0.9
Adjusted Hourly Production (LCY/Hr) |  | 320.1429
Hours Required (Hr) |  | 585.676
| Qty | Model | Hourly Cost Each | Operating Hours | $ Total
Loaders: | 2 | 374 | 296.54 | 1171.3521 | 347352.7443 |  | Only one loader required for the basic task of loading the hauler. One additional loader used for ripping surface prior to loading.
Haulers: | 6.0286 | 735C | 125.92 | 3530.7898 | 444597.0549
Support: | 1 | D6T | 140.71 | 585.676 | 82410.4752
Fleet Totals | 9.0286 |  |  | 5287.8179 | 874360.2744
Construct Spillway at Closure TOTAL |  |  |  |  | 3448167.3518
Year 1 - Interim Site Management
|  |  | Hourly Rate | Annual Salary
| 1 - Site Manager |  | 230.55 | 479544
| 1 - Site Engineer |  | 186.79 | 388523.2
| 1 - Site Security Officers | Need 2 staff | 40 | 83200
| 1 - Administrative Aide |  | 82.66 | 171932.8
| 1 - Laborer (surface) | Need 2 staff | 39.51 | 82180.8
| 1 - Mechanic |  | 51 | 106080
The staffing schedule for the interim period would be as follows:
|  | Interim Period (YR) | Annual Salary | Total Site A&E Management Cost
| 1/2 - Site Manager | 0.5 | 479544 | 239772
| 1 - Site Engineer | 1 | 388523.2 | 388523.2
| 2 - Site Security Officers | 1 | 166400 | 166400
| 1 - Administrative Aide | 1 | 171932.8 | 171932.8
| 2 - Laborer (surface) | 0.5 | 164361.6 | 82180.8
| 1 - Mechanic | 0.25 | 106080 | 26520
|  |  | Staff Subtotal | 1075328.8
Other costs include: |  |  |  | Total Annual Costs
| 4 - Site Pickup Trucks (including fuel & maintenance) ($/YR) |  |  | 47040 |  | *2025 Costmine Monthly lease Rate of 3/4T Crew Cab Truck = $980/mo
| Water Truck - Site Dust Control/Reclamation fleet support |  |  | 40080 | Assumes 6 months | *2025 Costmine Monthly lease rate of 5,000 gal Water Truck = $6,680/mo
| Motor Grader (14M) - Site/Reclamation fleet support, roads |  |  | 29400 | Assumes 1 month | *2025 Costmine Monthly lease rate of 14M Grader = $29,400/mo
| Electrical Cost per Year ($/YR) |  |  | 22572 |  | *Assumes $1881/mo using Northwest Energy Rate Sheet (10/1/2025; GS-2). Updated estimate would be helpful
| Site Maintenance Supplies |  |  | 60000
| Office Space, Operating Supplies & Misc |  |  | 10000
| Total Annual Cost ($/YR) |  |  | 209092
Interim Site Management, Total Cost |  |  |  |  | 1284420.8
Years 2-5 Closure Reclamation Management
|  |  | Hourly Rate | Annual Salary
| 1 - Site Manager |  | 230.55 | 479544
| 1 - Site Engineer |  | 186.79 | 388523.2
| 1 - Site Security Officers | Need 2 staff | 40 | 83200
| 1 - Administrative Aide |  | 82.66 | 171932.8
| 1 - Laborer (surface) | Need 2 staff | 39.51 | 82180.8
| 1 - Mechanic |  | 51 | 106080
Total Personnel | 8 |  |  | 1311460.8
The staffing schedule for the interim period would be as follows:
|  | Annual Time (YR) | Annual Salary | Annual Site A&E Management Cost
| 1/2 - Site Manager | 0.5 | 479544 | 239772
| 1 - Site Engineer | 1 | 388523.2 | 388523.2
| 2 - Site Security Officers | 1 | 166400 | 166400
| 1 - Administrative Aide | 1 | 171932.8 | 171932.8
| 2 - Laborer (surface) | 0.5 | 164361.6 | 82180.8
| 1 - Mechanic | 0.25 | 106080 | 26520
|  |  | Staff Subtotal | 1075328.8
Other costs include: |  |  |  | Total Annual Costs
| 4 - Site Pickup Trucks (including fuel & maintenance) ($/YR) |  |  | 47040 |  | *2025 Costmine Monthly lease Rate of 3/4T Crew Cab Truck = $980/mo
| Water Truck - Site Dust Control/Reclamation fleet support |  |  | 40080 | Assumes 6 months | *2025 Costmine Monthly lease rate of 5,000 gal Water Truck = $6,680/mo
| Motor Grader (14M) - Site/Reclamation fleet support, roads |  |  | 29400 | Assumes 1 month | *2025 Costmine Monthly lease rate of 14M Grader = $29,400/mo
| Electrical Cost per Year ($/YR) |  |  | 22572 |  | *Assumes $1881/mo using Northwest Energy Rate Sheet (10/1/2025; GS-2). Updated estimate would be helpful
| Site Maintenance Supplies |  |  | 60000
| Office Space, Operating Supplies & Misc |  |  | 10000
| Total Annual Cost ($/YR) |  |  | 209092
Closure Site Management, Total Annual Cost |  |  |  |  | 1284420.8
Dust Control (Years 1-5)
Area to be incrementally reclaimed (Post-1974) | [5 empty] | Divide by 28 Years
YDTI North Transition Zone (AC) | 50.7923 | Reseeding only - not tailings surface, but native soil in current forest |  |  |  | 1.814 | AC
YDTI Tailings Transition Zone (AC) | 251.6126 | Potential grading on small areas (10%?)- soil and reseeding |  |  |  | 8.9862 | AC
|  | Post-1974 area | Post-1974 area
Timeframe | Years | Total Reclaimed Beach Area | Reclaimable Tailings Transition Zone | Reclaimable North Trans Zone
Closure | 0-5 | 735.5502 | 0 | 0 | The reclaimable beach at closure (years 0-5) will become 735.6 (new map) for post-1974 areas
| 5-10 | 780.481 | 44.9308 | 9.07 | The larger area cited in MR's response to the Prelim Bond (>1,100 acres) and within the Rec Plan Table RP-8-2 includes pre-1974 areas
| 10-15 | 825.4118 | 44.9308 | 9.07 | The total area is sprayed one time (split into 5 years, not knowing the rate of coverage)
| 15-20 | 870.3426 | 44.9308 | 9.07 | The total area is not being used for each year between years 0-5
| 20-25 | 915.2734 | 44.9308 | 9.07
| 25-30 | 960.2042 | 44.9308 | 9.07
Equilibrium | 30-33 | 987.1627 | 26.9585 | 5.442
|  | Total | 251.6126 | 50.7923
Terramac Purchase | 334866 |  | MR quote (2020) to purchase a new Terramac from Tri State Truck & Equipment - Update would be helpful
Terramac Operation |  |  | See Above
Area to be covered in first 5 years (AC) | 735.5502 |  | Initial beach footprint, prior to capping.
Hourly application rate (AC/hr) | 4 |  | Estimated - updated values from MR would be helpful
Job Hours | 183.8875 |  | Assume each area receives application at least once prior to soil capping
Hourly Cost (Labor) | 94.09 |  | Assumes 1 equipment operator and 1 general labor
Hourly Cost (Equipment) | 92.68 |  | Estimated - updated values from MR would be helpful
Terramac Total Operation Cost ($) | 34344.6759
Magnesium Chloride Application |  |  | See Above
Area to be covered in first 5 years (AC) | 735.5502 |  | Initial beach footprint, prior to capping. Assume full area receives application once prior to soil capping
Coverage Rate (gallons/acre) | 2420 |  | Stillwater County quote from Dustbusters Inc. (Billings MT) = 0.5 gallon/yd^2; 1 acre = 4840 yd^2
Magnesium Chloride Volume (gallon) | 1780031.3925 |  | Assume 0.5 gallon/yd^2
Magnesium Chloride Cost ($/gallon) | 0.95835 |  | Updated cost provided by MR 11/13/2025
Magnesium Chloride Total Cost ($) | 1705887.8784
MR Mag Chloride Quote: We Dust Control- 10/11/2025
Sales/Delivery Only- Liquid Magnesium Chloride | 35.43 | tons for invoice
| 167.47 | $/ton for material
5933.4621
| 296.6731 | fuel charge
| 6230.1352 | Total Invoice
| 10.9 | Spec Grav (lb/gal)
| 175.8435 | $/ton delivered
| 0.95835 | $/gal delivered
Dust Control for Years 1-5, Total Cost ($) |  |  |  |  | 1740232.5544
TSF + WATER MONITORING, MANAGEMENT, TREATMENT, AND MAINTENANCE
Inspection/Monitoring Requirement | Frequency | Cost Per Event | Cost Per Year | Notes
Capped Surfaces (Embankment and Beach):
Inspect for cracking, slumping/deformation, erosion, slope failure, and any other changes in the embankment shape and tailings surface. Inspect the upstream slope, downstream slope and embankment crest. | Quarterly | 2260.64 | 9042.56 | Sr. Field Tech/Scientist + Field Techs- 8 hours per event
Inspect for daylighting seeps on the downstream embankment slope/benches, water pooling/ponding, soft/wet areas | Monthly | 766.32 | 9195.84 | Field tech- 8 hours per event
Inspect beach surface for dusting risk/potential | Monthly | 766.32 | 9195.84 | Field tech- 8 hours per event
Measure water levels in the monitoring wells and piezometers | Monthly | 1532.64 | 18391.68 | Field tech- 16 hours per event
Survey reclaimed beach for slope/settlement | Annually | 15134.8 | 15134.8 | Sr. Field Tech/Scientist + 2 Field Techs- 40 hours per event
Survey vegetation for plant establishment, cover, die-off, and noxious weeds | Annually | - | - | See Revegetation Tab
Pond and Transition Zone:
Measure pond water level | Monthly | 383.16 | 4597.92 | Field tech- 4 hours per event
Evaluate pond water storage volume | Annually | 2260.64 | 9042.56 | Sr. Field Tech/Scientist + Field Techs- 8 hours per event
Survey vegetation for plant establishment, cover, die-off, and noxious weeds2 | Annually | - | - | See Revegetation Tab
Spillway:
Inspect spillway intake, channel base and side slopes for erosion, blockage, damage, slope failure, and any other changes in the shape and surface of the spillway. | Quarterly and after large storm events | 2260.64 | 9042.56 | Sr. Field Tech/Scientist + Field Techs- 8 hours per event
HsB Seepage Collection System:
Record the HsB Weir flowrate. | Monthly | - | - | Will be managed as part of the BMFOU remedy.
Record the Seep 10 flowrate. | Monthly | - | - | Will be managed as part of the BMFOU remedy.
Site-Wide Water Management:
Inspect surface drainage ditches and culverts for erosion, blockage, damage. | Quarterly and after large storm events | 2260.64 | 9042.56 | Sr. Field Tech/Scientist + Field Techs- 8 hours per event. Will also be managed as part of the BMFOU remedy.
West Embankment Drain: | TBD | - | - | Will be managed as part of the BMFOU remedy.
Monitoring and Field Work Rates | Labor Rate
Project Manager | 230.55
Staff Scientist/Sr. Field Tech | 186.79
Field Technician | 95.79
Admin Support | 82.66
TSF Monitoring and Inspection- Total Costs Per Year |  |  |  |  | 92686.32
Engineer of Record and Independent Review Panel- Inspections and Review
Inspection/Monitoring Requirement | Frequency | Cost Per Event | Cost Per Year | Notes
Capped Surfaces (Embankment and Beach):
Engineer of Record | Annually | 18444 | 18444 | Assume 80 hours for annual inspection, review, and reporting-- EOR hourly rate not known
Independent Review Panel- Periodic Review | At least every 5 years | 44829.6 | 44829.6 | Assume 80 hours for each panel member inspection, review, and reporting-- IRP hourly rate not known
every 5 years
In Situ lime treatment for TSF Pond, based on modeling for Amend 010
Preliminary Bond:
Lime applied (ton/year) | 150
Unit cost for hydrated lime ($/ton)- delivered | 140 |  | Updated cost from MR on 11/13/2025
Cost for hydrated lime for in situ water treatment, per year | 21000
Purchase/installation of lime slurry application and mixing system
Initial purchase cost | 25000 | Year 1
Annual O&M | 10000
Water Quality Monitoring
Analytical Costs | [5 empty] | Updated Quote from Energy Labs- 9/3/2025
Groundwater aites (24) will be monitored twice per year |  |  |  |  | Acidity | 22
Surface water sites (12) will be monitored twice per year, as presented in current Annual Progress Reports |  |  |  |  | Alkalinity | 16
Sampling Frequency (Times/Year) |  |  | 2 |  | Anions | 32
Number of Sites (EA) |  |  | 36 |  | Conductivity | 16
Number of Samples per Year (Samples/Year) |  |  | 72 |  | pH | 16
Estimated Cost per Sample ($/EA) |  |  | 735 |  | Total Dissolved Solids | 29
Total Year Analytical Costs ($/YEAR) |  |  | 52920 |  | Total Suspended Solids | 23
[5 empty] | Mercury | 63
[5 empty] | Metals by ICP/ICPMS | 432
[5 empty] | Metals Digestion | 22
[5 empty] | Nitrate + Nitrite | 32
[5 empty] | Phosphorous, total | 29
[5 empty] | Sample disposal fee | 3
735
Field Work Per Sampling Event | Rate | Quantity | Cost
Project Manager | 230.55 | 16 | 3688.8
Staff Scientist/Sr. Field Tech | 186.79 | 16 | 2988.64
Field Technician (2) | 95.79 | 160 | 15326.4
Admin Support | 82.66 | 8 | 661.28
Supplies | 1000 | 1 | 1000
Sample Shipping Cost ($/Event) | 100 | 4 | 400
Subtotal Per Event |  |  | 24065.12
Total Year Field Work Costs ($/YEAR) |  |  | 48130.24 | Two sampling events per year
Report Preparation - Annual Report | Rate | Quantity | Cost
Project Manager | 230.55 | 8 | 1844.4
Staff Scientist/Sr. Field Tech | 186.79 | 40 | 7471.6
Field Technician(2) | 95.79 | 80 | 7663.2
Admin Support | 82.66 | 16 | 1322.56
Map/GIS/Drafting | 91.68 | 16 | 1466.88
Total Year Reporting Costs ($/YEAR) |  |  | 19768.64 | One annual report per year
Water Quality Monitoring, Data Compilation, and Reporting- Total Costs |  |  | 120818.88 |  | EACH YEAR
Vegetation/Reclamation Monitoring, Data Compilation, Reporting
Field Work Per Monitoring Event | Rate | Quantity | Cost
Project Manager | 230.55 | 16 | 3688.8
Staff Scientist/Sr. Field Tech | 186.79 | 16 | 2988.64
Field Technician (2) | 95.79 | 160 | 15326.4 | Assume 2 weeks (80 hours) for 2 staff
Admin Support | 82.66 | 8 | 661.28
Supplies | 1000 | 1 | 1000
Total Year Field Work Costs ($/YEAR) |  |  | 23665.12
Data Compilation- Report Preparation | Rate | Quantity | Cost
Project Manager | 230.55 | 8 | 1844.4
Staff Scientist/Sr. Field Tech | 186.79 | 40 | 7471.6
Field Technician(2) | 95.79 | 80 | 7663.2
Admin Support | 82.66 | 16 | 1322.56
Map/GIS/Drafting | 0 | 16 | 0
Total Year Reporting Costs ($/YEAR) |  |  | 18301.76
Monitoring Event, Data Compilation, and Reporting |  |  | 41966.88 |  | EACH ANNUAL EVENT
Revision 25-001, 3/20 Reply:
E East: At this time, any drilling in the area is not anticipated to utilize larger than a 12-inch diameter completion, consisting of no more than 10,000 linear feet of well completion (in total). It is anticipated that any new roads would be maintained, post-mining, for site security near the east-northeast extent of the permit boundary. New disturbances associated with highwall stabilization are not known at this time and cannot be differentiated; however, total new disturbance in this area will not exceed 10 acres. Even though it is anticipated that any new roads would be maintained, postmining, for the purposes of this revision, the (up to) 10 acres of new disturbance can be considered for future reclamation.
Dewatering: It is anticipated that flows would be minor, especially relative to existing sitewide flows and water management (i.e., hundreds of gallons per day (or less) versus millions of gallons per day). Also, it is anticipated that dewatering flows would ultimately be routed in temporary pipelines from well(s) to existing conveyance structures that are included in MR’s water resources monitoring program (WQ-2 or WQ-5), sampled semi-annually and reported in MR’s Annual Progress Report for Operating Permit. Any dewatering being considered is not planned to occur during post-mining.
Sitewide Drilling: Locations for other sitewide drilling activities are anticipated to be in previously disturbed areas. Otherwise, footprints would be minimized, and if outside the Continental Pit footprint, would be included in other site reporting (i.e., reports provided by Engineer of Record and/or MR Annual Progress Report(s) for Operating Permit) Applicable Reclamation Methods: -- Wells and drillholes used in the mining operation, that are deemed unnecessarry, would be decommissioned in accordance with ARM 17.24.106, 17.24.107, and/or 36.21.810 (see Section 8.9.1)
-- Monitoring wells not required for postclosure monitoring would be abandoned in accordance with ARM 36.21.810 and reclaimed per MCA 82-4-336(9).
-- Exploration disturbances, including drillholes, wells, pads, and access roads not required for post-closure monitoring, will be abandoned and reclaimed per ARM 17.24.104 through 17.24.107 and MCA 82-4-332(4) and 82-4-336(9)(a).
-- Long-term monitoring sites in previously undisturbed areas will be ripped as necessary, regraded, covered with 6 inches of topsoil (if topsoil was previously removed), amended as recommended by testing, and revegetated as described in Section 6.0. The same reclamation methods would apply to long-term monitoring sites in disturbed ground, except that coversoil application would be consistent with adjacent areas and the slope specifications described in Section 4.4.
-- When monitoring wells and drillholes are no longer needed, they would be abandoned per ARM 17.24.106, 17.24.107, 36.21.670, and/or 36.21.810; pads would be graded to a stable configuration per ARM 17.24.107(4) and seeded using MR’s permanent mix in Table RP-6-1.
2023 Reclamation Plan: 10.5 WATER RESOURCES MONITORING
Following cessation of mining operations, a post-closure water monitoring program would be implemented. During the final phases of mine operations, a post-closure monitoring plan would be developed in consultation with DEQ based on the final mine facilities layout and operational phase monitoring results. The post-closure water monitoring program would be used in conjunction with other reclamation and revegetation monitoring to document post-reclamation conditions at the former mine site and surrounding water resources. Post-closure monitoring would occur until such time as the mine is certified as fully reclaimed and all bonding release milestones are met, or as determined in the post-closure monitoring program to be developed in conjunction with DEQ. After termination of the post-closure water monitoring, any continued water monitoring would occur as part of the BMFOU program, if necessary. Assumptions: All wells are monitored during the spring (June) and fall (October) for a 20-year period (Amendment 010) (see Table 10-2) A third party contractor would be hired to do the sampling and data reporting
Assumptions: Well depth information gathered from Table 4-1 in September 2017 OP Amendment Application. At the end of post-closure monitoring, wells must be plugged and abandoned. Hole plugging rate includes equipment, personel, and materials to backfill hole. Plugging includes bentonite from the bottom to within 5-10 feet of surface, then cement fill from top of bentonite to land surface, per MT ARM 17.24.106(2)
2023 Rec Plan: 8.1.4 Closure Spillway
A conceptual closure spillway has been designed to prevent water from pooling against the embankment (Figure RP-8-4). A conceptual design for the closure spillway is presented in Appendix B to Knight Piésold’s Reclamation Overview report of the Design Document (KP 2018b).
The spillway walls and bottom in the segment would be excavated in bedrock. The spillway segment traversing previously disturbed areas would be regraded, covered with 20 inches of alluvium, and broadcast seeded with the mixture shown in Table RP-6-1.
8.1.5 West Embankment Drain and Pond
Post-closure, water collected by the WED would be managed as part of the BMFOU remedy per resolution of a stipulation to Permit Amendment 10.
When the Extraction Pond is no longer deemed necessary, its reclamation would also be managed as part of the transition of WED flow to BMFOU remedy.
Assumptions: A conceptual post-closure spillway design was approved through Amend 010. A detailed design will be undertaken once the facility closure is imminent and closure conditions are available. The design is located in KP's Reclamation Overview Design Document, Appendix B. The spillway was modeled as a trapezoid channel cut into bedrock on the left abutment of the YDTI embankment. The excavated channel will extend 5,000 feet southward to a point where local topography creates a flow path to the Continental Pit. The conceptual spillway intake and channel designs and costs were provided by Knight Piesold (2020), as follows:
Assumptions: At closure, all processing fluids and remaining tailings from the mill circuit are discharged to the impoundment. Ongoing discharge of BMFOU waters into the TSF is not currently approved. The tailings are allowed to dry naturally and consolidate, therefore are susceptible to wind erosion. Based on the 2025 map, a certain area can be capped with 28 inches of alluvium or 22 inches of alluvium and 6 inches of topsoil (see Earthmoving tab costs) in the first 5 years of Interim and Closure tasks. Dust control may be neeeded for this area initially, but the area will decrease in the future as capping is completed. The exposed transition zone will need dust control in the future (see Long-Term tab). The meterological station will still be available to provide live-time data (rental rates are included). If deemed applicable and safe, dust suppressant, such as Magnesium Chloride, will be applied using a purchased Terramac RT9. Dust suppressant is applied to the tailings beach surface at varying application rates. Deployment of the Terramac, requires two operators to maneuver the machine (hourly rate to be included here).
Repair or Clean out the Extraction Pond: This feature is to be managed under BMFOU (as outcome to Amend 010 Stipulation)- no bond required for Hard Rock Mining Operating Permit. Assumptions from 2020 Bond: The Extraction Pond may become damaged or require maintenance. The Extraction Basins with two installed wells would remove seepage from the WED and return to the YDTI, while the pond is repaired. The nature and extent of the repair or clean out work is unknown, so a yearly cost of $50,000 is assumed. It is assumed that the pond elevation will not exceed 6380 feet in the next 5 years, see "Water Treatment" tab. Therefore, hydrodynamic containment through use of the WED and other contingency features would not be required. The Extraction Pond would not be needed to contain water prior to treatment and being pumped back to the YDTI pond The WED would be plugged in the case of an unforeseen closure in the next 5 year period.
Plug WED: This feature is to be managed under BMFOU (as outcome to Amend 010 Stipulation)- no bond required for Hard Rock Mining Operating Permit. Assumptions from 2020 Bond: After closure, seepage to a flow through the WED will steadly decrease as the impoundment drains down and the pond level decreases. Under the full extent of operations/filling in Amendment 010, the pond level was expected to approach the 6380 foot target level for maintaining hydrodynamic containment. After approximatelyt 20 years of draindown, the south end of the WED would be grouted or otherwise plugged to preclude drainage to the Extraction Pond. The WED is designed to transmit 4,500 gallons per minute. The cross sectional area is 300 Square Feet. The drain rock is approximately 7 feet thick and 43 feet wide. The depth to WED invert from embankment crest is 110 feet. According to the Reclamation Overview Design Document (page 10 of 15) the WED connection to the Extraction Pond will be decommissioned by grouting the section of the drain through the topographic boundary "Rocky Knob" Based on data provided in RS Means (Section A10 Foundations) Cast-in-Place Concrete Piles To stop the flow, 4 rows of Cast-in-Place piles 2 feet apart across the WED are necessary. A total of 80 piles are required. Based on cost data provided by RS Means, one row of Cast-in-Place piles will cost $125,000 each. Assuming 4 rows are required, the total cost is $500,000.
Maintain Electrical System for Extraction Basin: This feature is to be managed under BMFOU (as outcome to Amend 010 Stipulation)- no bond required for Hard Rock Mining Operating Permit. Assumptions from 2020 Bond: The electrical systems need to be maintained on the west side to run the two subermersible pumps in the Extraction Basin. Assume a yearly cost of $10,000 to maintain the electrical systems on the west side. It is assumed that the pond elevation will not exceed 6380 feet in the next 5 years, see "Water Treatment" tab. Therefore, hydrodynamic containment through use of the WED and other contingency features (extraction basins) would not be required. The WED would be plugged in the case of an unforeseen closure in the next 5 year period.
Install Submersible Pumps in Extraction Basins: This feature is to be managed under BMFOU (as outcome to Amend 010 Stipulation)- no bond required for Hard Rock Mining Operating Permit. Assumptions from 2020 Bond: The WED was designed to operate with continious pumping at the Extraction Pond at a design flow of 4,500 gpm. The Extraction Basin was designed to have an operations ready alternative pumping option. The Extraction Basin pump intake assembly is operational but the pumps have not been purchased .The Extraction Basin discharge pipeline assemble has NOT been installed. The Extraction Basin pumping system, two 2,250 gpm submersible pumps, have NOT been purchased. Based on cost data obtained from RS Means (22 14 2100) one submersible pump cost approximately $16,000. The discharge pipeline with a pressure transducer, air release valve, and flow meter is estimated to cost another $10,000 each. Electrical Costs estimated at $10,000 per year. The estimated total cost is #53,000. It is assumed that the pond elevation will not exceed 6380 feet in the next 5 years, see "Water Treatment" tab. Therefore, hydrodynamic containment through use of the WED and other contingency features (extraction basins) would not be required. The WED would be plugged in the case of an unforeseen closure in the next 5 year period.
Maintain and Replace Piezometers and Remote Comms System: Assumptions: Vibrating wire piezometer data is transmitted from the monitoring sites to an on-line system via cellular/radio connection. Data is viewable in live-time on Sensemetrics online system. Annual repair, maintainace, replacement, and upgrade of the system would be necessary. The nature and extent of the work to repair, replace, or upgrade is unknown, so an annual cost of $25,000 is assumed.
Amendment 010 (2018): "For the Worst Case, the pool would gradually become slightly acidic after closure (net alkalinity of -200 mg/L and pH of 5.5 to 7.0), with iron of up to 36 mg/L and aluminum up to 16 mg/L. Sulfate would be around 1100 mg/L (TDS of 1800 mg/L) at closure and would gradually decline to less than 500 mg/L (TDS 1000 mg/L) around 30 years post-closure.
If acidic conditions were to develop after closure, lime would be added to maintain alkaline conditions and low metals. 5000 tons of lime would be needed over the 30-year post-closure period, or about 150 tons per year. " 2023 Reclamation Plan: 10.2.5 Post-Closure Beach and Pond Management and Monitoring Post-closure pond management and monitoring will include:
• for the Probable Case model of post-closure pond water quality, water treatment is not anticipated since the pool would remain alkaline and metals would remain low (see Appendix C “Phase Two Mass Load Model of the Yankee Doodle Tailings Pond” in Amendment 10 (MR 2018)). Assumptions: Additional details or designs are not available about the infrastructure or methods to apply lime to the residual tailings pond, or ensure sufficient mixing to optimize pH adjustment of the system. Assumed costs provided below:
Assumptions: Based on DEQ's experience with previous operation bankruptcy, approximately a one-year period of interim maintenance is needed to obtain the bond. These tasks and costs represent the essential operations while the agency gets the bond. A third party contractor would be hired to monitor the site during the interim period. The interim site maintenance activities that were identified mainly deal with controlling dust off the impoundment, erosion control, and weed spraying. Dust control for closure year 1 is included below, not duplicated here. Water monitoring is included below, not duplicated here. Fluids from the Concentrator and Precipitation Plant are exempt (pre-1971), so no reclamation cost can be bonded. Assume the following personnel to manage the site, oversee contractors, and implement any initial components of the reclamation plan:
Assumptions: It is assumed the during the closure period reclamation would start in earnest beginning after the first year following closure (Year 1) and take approximately 4 years to complete (Years 2 through 5). A third party contractor would be hired to implement the approved reclamation plan. Other ongoing maintenance activities would continue (dust control, erosion control, weed spraying, etc.) Dust control for Years 2-5 is included below, not duplicated here. Water monitoring for Years 2-5 is included below, not duplicated here.
Assume the following personnel to manage the site, oversee contractors, and implement the approved reclamation plan:
10.4 REVEGETATION MONITORING AND MANAGEMENT
Reclaimed areas are monitored to assess desirable plant establishment, particularly as it relates to the utility and stability of reclamation relative to adjacent areas. Monitoring data also characterize the presence and extent of undesirable species and prescribe management options. MR evaluates the relationship between coversoil and/or topsoil characteristics and revegetation establishment. Site stability measurements include the distribution, dimensions, and photo documentation of erosion features. Monitoring work also includes inspection of catchment areas, including Clearwater Ditch, to identify potential impacts of sediment deposition on surface flow patterns and prescribe remedies.
Sites with poor vegetation establishment, substantial erosion, or undesirable sediment deposition are identified for supplemental seeding and/or repair.
Revegetated areas will be qualitatively and quantitatively evaluated by qualified reclamation specialists. Initially, monitoring would focus on documenting perennial grass seedling density, identifying areas with noxious weeds or other invasive species, and describing areas with accelerated erosion. Subsequent monitoring would focus on documenting revegetation development to a stable, self-sustaining vegetative cover that is capable of supporting post-closure land use objectives.
10.4.1 First Growing Season Monitoring
Typically, monitoring during the first growing season would occur as late as practicable within that season to allow for plant establishment. Monitoring would focus on evaluating perennial grass establishment, erosion, and invasive species establishment.
10.4.2 Subsequent Growing Season Monitoring
Revegetation monitoring in subsequent growing seasons would focus on documenting the establishment of a stable, self-sustaining vegetative cover that is capable of supporting post-closure land use objectives. In particular, monitoring in subsequent years would document plant canopy cover and species composition as well as continue to record accelerated erosion and invasive species. 10.4.3 Revegetation Management
Areas with poor germination and/or growth would be noted and evaluated during revegetation monitoring to determine the probable cause. Remedial seeding or additional erosion control measures may be completed if necessary to address areas of poor germination or growth.
Revegetation techniques and seed mixtures proposed in this Reclamation Plan may be modified, with DEQ concurrence, to improve revegetation success if monitoring indicates failure, or if new techniques or methods are developed that would improve revegetation establishment and stability. Vehicle traffic would be barred from reclaimed areas. Wildlife damage may be controlled as necessary by selective fencing or chemical repellent.
Noxious weeds would be treated as discussed in Section 10.7 and Appendix RP-A.
The goal of reclamation is to establish a stable, self-sustaining vegetative cover capable of supporting post-closure land use objectives. MR prefers to minimize special post-closure treatments that would be necessary to achieve this goal. Irrigation, supplemental fertilization, interseeding or other treatments are not proposed at this time but may be considered on a case-by-case basis as necessary, following consultation with DEQ. Assumptions: The schedule in the Reclamation Plan reflects the required timelines for the permittee and their available equipment fleet and staffing.
Following a hypothetical bankruptcy or permit revocation and bond forfeiture, DEQ assumes that at least 1 year will be needed to resolve bankruptcy conditions and/or obtain the bond. Reclamation will occur annually across the mine site during the initial years post-closure (assumed within 5 years from closure), followed by less frequent reclamation of the TSF transition zone as the pond recedes to an equilibrium volume/elevation. BMFOU water management and treatment would be ongoing throughout this time period, under the applicable requirements for the Remedy. - Year 1 interim management and monitoring (legal process/obtain bond); - Years 2-5 implement major reclamation actions, site management and monitoring; - Years 6-30+ incremental reclamation of TSF transition zone, post-closure site management and monitoring Revegetation monitoring would occur annually for five years following successive seeding campaigns, then frequency would decrease to five year intervals until determining stable vegetation sucess to allow bond release/permit closure.
Proposed Bond Update: A contingency for lime treatment of the post-closure TSF pond is no longer necessary or "reasonably foreseeable." This cost is removed from the Proposed Bond.
The "Worst Case" and "Probably Case" scenarios in Amendment 010 (2018) included pumping the water from WED seepage back to the TSF pond, which would be a long-term source of acidity and metals. There was also uncertainty at that time about the kinetic behavior of tailings that remained unreclaimed during pond recession.
The WED seepage is now considered part of BMFOU post-mining management (9/12/22 approval from EPA), meaning this would no longer be an inflow source to the pond. MR has also conducted kinetic tests of tailings (2023-2024; in Amend 012 application) to demonstrate a slow oxidation rate, which supports assumptions that exposed tailings would be capped quickly or otherwise saturated and precluded from significant acidification of the pond. If the pond is retained as a water treatment feature under BMFOU (decision not yet formalized?), then contingencies for the water level and chemistry would fall under Superfund authority.

## 5-Long-Term
Montana Resources, LLC
Operating Permit #00030
Final Comprehensive 5-Year Bond Review
2026-05-04
Task 5- Long-Term Activities
Description | [6 empty] | Source, Assumptions, Adjustments, etc
YEARS 6 - 33, ANNUAL TASKS, POST-CLOSURE
Site Care & Maintenance/Reclamation Management (3rd part representative for Agency) |  |  | 450028.8 |  |  |  | Maintain essential operations while DEQ gets the bond. Anticipated tasks to include dust control (other tasks/tabs), erosion control, weed control, site security, etc.
Site Administration & Equipment |  |  | 130332 |  |  |  | *Includes annual lease of Water Truck for dust control/site reclamation fleet support
TSF + Water Monitoring, Management, Treatment and Maintenance
Maintain/replace piezometers + related networks |  |  | 25000
TSF monitoring and inspections (beach, embankments, pond, transition zone, etc.) |  |  | 92686.32
In Situ lime treatment for TSF Pond, based on modeling for Amend 010 |  |  | 0 |  | No longer required in Proposed Bond. As modeled in the "Probable Case" in Amend 010 and further supported by no longer diverting post-closure WED seepage to the pond (now part of BMFOU management)
Sitewide water quality monitoring, compilation of data and reporting |  |  | 120818.88
Engineer of Record Inspection + Review |  |  | 18444 |  |  |  | Annual inspections by EOR
YEARS 6 - 33, PERIODIC TASKS (EVERY 5 YEARS), POST-CLOSURE
Independent Review Panel inspection & Review | Every 5 years, starting year 10 |  | 44829.6
TSF Transition Zone | Every 5 years, starting year 10 |  | 44.9308 | AC per 5-year increment |  |  | Assume Transition Zone total is split into increments
Transition Zone Settlement - Recontouring/Regrading | Assumes 10% of Area |  | 6388.0256
Transition Zone Alluvium Placement |  |  | 398767.9477
Seeding & Weed Control |  |  | 67396.2233 |  |  |  | Every 5 years (after Years 1-5)
Revegetation Monitoring, compilation of data and reporting |  |  | 41966.88 |  |  |  | Every 5 years (after Years 1-5)
TSF North Transition Zone |  |  | 9.07 | AC per 5-year increment |  |  | Assume North Transition Zone total is split into increments
Seeding & Weed Control | Every 5 years, starting year 10 |  | 13605.0734 |  |  |  | Every 5 years (after Years 1-5)
Dust Control | [5 empty] | Prelim bond
Magnesium Chloride Application on incrementally exposed tailings |  |  | 21260.2952 |  |  | 16812 | Assumes remaining exposed tailings are sprayed once- cost/area is split evenly over 5-year increments
LONG-TERM CLOSURE RECLAMATION COST
LONG-TERM CARE & MAINTENANCE, POST-CLOSURE | Years of Interest (n) |  | Includes Discount Rate @ |  | 2%
Year 6 | 5 |  | 837310 | -78932.5356 | 758377.4644
Year 7 | 6 |  | 837310 | -93802.682 | 743507.318
Year 8 | 7 |  | 837310 | -108381.2568 | 728928.7432
Year 9 | 8 |  | 837310 | -122673.9773 | 714636.0227
Year 10 | 9 |  | 903399.8952 | -147475.2757 | 755924.6195
Year 11 | 10 |  | 837310 | -150424.165 | 686885.835
Year 12 | 11 |  | 837310 | -163892.5147 | 673417.4853
Year 13 | 12 |  | 837310 | -177096.7792 | 660213.2208
Year 14 | 13 |  | 837310 | -190042.1364 | 647267.8636
Year 15 | 14 |  | 903399.8952 | -218735.6774 | 684664.2178
Year 16 | 15 |  | 837310 | -215176.3364 | 622133.6636
Year 17 | 16 |  | 837310 | -227375.0357 | 609934.9643
Year 18 | 17 |  | 837310 | -239334.5448 | 597975.4552
Year 19 | 18 |  | 837310 | -251059.5537 | 586250.4463
Year 20 | 19 |  | 903399.8952 | -283278.4188 | 620121.4764
Year 21 | 20 |  | 837310 | -273824.3731 | 563485.6269
Year 22 | 21 |  | 837310 | -284873.1109 | 552436.8891
Year 23 | 22 |  | 837310 | -295705.2067 | 541604.7933
Year 24 | 23 |  | 837310 | -306324.9086 | 530985.0914
Year 25 | 24 |  | 903399.8952 | -341736.7681 | 561663.127
Year 26 | 25 |  | 837310 | -326943.7068 | 510366.2932
Year 27 | 26 |  | 837310 | -336950.889 | 500359.111
Year 28 | 27 |  | 837310 | -346761.852 | 490548.148
Year 29 | 28 |  | 837310 | -356380.4431 | 480929.5569
Year 30 | 29 |  | 903399.8952 | -394684.2963 | 508715.5989
Year 31 | 30 |  | 837310 | -375055.5239 | 462254.4761
Year 32 | 31 |  | 837310 | -384119.3372 | 453190.6628
Year 33 | 32 |  | 882139.6 | -414046.9499 | 468092.6501 | Final year- last monitoring and verification for closure (All capped- no tailings dust control)
LONG-TERM RECLAMATION TASKS, POST-CLOSURE | Years of Interest (n) |  | Includes Discount Rate @ |  | 2% |  | Does not include Dust Control (added above)
Year 10 | 9 |  | 528124.1499 | -86213.4864 | 441910.6634
Year 15 | 14 |  | 528124.1499 | -127872.0468 | 400252.1031
Year 20 | 19 |  | 528124.1499 | -165603.4884 | 362520.6615
Year 25 | 24 |  | 528124.1499 | -199778.0176 | 328346.1323
Year 30 | 29 |  | 528124.1499 | -230730.9416 | 297393.2083
Year 33 | 32 |  | 316874.4899 | -148730.3325 | 168144.1574 |  | Remaining 3 years = Transition Zone and North Transition Zone
LONG-TERM CARE & MAINTENANCE COSTS |  |  |  |  | 16714870.8206
LONG-TERM RECLAMATION COSTS |  |  |  |  | 1998566.9259
NOTES AND DETAILED CALCULATIONS:
Post Closure Management
A third party A&E firm would be hired to implement the post closure reclamation plan
Third Party Construction Management Cost Reconciliation is located under "Labor Rates"
It is assumed the "Post Closure" period would begin five years after "Closure" begins (Year 6)
These A&E calculations apply to management and oversight for activities conducted from Years 6-33 (27 years)
Assume that 4 employees would be needed to maintain the mine site and deal with environmental problems
The 4 people would be needed to cover the mine site 24 hours a day, 7 days a week
The 4 key people include:
|  |  | Hourly Rate | Annual Salary
| 1 - Site Manager |  | 230.55 | 479544
| 1- Site Security Officers |  | 40 | 83200
| 1 - Administrative Aide |  | 82.66 | 171932.8
| 1 - Laborer (surface) |  | 39.51 | 82180.8
Total Personnel |  |  |  | 816857.6
The staffing schedule for years 6-33 would be as follows:
|  | Staffing Year 6-33 | Annual Salary | Total Site A&E Management Cost
| 1/2 - Site Manager | 0.5 | 479544 | 239772
| 1 - Site Security Officers | 1 | 83200 | 83200
| 1 - Administrative Aide | 0.5 | 171932.8 | 85966.4
| 1 - Laborer (surface) | 0.5 | 82180.8 | 41090.4
450028.8
Other costs include: |  |  |  | Total 25 Years A&E Other Costs
| 2 - Site Pickup Trucks (including fuel & maintenance) ($/YR) |  |  | 23520 |  | *2025 Costmine Monthly lease Rate of 3/4T Crew Cab Truck = $980/mo
| Water Truck - Site Dust Control/Reclamation fleet support |  |  | 20040 | Assumes 3 months | *2025 Costmine Monthly lease rate of 5,000 gal Water Truck = $6,680/mo
| Motor Grader (14M) - Road maintenance as needed |  |  | 29400 | Assumes 1 month | *2025 Costmine Monthly lease rate of 14M Grader = $29,400/mo
| Electrical Cost per Year ($/YR) |  |  | 22572 |  | *Assumes $1881/mo using Commercial Customer quote. Updated estimate would be helpful
| Heavy Equipment Rental |  |  | 4800
| Site Maintenance Supplies |  |  | 20000
| Office Space, Operating Supplies & Misc |  |  | 10000
| Total Annual Cost ($/YR) |  |  | 130332
Post-closure electrical costs are assumed to include office space and equipment, lighting/security around the facility, any hard-wired monitoring systems
Post Closure Management, Total Cost |  |  |  |  | 580360.8
Dust Control (Years 6-33)
Area to be incrementally reclaimed (Post-1974) | [5 empty] | Divide by 28 Years
YDTI North Transition Zone (AC) | 50.7923 | Reseeding only - not tailings surface, but native soil in current forest |  |  |  | 1.814 | AC | 5.442
YDTI Tailings Transition Zone (AC) | 251.6126 | Potential grading on small areas (10%?)- soil and reseeding |  |  |  | 8.9862 | AC | 26.9585
|  | Post-1974 area | Post-1974 area
Timeframe | Years | Total Reclaimed Beach Area | Reclaimable Tailings Transition Zone | Reclaimable North Trans Zone
Closure | 0-5 | 735.5502 | 0 | 0 | The reclaimable beach at closure (years 0-5) will become 735.6 (new map) for post-1974 areas
| 5-10 | 780.481 | 44.9308 | 9.07 | The larger area cited in MR's response to the Prelim Bond (>1,100 acres) and within the Rec Plan Table RP-8-2 includes pre-1974 areas
| 10-15 | 825.4118 | 44.9308 | 9.07 | The total area is sprayed one time (split into 5 years, not knowing the rate of coverage)
| 15-20 | 870.3426 | 44.9308 | 9.07 | The total area is not being used for each year between years 0-5
| 20-25 | 915.2734 | 44.9308 | 9.07
| 25-30 | 960.2042 | 44.9308 | 9.07
Equilibrium | 30-33 | 987.1627 | 26.9585 | 5.442
|  | Total | 251.6126 | 50.7923
Terramac Operation
Area to be covered every 5 years (AC) | 44.9308 |  | Exposed transition zone is the only accessible tailings surface that has not been capped, could produce dust
Hourly application rate (AC/hr) | 4 |  | Estimated - updated values from MR would be helpful
Job Hours | 11.2327 |  | Assume each area receives application at least once prior to soil capping
Hourly Cost (Labor) | 94.09 |  | Assumes 1 equipment operator and 1 general labor
Hourly Cost (Equipment) | 92.68 |  | Estimated - updated values from MR would be helpful
Terramac Total Operation Cost ($) | 2097.9321
Magnesium Chloride Application
Area to be covered in first 5 years (AC) | 44.9308 |  | Assume full area receives application once prior to soil capping
Coverage Rate (gallons/acre) | 2420 |  | Stillwater County quote from Dustbusters Inc. (Billings MT) = 0.5 gallon/yd^2; 1 acre = 4840 yd^2
Magnesium Chloride Volume (gallon) | 108732.5735 |  | Assume 0.5 gallon/yd^2
Magnesium Chloride Cost ($/gallon) | 0.95835 |  | Updated cost provided by MR 11/13/2025
Magnesium Chloride Total Cost ($) | 104203.5438
Dust Control, Every 5 Years (Years 6-33), Total Cost ($) |  |  |  |  | 106301.4759 | Every 5 years (after Years 1-5)
Vegetation/Reclamation Monitoring, Data Compilation, Reporting
Field Work Per Monitoring Event | Rate | Quantity | Cost
Project Manager | 230.55 | 16 | 3688.8
Staff Scientist/Sr. Field Tech | 186.79 | 16 | 2988.64
Field Technician (2) | 95.79 | 160 | 15326.4 | Assume 2 weeks (80 hours) for 2 staff
Admin Support | 82.66 | 8 | 661.28
Supplies | 1000 | 1 | 1000
Total Year Field Work Costs ($/YEAR) |  |  | 23665.12
Data Compilation- Report Preparation | Rate | Quantity | Cost
Project Manager | 230.55 | 8 | 1844.4
Staff Scientist/Sr. Field Tech | 186.79 | 40 | 7471.6
Field Technician(2) | 95.79 | 80 | 7663.2
Admin Support | 82.66 | 16 | 1322.56
Map/GIS/Drafting | 91.68 | 16 | 1466.88
Total Year Reporting Costs ($/YEAR) |  |  | 19768.64
Vegetation/Reclamation Monitoring Event, Data Compilation, and Reporting |  |  |  |  | 43433.76 | Every 5 years (after Years 1-5)
Assumptions: Ongoing discharge of BMFOU waters into the TSF is not currently approved. The tailings are allowed to dry naturally and consolidate, therefore are susceptible to wind erosion. The exposed transition zone will need dust control before it is capped with alluvioum and revegetated. If deemed applicable and safe, dust suppressant, such as Magnesium Chloride, will be applied using a purchased Terramac RT9. Dust suppressant is applied to the tailings beach surface at varying application rates. Deployment of the Terramac, requires two operators to maneuver the machine (hourly rate to be included here).

## Labor Rates 2025
MONTANA - Prevailing Wage Rates for Heavy Construction Services 2025 |  |  |  |  | 2024 rates (no rates issued for 2025)
*Effective: January 13, 2025
Title | Description | Wage | Benefit | Total | Travel 1 |  | Travel 2 |  | Travel 3
Boilermakers | Steam Boilers, Boiler House, Pressure Vessels | 35.3 | 34 | 69.3 | $ - | 0 - 120 mi | (Fed. Mileage) | 120 mi +
Brick, Block and Stone Masons |  | 32.32 | 16.78 | 49.1 | $ - | 0 - 70 mi | $60/day | 70 - 90 mi | $80/day | 90 mi +
Carpenters |  | 36.49 | 17.45 | 53.94 | $ - | 0 - 30 mi | 4 | 30 - 60 mi | 6 | 60 mi +
Cement Masons and Concrete Finishers |  | 38.54 | 17.04
Construction Equipment Operators, Group 1 | Hand tools, Grinder, Truck Crane, Forklift | 31.51 | 15.73 | 47.24 | $ - | 0 - 30 mi | 3.5 | 30 - 60 mi | 5.5 | 60 mi +
Construction Equipment Operators, Group 2 | Backhoe/Excavator/Shovel up to 3cy, Trencher | 32.88 | 15.15 | 48.03 | $ - | 0 - 30 mi | 3.5 | 30 - 60 mi | 5.5 | 60 mi +
Construction Equipment Operators, Group 3 | Paving, Backhoe/Excavator/Shovel over 3cy, Cranes (<24T), Scraper | 38 | 16.35 | 54.35 | $ - | 0 - 30 mi | 3.5 | 30 - 60 mi | 5.5 | 60 mi +
Construction Equipment Operators, Group 4 | Asphalt/Hot Plant Op, Crane (25-44T), Finish Scraper | 38 | 16.35 | 54.35 | $ - | 0 - 30 mi | 3.5 | 30 - 60 mi | 5.5 | 60 mi +
Construction Equipment Operators, Group 5 | Cranes (45-74T) | 38 | 16.35 | 54.35 | $ - | 0 - 30 mi | 3.5 | 30 - 60 mi | 5.5 | 60 mi +
Construction Equipment Operators, Group 6 | Cranes (75-149T), Whirley | 40 | 16.35 | 56.35 | $ - | 0 - 30 mi | 3.5 | 30 - 60 mi | 5.5 | 60 mi +
Construction Equipment Operators, Group 7 | Cranes (150-250T), Cranes (250T +, add $1/100T) | 42 | 16.35 | 58.35 | $ - | 0 - 30 mi | 3.5 | 30 - 60 mi | 5.5 | 60 mi +
Construction Laborers Group 1, Flag Person for Traffic Control |  | 23.08 | 11.82 | 34.9 | $ - | 0 - 30 mi | 3.05 | 30 - 60 mi | 4.85 | 60 mi +
Construction Laborers Group 2 | General Labor, Cement, Landscaper, Riprapper | 26.15 | 13.44 | 39.59 | $ - | 0 - 30 mi | 3.05 | 30 - 60 mi | 4.85 | 60 mi +
Construction Laborers Group 3 | Concrete Vibrator, Jackhammer, Rollers, Pipelayer | 26.07 | 13.44 | 39.51 | $ - | 0 - 30 mi | 3.05 | 30 - 60 mi | 4.85 | 60 mi +
Construction Laborers Group 4 | Water Well Laborer, Blaster, Cutting Torch, Power Saw | 26.76 | 11.82 | 38.58 | $ - | 0 - 30 mi | 3.05 | 30 - 60 mi | 4.85 | 60 mi +
Diver Tender | 2 hours pay per shift for dressing/undressing Diver in hyperbaric conditions | 47.55 | 16.05 | 63.6 | $ - | 0 - 30 mi | 4 | 30 - 60 mi | 6 | 60 mi +
Divers, Stand-By |  | 48.51 | 16.05 | 64.56 | $ - |  | 4 | 30 - 60 mi | 6 | 60 mi +
Divers, Diving | *See Prevailing Rates for Dive Depth Rates | 97.52 | 16.05 | 113.57 |  |  | 4 | 30 - 60 mi | 6 | 60 mi +
Electricians | *No Mileage due when traveling in employer's vehicle | 38.66 | 17.84 | 56.5 | $ - | 0-18 mi | (Fed. Mileage) | 18 - 60 mi | $75/day | 60 mi +
Insulations Workers - Mechanical (Heat & Frost) | *See Prevailing Rates for Travel over 50mi | 42.26 | 21.99 | 64.25 | $ - | 0 - 30 mi | $25/day | 30 - 40 mi | $35/day | 40 - 50 mi
Ironworkers - Reinforcing Iron and Rebar Workers | *See Prevailing Rates for Travel over 100mi | 34.83 | 28.07 | 62.9 | $ - | 0 - 45 mi | $50/day | 45 - 60 mi | $75/day | 60 - 100 mi
Ironworkers - Structural Iron and Steel Workers | *See Prevailing Rates for Travel over 100mi | 34.83 | 28.07 | 62.9 | $ - | 0 - 45 mi | $50/day | 45 - 60 mi | $75/day | 60 - 100 mi
Line Construction - Equipment Operators | All work on Substations | 38.56 | 17.93 | 56.49 | $60/day | All
Line Construction - Groundman | All work on Substations | 29.09 | 8.36 | 37.45 | $60/day | All
Line Construction - Lineman | All work on Substations | 52.11 | 18.75 | 70.86 | $60/day | All
Millwrights |  | 45.26 | 21.25 | 66.51 | $ - | 0 - 30 mi | 4 | 30 - 60 mi | 6 | 60 mi +
Painters |  | 25 |  | 25 | $ - | All
Pile Bucks | Set up crane/hammer, Cut piles to grade, direct crane | 36.49 | 14.33 | 50.82 | $ - | 0 - 30 mi | 4 | 30 - 60 mi | 6 | 60 mi +
Plumbers, Pipefitters and Steamfitters | Assemble, install, alter, repair pipe/pipe systems | 45.6 | 21.26 | 66.86 | $ - | 0 - 70 mi | $0.55/mi or $110/day | 70 mi+
Sprinker Fitters | All fire protection system work. *See Prevailing Rates for travel rates | 39.06 | 25.39 | 64.45
Truck Drivers |  | 31.28 | 9.37 | 40.65 | $ - | 0 - 30 mi | 3.05 | 30 - 60 mi | 4.85 | 60 mi +
Labor Related Costs- Site Management and Monitoring Programs
Third Party Construction Management Cost Reconciliation
| Category1 |  | DEQ Rates |  | *GSA/SMC 2025 Bond Labor Rates
| Project Manager |  | 230.55 |  | *Principal in Charge
| Project Engineer |  | 186.79 |  | *Project Manager
| Water Treatment Plant Operator/Field Engineer |  | 95.79
| Clerical and Administration |  | 82.66
| Mechanic |  | 51
| Laborers |  | 39.51
| Security Personnel |  | 40
Footnotes:
1. GSA Federal Supply Contractor Price List (2013-2014)
2. Eliminate high and low rates, average the balance
Care & Maintenance & Water Quality Sampling Oversight Team_3rd Party A&E
|  |  | Hourly Rate ($/hr) |  | Annual Salary ($/yr)
| Project Manager |  | 230.55 |  | 479544
| Project Engineer |  | 186.79 |  | 388523.2
| Clerical and Administration |  | 82.66 |  | 171932.8
| Water Treatment Plant Operator |  | 95.79 |  | 199243.2
| Mechanic |  | 51 |  | 106080
| Laborers |  | 39.51 |  | 82180.8
| Security Personnel |  | 40 |  | 83200
| CAD/Drafting |  | 91.68 |  | 190694.4
Note on H34: Abelmann, Christine: $0.55/mi if not consecutive days (not to exceed 2 trips), $110/day if consecutive days

## Equipment Rates 2025
Equipment Rates 2025 Costmine | [5 empty] | Fuel Consumption (Cat Handbook Vol.49 - 2019)
EQUIPMENT ID | SUBTYPE | SIZE CLASS | COMPARABLE MODEL | DEQ Costmine |  | LOW | MEDIUM | HIGH
[6 empty] | (U.S. gal/hr) | (U.S. gal/hr) | (U.S. gal/hr)
DOZERS
104 HP Dozer | 9.6 ft Blade Width | Cat D3K | D3K LGP | 49.16 |  | 1.8 | 2 | 4
205 HP Dozer | 10.7 ft Blade Width | Cat D5N | D5N LGP | 97.76 |  | 3.9 | 5.1 | 6.8
215 HP Dozer | 13.4 ft Blade Width | Cat D6T | D6T LGP | 92.68 |  | 5.9 | 7.6 | 9.4
265 HP Dozer | 12.1 ft Blade Width | Cat D7R | D7R DS LGP SERIES II | 146.07 |  | 6.5 | 8.2 | 9.9
350 HP Dozer | 13.0 ft Blade Width | Cat D8T | D8T | 166.29 |  | 9.1 | 11.7 | 14.3
600 HP Dozer | 16.2 ft Blade Width | Cat D10T | D10T2 | 312.43 |  | 14.9 | 19.4 | 23.9
850 HP Dozer | 21.0 ft Blade Width | Cat D11T | D11T | 312.43 |  | 22.8 | 29.6 | 36.4
EXCAVATORS
98 hp Backhoe | 0.44 CY Bucket, 18.0 ft Digging Depth | 12.1 - 14.0 MTons | 311F LRR / Cat 430 | 33.36 |  | 1.7 | 2.5 | 3.4
166 hp Backhoe | 1.2 CY Bucket, 22.1 ft Digging Depth | 21.1 - 24.0 MTons | 320F L | 56.34 |  | 3.5 | 4.9 | 7
177 hp Backhoe | 2.1 CY Bucket, 21.5 ft Digging Depth | 24.1 - 28.0 MTons | 324E L | 79.76 |  | 3.8 | 5.7 | 7.7
367 hp Backhoe | 2.98 CY Bucket, 24.4 ft Digging Depth | 33.1 - 40.0 MTons | 336F L | 126.92 |  | 5.4 | 8.1 | 10.7
463 hp Backhoe | 3.3 CY Bucket, 28.2 ft Digging Depth | 66.1 - 90.0 MTons | 365C L | 182.35
523 hp Backhoe | 4.7 - 7.3 CY Bucket, 35.7 ft Digging Depth |  | 374F | 248.51 |  | 12.2 | 14.5 | 18
LOADERS
74 hp Skidsteer | 2,900 lb Capacity | 1751 - 2200 lbs | 246D | 22.33 |  | 2 | 2.6 | 3.2
74 HP Loader | 1.2 CY Bucket | 70 - 79 HP | 906M | 25.8 |  | 1 | 1.5 | 2.5
74 HP Loader | 1.4 CY Bucket | 70 - 79 HP | 908M | 30.08 |  | 1 | 1.5 | 2.5
210 HP Loader | 4.2 CY Bucket | 175 - 199 HP | 938M | 63.79 |  | 1.6 | 2.5 | 3.3
250 HP Loader | 4.25 CY Bucket | 175 - 199 HP | 950M | 85.01 |  | 2.7 | 3.4 | 4.3
417 HP Loader | 7.5 CY Bucket | 275 - 349 HP | 980M | 125.22 |  | 4.9 | 6 | 7.6
536 HP Loader | 9.0 CY Bucket | 350 - 499 HP | 988K | 208 |  | 9 | 11.8 | 14.6
699 HP Loader | 11.2 CY Bucket | 500 - 999 HP | 990K | 301.53 |  | 15.4 | 19.8 | 24.2
2300 HP Loader | 53 CY Bucket | 1000 HP & Over | L2350 | 1315.95
SCRAPERS
407 HP Scraper | Single Engine, Elevating, 23 CY, 27.6 st Capacity | 18 & Under 30CY | 623G | 185.83 |  | 11.4 | 14.4 | 18
407 HP Scraper | Tandam, 24 CY, 28.8 st Capacity | Under 18CY | 627G P-P | 198.69 |  | 16.3 | 21.5 | 28.2
462 HP Scraper | Tandam, 31 CY, 37.0 st Capacity | 18CY & Over | 631K | 250.9 |  | 12.3 | 15.9 | 21
564 HP Scraper | Tandam, 44 CY, 52.0 st Capacity | 18CY & Over | 637G | 318.85 |  | 19 | 25.1 | 32.8
SHOVELS
760 HP Shovel | 8.5 CY Bucket | 90.1 - 150.0 MTons | EX1200-6 | 347.87
3000 HP Shovel | 38.0 CY Bucket | 400.1 MTons & Over | PC5500-6 | 2042.75
1000 HP Shovel | 15.7 CY Bucket |  | 6040B | 669.49 | Verify
TRACK LOADER
155 HP Track Loader | 2.4 CY Bucket | 130 - 189 HP | 953K | 89.6 |  | 3.1 | 4.4 | 5.7
194 HP Track Loader | 3.2 CY Bucket | 130 - 189 HP | 963K | 119.38 |  | 4 | 5.9 | 8.1
275 HP Track Loader | 4.2 CY Bucket | 190 HP & Over | 973K | 187.29 |  | 5.1 | 8.1 | 11.1
OFF-HIGHWAY ARTICULATED REAR DUMP
321 HP Articulated Rear Dump | 26.5 st / 19.6 CY | 20 - 25 MTons | 725C | 53.12 |  | 3.9 | 6.2 | 7.8
345 HP Articulated Rear Dump | 31.0 st / 22.9 CY | 26 - 29 MTons | 730C | 62.53 |  | 4.1 | 6.6 | 8.2
455 HP Articulated Rear Dump | 41.0 st / 30.0 CY | 35 MTons & Over | 740B | 77.89 |  | 6 | 9.5 | 11.9
OFF-HIGHWAY REAR DUMP
42.1 ST Rear Dump, Rigid | 508 HP | 30 - 39 MTons | 770G | 90.54 |  | 4.3 | 5.6 | 7.1
51.6 ST Rear Dump, Rigid | 550 HP | 40 - 54 MTons | 772G | 102.22 |  | 4.7 | 6.3 | 8.4
60 ST Rear Dump, Rigid | 775 HP | 40 - 54 MTons | 773G | 125.19 |  | 7.3 | 9.2 | 11.3
70 ST Rear Dump, Rigid | 760 HP | 55 - 74 MTons | 775G | 124.62 |  | 7.5 | 9.4 | 12.3
101.6 ST Rear Dump, Rigid | 1200 HP | 90 - 104 MTons | 777G | 195.9 |  | 12.1 | 15 | 19
238 ST Rear Dump, Rigid, Elec. | 2500 HP | 200 MTons & Over | 830E | 539.58
205 ST Rear Dump, Rigid, Elec | 2000 HP | 169.5 - 199.4 Mtons | 730E | 313.23
ON-HIGHWAY REAR DUMP
16-18 CY Highway Rear Dump | 16ft Dump Truck, Class 8 | 60,001 GVW & Over | 6X4 18YD 70KGVW | 52.62
20-22 CY Highway Rear Dump | 20ft Dump Truck, Class 8 | 60,001 GVW & Over | 8X4 18YD 85KGVW | 59.33
7 CY Highway Rear Dump | 10ft Dump Truck, Class 7 | 19,501 - 26,000 GVW | 4X2 6YD DSL | 39.76
LUBE TRUCK
1000 gal Diesel/Lube Truck | 300 HP | To 199 HP | BB2 DSL 4X2 3000 | 50.46
2000 gal Diesel/Lube Truck | 350 HP | 200 HP & Over | DSL 6X4 3500 | 64.59
PICKUP TRUCKS
Utility Truck, Tilting Flatbed Truck | On-Highway Light Duty Trucks | 330 HP | 4X2 1/2 260 EXT DIESEL | 22.14
1 Ton, Crew Cab Pickup Truck | On-Highway Light Duty Trucks | 470 HP | 4X2 1 195 CREW DSL | 27.48
3/4 Ton, Extra Cab Pickup Truck | On-Highway Light Duty Trucks | 470 HP | 4X4 3/4 445 CONV DIESEL | 25.66
GRADERS
12 ft AWD Grader | Articulated Frame Graders | 225 HP | 120M | 96.87 |  | 2.1 | 3.5 | 4.9
12 ft Grader | Articulated Frame Graders | 215 HP | 12M | 84.51 |  | 2.3 | 3.8 | 5.3
14 ft AWD Grader | Articulated Frame Graders | 275 HP | 140M | 111.9 |  | 3.2 | 5.3 | 7.4
14 ft Grader | Articulated Frame Graders | 255 HP | 14M | 97.06 |  | 3.3 | 5.6 | 7.8
16 ft AWD Grader | Articulated Frame Graders | 300 HP | 160M | 121.66 |  | 3.4 | 5.6 | 7.8
16 ft Grader | Articulated Frame Graders | 280HP | 16M | 105.72 |  | 4.4 | 7.3 | 10.2
FUEL TRUCK
2,000 Gal Truck | On-Highway Water Tankers | 270 HP | DSL 4X2 3000
4,000 Gal Truck | On-Highway Water Tankers | 250 HP | DSL 6X4 3500
COMPACTORS
84" wide x 61" dia Padfoot Roller | Self Propelled Pad Foot Compactors | 176 HP | 815K | 70.33 |  | 8 | 11 | 12.5
84" wide x 65" dia Smooth Roller | Self Propelled Smooth Drum Compactors | 174 HP | 816F | 64.26 |  | 8 | 11 | 12.5
OFF-HIGHWAY WATER TANKER
5,000 gal Water Truck | Articulated Truck Chassis | 334 HP | 5000 150 | 54.21
8,000 gal Water Truck | Articulated Truck Chassis | 439 HP | 7000 330 | 75.28
ON-HIGHWAY WATER TANKER
2,000 gal Water Truck | On-Highway Water Tanker Trucks | 270 HP | DSL 4X2 2500 | 31.29
4,000 gal Water Truck | On-Highway Water Tanker Trucks | 250 HP | DSL 6X4 3500 | 33.1
ON-HIGHWAY FLATBED
Class 5 Flatbed Truck | On-Highway Flatbed Trucks | 16,001 - 19,500 lb | 4X2 15KGVW DSL | 26.78
Class 6 Flatbed Truck | On-Highway Flatbed Trucks | 19,501 - 26,000 lb | 4X2 30KGVW DSL | 26.38
Class 7 Flatbed Truck | On-Highway Flatbed Trucks | 26,001 - 33,000 lb | 6X4 45KGVW DSL | 25.53
ON-HIGHWAY TRACK TRACTOR
24 ft Equipment Hauler Trailer | On Highway Equipment Hauler Trailer | 12 ST capacity |  | 1.45
25 ft Equipment Hauler Trailer | On Highway Equipment Hauler Trailer | 22.5 ST capacity |  | 2.53
30 ft Equipment Hauler Trailer | On Highway Equipment Hauler Trailer | 31 ST capacity |  | 3.09
26 CY Rear Dump Hauler Trailer | Requires 330 HP Tractor | 33 ST capacity |  | 16.58
32 CY Rear Dump Hauler Trailer | Requires 450 HP Tractor | 40 ST capacity |  | 22.39
MISCELLANEOUS TRUCKS
ANFO Loader Delivery Truck (11,264 lb capacity) |  | 380 HP |  | 242.24
Seeder - 77 lb Capacity ATV Mounted |  |  |  | 0.03
Seeder - 750 lb Capacity Tractor Mounted | Trailer Mounted Seed Sprayers | 3 pt Hitch |  | 0.28
Seeder - 2,440 lb Capacity Tractor Mounted | Seed Sprayers For Truck Mounting | 3 pt Hitch |  | 0.68
Power Mulcher/Chipper/Shredder | Trailer Mounted Mulchers | 7" max diameter |  |  | 5.7
Impact Hammer / Breaker |  |  |  | 40.07
Telehandler - 42.3 ft Lift |  | 6,000 lb Capacity, 74 HP |  |  | 33.73
UNDERGROUND MINING - LHD's (Load-Haul-Dumps)
2.5 CY LHD - Diesel |  | 130 HP |  | 142.42
5.9 CY LHD - Diesel |  | 250 HP | Cat 1600 LHD | 238.61 |  | 4.1 | 5.2 | 6.9
8.4 CY LHD - Diesel |  | 335 HP |  | 289.4 |  | 5.3 | 7.1 | 8.9
10.3 CY LHD - Diesel |  | 472 HP |  | 383.67 |  | 6.1 | 8.1 | 10.1
UNDERGROUND MINING - ARTICULATED TRUCKS
22 ton Rear Dump Articulated Truck |  | 300 HP |  | 99.2 |  | 3.6 | 5.4 | 7.2
46 ton Rear Dump Articulated Truck |  | 535 HP |  | 253.98 |  | 5.9 | 8.8 | 11.7

## Graphs
Project Management Fee
Project size of site | Percentage of Direct Costs
Project managed by State Agency | 0%
< 90 Acres (including other facilities) | 6%
Between 90-700 Acres | 5%
> 700 Acres | 3%